This Strategic Action Plan operationalizes the Kuwait NEDMP and its Implementation Plan through coded actions, tasks, responsibilities, indicative timing, resources, KPIs, targets, verification, dependencies and risk controls. Proposed responsibilities and dates require validation by the competent national authorities.

Institutional names follow the source documents, which use Environment Public Authority, Kuwait Environment Public Authority, EPA and KEPA. This report uses Environment Public Authority / Kuwait Environment Public Authority (EPA/KEPA) when a proposed coordinating role requires clarity.

Acknowledgements

The plan draws on the consolidated NEDMP, its eight principal evidence reports and the supplied Implementation Plan. It reflects national consultation, diagnostic assessment, benchmarking, data classification and governance recommendations prepared through the Kuwait NEDMP process.

Executive Summary

The Strategic Action Plan is the operational bridge between the NEDMP Implementation Plan and annual institutional workplans. The NEDMP defines the national strategic direction; the Implementation Plan defines governance, workstreams, sequencing, resources, risk and monitoring; this document identifies the specific actions, tasks, milestones, responsibilities and performance evidence required to deliver them.

The action register contains 30 actions organized under the five approved pillars, supported by 90 tasks, 60 milestones, 30 KPI records and action-level risks and dependencies. Governance and standards precede dependent technology and publication actions. All proposed bodies and responsibilities are explicitly subject to national confirmation.

The diagnostic baseline confirms an active environmental data production system but identifies a governance gap: overall data availability is 70.9 per cent, the documented data gap is 29.1 per cent, interoperability readiness is 74.1 per cent, data-quality readiness is 73.4 per cent and governance readiness is 57.6 per cent. Full public availability is 18.8 per cent, while sensitivity and legal restrictions remain major access constraints.

The proposed horizon is 2027-2031 and is indicative, subject to national approval. Early actions establish governance, focal points, dataset ownership, the national registry, classification, metadata, QA/QC, legal review and security baselines. Integration pilots, portal services, public information and advanced analytics follow only after those decision gates are met.

The accompanying Excel workbook is the live monitoring instrument. It provides an executive dashboard, master action plan, task register, schedule, Gantt chart, milestones, responsibilities, RACI, resources, budgets, KPIs, targets, status, risks, dependencies, corrective actions, reporting and traceability sheets.

| Indicator | Value | Implementation interpretation | Data bar |
| --- | --- | --- | --- |
| Overall data availability | 70.9% | Build on an active production base while closing documented gaps. | ¦¦¦¦¦¦¦ 70.9% |
| Environmental data gap | 29.1% | Prioritize dataset inventory, gap closure and recurring updates. | ¦¦¦ 29.1% |
| Interoperability readiness | 74.1% | Move from active exchange to governed, machine-readable recurrent flows. | ¦¦¦¦¦¦¦ 74.1% |
| Data quality readiness | 73.4% | Convert partial quality practice into mandatory QA/QC and metadata controls. | ¦¦¦¦¦¦¦ 73.4% |
| Governance readiness | 57.6% | Treat governance, stewardship, decision rights and SOPs as first implementation priority. | ¦¦¦¦¦¦ 57.6% |

Figure 1. Source-derived readiness baseline for the Strategic Action Plan

Source: S4III p. 5; S6 pp. 16, 21, 32.

Table of Contents

Chapter 1. Introduction	13

1.1 Background	13

1.2 Purpose of the Strategic Action Plan	13

1.3 Scope	13

1.4 Intended users	13

1.5 Relationship with the NEDMP	13

1.6 Relationship with the Implementation Plan	13

1.7 Relationship with annual institutional workplans	13

1.8 Action-plan period	13

1.9 Methodology	13

1.10 Evidence base	13

1.11 Assumptions and limitations	13

Chapter 2. NEDMP Strategic Alignment	14

2.1 Mandate	14

2.2 Vision	14

2.3 Strategic objectives	14

2.4 Foundational pillars	14

2.5 Expected strategic outcomes	14

2.6 Alignment with Kuwait Vision 2035	14

2.7 Alignment with the Kuwait National Development Plan	15

2.8 Alignment with Environment Protection Law No. 42 of 2014	15

2.9 Alignment with GEDS, SDGs and relevant international frameworks	15

2.10 Relationship between objectives, pillars and actions	15

Chapter 3. Diagnostic Basis for Action	18

3.1 National environmental data baseline	18

3.2 KEPA/EPA diagnostic findings	20

3.3 All-stakeholder findings	20

3.4 Priority challenges	20

3.5 Root-cause analysis	20

3.6 Challenge-to-objective mapping	20

3.7 Challenge-to-action mapping	20

3.8 Implementation readiness	21

3.9 Priority-setting methodology	21

Chapter 4. Action-Planning Framework	22

4.1 Results hierarchy	22

4.2 Action coding	22

4.3 Action categories	22

4.4 Prioritization criteria	22

4.5 Responsibility model	22

4.6 Status model	22

4.7 Timeline model	22

4.8 Resource model	22

4.9 KPI and target methodology	22

4.10 Reporting and verification approach	22

Chapter 5. Pillar 1 Strategic Actions	23

5.1 Pillar objective and expected outcome	23

5.2 Challenges addressed	23

5.3 Programme and action summary	23

5.4 Detailed actions	25

SO1-P1-PR1-A01 | Endorse the NEDMP implementation instruments and governance charter	25

SO1-P1-PR2-A02 | Activate the NEDMP programme management and coordination function	25

SO1-P1-PR3-A03 | Establish the institutional environmental data focal-point network	25

SO1-P1-PR4-A04 | Assign data owners, stewards and custodians for priority datasets	25

SO1-P1-PR5-A05 | Complete the environmental data legal and policy gap assessment	25

SO1-P1-PR6-A06 | Approve the core governance policy, SOP and data-sharing instrument package	25

Chapter 6. Pillar 2 Strategic Actions	27

6.1 Pillar objective and expected outcome	27

6.2 Challenges addressed	27

6.3 Programme and action summary	27

6.4 Detailed actions	29

SO2-P2-PR1-A01 | Complete the national environmental dataset inventory and registry	29

SO2-P2-PR2-A02 | Approve the priority and authoritative dataset list and indicator catalogue	29

SO2-P2-PR3-A03 | Issue the national environmental metadata profile, dictionaries and vocabularies	29

SO2-P2-PR4-A04 | Implement minimum QA/QC, validation and reliability grading	29

SO2-P2-PR5-A05 | Establish version control, provenance, traceability and methodology records	29

SO2-P2-PR6-A06 | Implement data-quality improvement and priority gap-closure plans	29

Chapter 7. Pillar 3 Strategic Actions	31

7.1 Pillar objective and expected outcome	31

7.2 Challenges addressed	31

7.3 Programme and action summary	31

7.4 Detailed actions	33

SO3-P3-PR1-A01 | Complete the systems inventory, digital-readiness assessment and target architecture	33

SO3-P3-PR2-A02 | Approve the national environmental data interoperability framework	33

SO3-P3-PR3-A03 | Establish identity, cybersecurity, backup and business-continuity controls	33

SO3-P3-PR4-A04 | Pilot governed recurrent data flows linked to eMISK	33

SO3-P3-PR5-A05 | Approve and implement the National Environmental Data Portal operating model	33

SO3-P3-PR6-A06 | Scale integration, migration, service management and technology renewal	33

Chapter 8. Pillar 4 Strategic Actions	35

8.1 Pillar objective and expected outcome	35

8.2 Challenges addressed	35

8.3 Programme and action summary	35

8.4 Detailed actions	37

SO4-P4-PR1-A01 | Operationalize the five-level environmental data classification model	37

SO4-P4-PR2-A02 | Implement access request, approval, release, licensing and appeal workflows	37

SO4-P4-PR3-A03 | Operate a publication-readiness and open environmental data calendar	37

SO4-P4-PR4-A04 | Develop national environmental dashboards, maps and information services	37

SO4-P4-PR5-A05 | Standardize national, SDG, MEA and State of the Environment reporting workflows	37

SO4-P4-PR6-A06 | Operate user feedback, data correction, researcher access and data-use monitoring	37

Chapter 9. Pillar 5 Strategic Actions	39

9.1 Pillar objective and expected outcome	39

9.2 Challenges addressed	39

9.3 Programme and action summary	39

9.4 Detailed actions	41

SO5-P5-PR1-A01 | Complete institutional capacity, staffing and training-needs assessments	41

SO5-P5-PR2-A02 | Approve the NEDMP competency framework and role-based learning pathways	41

SO5-P5-PR3-A03 | Deliver and certify role-based NEDMP training	41

SO5-P5-PR4-A04 | Establish train-the-trainer, communities of practice and knowledge management	41

SO5-P5-PR5-A05 | Establish multi-year resource, costing and financing arrangements	41

SO5-P5-PR6-A06 | Institutionalize monitoring, adaptive management, succession and responsible AI readiness	41

Chapter 10. Cross-Cutting Actions	43

Chapter 11. Institutional Responsibilities	46

11.1 Governance and oversight	46

11.2 Programme management	46

11.3 Institutional focal points	46

11.4 Data owners and stewards	46

11.5 Technical working groups	46

11.6 Participating institutions	46

11.7 Decision rights	46

11.8 Accountability and escalation	46

11.9 RACI matrix	46

Chapter 12. Implementation Schedule	48

12.1 Action-plan horizon	48

12.2 Implementation phases	48

12.3 Immediate actions	48

12.4 Short-term actions	48

12.5 Medium-term actions	48

12.6 Long-term actions	48

12.7 Quick wins	48

12.8 Milestones	48

12.9 Dependencies	48

12.10 Critical path	48

12.11 Consolidated Gantt chart	48

Chapter 13. Resources and Financing	51

13.1 Human resources	51

13.2 Institutional resources	51

13.3 Technical resources	51

13.4 Capital requirements	51

13.5 Recurrent requirements	51

13.6 Indicative costing method	51

13.7 Multi-year resource profile	51

13.8 Potential funding sources	51

13.9 Funding gaps	51

13.10 Budget preparation responsibilities	51

13.11 Financial sustainability	51

Chapter 14. KPI and Target Framework	53

14.1 Results-measurement approach	53

14.2 Impact indicators	53

14.3 Outcome indicators	53

14.4 Output indicators	53

14.5 Process indicators	53

14.6 Baselines	53

14.7 Annual targets	53

14.8 Final targets	53

14.9 Data collection	53

14.10 Means of verification	53

14.11 Reporting responsibilities	53

14.12 KPI register	53

Chapter 15. Status Monitoring and Reporting	55

15.1 Status definitions	55

15.2 Percentage-completion method	55

15.3 Traffic-light reporting	55

15.4 Monthly or quarterly implementation reporting	55

15.5 Annual progress report	55

15.6 Management dashboard	55

15.7 Issue escalation	55

15.8 Corrective-action tracking	55

15.9 Change-control process	55

Chapter 16. Risks, Dependencies and Assumptions	57

16.1 Risk-management approach	57

16.2 Strategic risks	57

16.3 Institutional risks	57

16.4 Technical risks	57

16.5 Financial risks	57

16.6 Capacity risks	57

16.7 Cybersecurity risks	57

16.8 Dependencies	57

16.9 Assumptions	57

16.10 Risk register	57

16.11 Risk heatmap	57

Chapter 17. Review and Adaptive Management	59

17.1 Quarterly review	59

17.2 Annual review	59

17.3 Mid-term review	59

17.4 Final evaluation	59

17.5 Target revision	59

17.6 Action reprioritization	59

17.7 Lessons learned	59

17.8 Preparation of annual workplans	59

17.9 Preparation of the next action-plan cycle	59

Annexes	61

Annex A. Consolidated Strategic Action Matrix - identity and results	62

Annex A continued. Governance, schedule and status	67

Annex A continued. Resources, performance and risk	75

Annex B. Detailed Task Register	83

Annex C. NEDMP Objectives-Pillars-Actions Matrix	98

Annex D. Challenge-to-Action Traceability Matrix	102

Annex E. RACI Matrix	105

Annex F. Institutional Responsibilities Matrix	108

Annex G. Five-Year Gantt Chart	113

Annex H. Annual Milestone Schedule	117

Annex I. Dependency and Critical-Path Matrix	121

Annex J. Resource Requirements Matrix	126

Annex K. Indicative Budget Template	132

Annex L. KPI Register	135

Annex M. KPI Metadata Sheets	139

Annex N. Annual Target Matrix	146

Annex O. Status Reporting Template	150

Annex P. Quarterly Progress Report Template	151

Annex Q. Corrective Action Log	152

Annex R. Risk Register	153

Annex S. Assumptions Log	158

Annex T. Decision and Issue Log	159

Annex U. Source-Evidence Traceability Matrix	160

Annex V. Glossary	164

Annex W. References	165

List of Acronyms, Abbreviations and Codes

| Code | Meaning |
| --- | --- |
| A | Action code; in RACI, Accountable |
| A/R | RACI role code meaning Accountable and Responsible |
| A/R/C/I | RACI table role codes: Accountable / Responsible / Consulted / Informed |
| AI | Artificial intelligence |
| API | Application programming interface |
| AS | Assumption-log record code |
| CA | Corrective-action record code |
| CSB | Central Statistical Bureau |
| DAMA | Data Management Association International |
| DAMA-DMBOK | Data Management Body of Knowledge |
| DI | Decision and issue log record code |
| DMBOK | Data Management Body of Knowledge |
| DR | Disaster recovery |
| EC | European Commission |
| eMISK | Environmental Monitoring Information System of Kuwait |
| EPA | Environment Public Authority |
| EPA/KEPA | Environment Public Authority / Kuwait Environment Public Authority |
| FAIR | Findable, Accessible, Interoperable and Reusable |
| FDES | Framework for the Development of Environment Statistics |
| GEDS | Global Environmental Data Strategy |
| GIS | Geographic information system |
| ICT | Information and communications technology |
| ID | Identifier |
| IEA | Integrated environmental assessment |
| INSPIRE | Infrastructure for Spatial Information in the European Community |
| IP | Kuwait NEDMP Implementation Plan supplied with this assignment |
| ISO | International Organization for Standardization |
| ISO/IEC | International Organization for Standardization / International Electrotechnical Commission |
| IT | Information technology |
| KEPA | Kuwait Environment Public Authority, used in source documents alongside EPA |
| KEPA/EPA | Kuwait Environment Public Authority / Environment Public Authority, an ordering used in some source headings |
| KEPA/UNEP | Kuwait Environment Public Authority / United Nations Environment Programme |
| KISR | Kuwait Institute for Scientific Research |
| KNDP | Kuwait National Development Plan |
| KPI | Key performance indicator |
| M | Milestone code |
| M&E | Monitoring and evaluation |
| MEA | Multilateral environmental agreement |
| MoU | Memorandum of understanding |
| NEDMP | Kuwait National Environmental Data Management Plan (consolidated strategic document) |
| P1.1-P5.4 | Implementation programme codes; P means Programme, the first number maps to the related workstream/pillar and the decimal number is the programme sequence |
| PMO | Programme management office |
| PR | Implementation programme code |
| QA/QC | Quality assurance and quality control |
| RACI | Responsible, Accountable, Consulted and Informed |
| RAG | Red-Amber-Green traffic-light status |
| RBM | Results-based management |
| S1 | Section I - Mandate, Vision, Objectives and Pillars |
| S2 | Section II - Alignment with National and International Frameworks |
| S3 | Section III - Benchmarking Best Practices |
| S4I | Section IV Part I - Current State of National Environmental Data |
| S4II | Section IV Part II - EPA/KEPA Department Assessment |
| S4III | Section IV Part III - All-Stakeholder Assessment |
| S6 | NEDMP Data Classification and Governance Framework |
| SDG | Sustainable Development Goal |
| SDMX | Statistical Data and Metadata eXchange |
| SEEA | System of Environmental-Economic Accounting |
| SEIS | Shared Environmental Information System |
| SO | Strategic objective |
| SO1-SO5 | NEDMP strategic objective codes 1 to 5 |
| SOE | State of the Environment |
| SOP | Standard operating procedure |
| T | Task or sub-task code |
| TBD | To be determined through baseline confirmation or detailed costing |
| TOR | Terms of reference |
| UN | United Nations |
| UNEA-7 | Seventh session of the United Nations Environment Assembly |
| UNEP | United Nations Environment Programme |
| WESR | World Environment Situation Room |
| WS | Workstream |
| WS1-WS5 | NEDMP implementation workstream codes 1 to 5 |
| Y1-Y5 | Year 1 to Year 5 of the proposed action-plan horizon |

List of Figures

Figure 1. Source-derived readiness baseline for the Strategic Action Plan	2

Figure 2. Relationship between NEDMP instruments and annual workplans	13

Figure 3. NEDMP strategy-to-action hierarchy	16

Figure 4. NEDMP objectives-to-pillars-to-actions flow	17

Figure 5. Challenge-to-action response framework	20

Figure 6. Action prioritization matrix	21

Figure 7. Five-pillar action architecture	22

Figure 8. Cross-cutting controls across the five pillars	45

Figure 9. Institutional responsibility structure	46

Figure 10. RACI responsibility model	47

Figure 11. Implementation phases	48

Figure 12. Milestone roadmap	49

Figure 13. Critical-path diagram	50

Figure 14. Resource mobilization framework	52

Figure 15. KPI and target hierarchy	54

Figure 16. Status and traffic-light dashboard	55

Figure 17. Monitoring and reporting cycle	56

Figure 18. Risk heatmap	58

Figure 19. Adaptive-management feedback loop	60

List of Tables

Table 1. Approved NEDMP strategic objectives	14

Table 2. Approved NEDMP foundational pillars	14

Table 3. National implementation baseline	19

Table 4. Priority diagnostic challenge themes	20

Table 5. Challenge-to-action summary	20

Table 6. Status and traffic-light model	22

Table 7. Pillar 1 strategic action matrix	24

Table 8. Pillar 2 strategic action matrix	28

Table 9. Pillar 3 strategic action matrix	32

Table 10. Pillar 4 strategic action matrix	36

Table 11. Pillar 5 strategic action matrix	40

Table 12. Cross-cutting action responsibilities	44

Table 13. Strategic responsibility summary	46

Table 14. Strategic Action Plan implementation phases	48

Table 15. Resource requirements by category	51

Table 16. KPI framework summary	53

Table 17. Strategic risk-category summary	57

Table 18. Consolidated Strategic Action Matrix, block 1	62

Table 19. Consolidated Strategic Action Matrix, block 2	67

Table 20. Consolidated Strategic Action Matrix, block 3	75

Table 21. Detailed task register	83

Table 22. Objectives, pillars and actions	98

Table 23. Challenge-to-action traceability	102

Table 24. Strategic action RACI matrix	105

Table 25. Institutional responsibilities	108

Table 26. Five-year action schedule	113

Table 27. Annual milestone schedule	117

Table 28. Dependencies and critical path	121

Table 29. Resource requirements	126

Table 30. Indicative budget template	132

Table 31. KPI register	135

Table 32. KPI metadata sheets	139

Table 33. Annual target matrix	146

Table 34. Status reporting template	150

Table 35. Quarterly progress report template	151

Table 36. Corrective action log template	152

Table 37. Action-level risk register	153

Table 38. Assumptions log template	158

Table 39. Decision and issue log template	159

Table 40. Source-evidence traceability	160

Table 41. Strategic Action Plan glossary	164

Table 42. References	165

List of Boxes

Box 1. Source reconciliation note	13

Box 2. Consolidated NEDMP vision - reproduced verbatim	14

# Chapter 1. Introduction

This chapter positions the Strategic Action Plan within the NEDMP document hierarchy and defines its scope, users, period, evidence base and limitations.

## 1.1 Background

The State of Kuwait has established the NEDMP strategic framework and an Implementation Plan covering governance, quality, interoperability, access, capacity, resources, risk and monitoring. This Strategic Action Plan converts that architecture into a coded operational register.

## 1.2 Purpose of the Strategic Action Plan

The purpose is to specify what must be done, why it is required, who is accountable, when it should be completed, what resources are needed and how results will be verified.

## 1.3 Scope

The plan covers national environmental data governance, datasets, systems, access, reporting, capacity, financing, security, monitoring and institutionalization across the five approved NEDMP pillars.

## 1.4 Intended users

Primary users are senior decision-makers, EPA/KEPA coordination functions, participating institutions, proposed NEDMP governance bodies, programme managers, data owners, stewards, technical teams and monitoring personnel.

## 1.5 Relationship with the NEDMP

The NEDMP remains the controlling strategic instrument for the mandate, vision, objectives, pillars and intended strategic outcomes.

## 1.6 Relationship with the Implementation Plan

The supplied Implementation Plan provides the workstreams, programme architecture, governance model, sequencing, resource logic, risk framework and monitoring approach operationalized here.

## 1.7 Relationship with annual institutional workplans

Annual workplans should select approved actions and tasks from this register, confirm named units, budgets and procurement packages, and report against the same codes.

## 1.8 Action-plan period

The proposed horizon is 1 January 2027 to 31 December 2031 and is subject to national approval. Dates are planning assumptions, not approved government commitments.

## 1.9 Methodology

The methodology reconciled the strategic NEDMP, the eight source reports and the supplied Implementation Plan, then mapped each challenge to objectives, pillars, actions, tasks, responsibilities, milestones, resources, KPIs, risks and source evidence.

## 1.10 Evidence base

Kuwait-specific evidence is drawn from the uploaded NEDMP documents. International standards are used as implementation references and not presented as national legal obligations unless formally adopted.

## 1.11 Assumptions and limitations

No exact budget is invented. Responsibilities remain proposed where the sources do not confirm a mandate. Baselines that depend on a national register are accompanied by Year 1 baseline tasks.

| Strategic NEDMP | Implementation Plan | Strategic Action Plan | Annual workplans |
| --- | --- | --- | --- |
| Mandate, vision, objectives and pillars | Governance, workstreams, phases, resources and risk | Actions, tasks, milestones, responsibilities, KPIs and targets | Approved yearly assignments, budgets, procurement and reporting |

Figure 2. Relationship between NEDMP instruments and annual workplans

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

Box 1. Source reconciliation note

The consolidated NEDMP wording controls the formal vision reproduced in Chapter 2. Section I contains a longer earlier formulation. The two are not merged; the consolidated statement is retained and the extended wording is treated as supporting context. Diagnostic statistics use the all-stakeholder assessment and classification governance framework values because they form the most complete implementation baseline in the latest source set.

# Chapter 2. NEDMP Strategic Alignment

The action plan retains the approved NEDMP architecture and links every action to a strategic objective, primary pillar, challenge, programme, deliverable, KPI and target.

## 2.1 Mandate

The mandate is grounded in Environment Protection Law No. 42 of 2014, Kuwait Vision 2035, the Kuwait National Development Plan and national and international environmental reporting requirements, as summarized in the NEDMP source documents (NEDMP pp. 6-7; S1 p. 7; S2 pp. 14-16).

## 2.2 Vision

Box 2. Consolidated NEDMP vision - reproduced verbatim

The NEDMP vision is to establish an integrated, reliable and interoperable national environmental data management system that unifies environmental datasets, improves quality and accessibility, strengthens transparency and enables evidence-based policy-making. Controlling source: consolidated NEDMP, p. 8. The longer Section I vision statement is recorded in the source reconciliation annex.

## 2.3 Strategic objectives

Table 1. Approved NEDMP strategic objectives

| Code | Approved objective |
| --- | --- |
| SO1 | Institutionalize Environmental Data Governance |
| SO2 | Ensure High-Quality and Standardized Environmental Data |
| SO3 | Enable Interoperability and System Integration |
| SO4 | Strengthen Data Sharing, Accessibility and Transparency |
| SO5 | Build Sustainable National Capacities |

## 2.4 Foundational pillars

Table 2. Approved NEDMP foundational pillars

| Code | Approved pillar | Action-plan outcome |
| --- | --- | --- |
| Pillar 1 | Data Governance and Institutional Management | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. |
| Pillar 2 | Data Quality | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. |
| Pillar 3 | Data Interoperability and System Integration | Priority environmental data flows move securely between systems through agreed standards and governed integration services. |
| Pillar 4 | Data Sharing, Accessibility and Transparency | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. |
| Pillar 5 | Capacity Development and Sustainability | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. |

## 2.5 Expected strategic outcomes

The five action-plan outcomes operationalize the five strategic objectives. Completion requires both deliverables and verified institutional use; a document, platform module or training event alone is not treated as an outcome.

## 2.6 Alignment with Kuwait Vision 2035

Actions strengthen effective government, digital transformation, knowledge-based development, environmental sustainability and evidence-based planning.

## 2.7 Alignment with the Kuwait National Development Plan

The coded register links delivery, responsible roles, resources, risks, KPIs and annual review to national planning and performance management.

## 2.8 Alignment with Environment Protection Law No. 42 of 2014

Actions support environmental information systems, monitoring, coordination, reporting and safeguarded data exchange. Legal interpretation and formal responsibility remain with the competent authorities.

## 2.9 Alignment with GEDS, SDGs and relevant international frameworks

The plan applies GEDS pillars on management, quality and provenance, interoperability, accessibility and affordability, and capacity-building. It also uses FDES, SEEA, SDMX, FAIR, SEIS, ISO and INSPIRE as implementation references.

## 2.10 Relationship between objectives, pillars and actions

Each primary pillar aligns with its corresponding strategic objective, while secondary dependencies record cross-pillar requirements such as governance, quality, security and capacity.

| Mandate | Vision | Objective | Pillar | Programme | Action | Task | KPI and target |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Law and national priorities | Approved NEDMP direction | SO1-SO5 | Pillar 1-Pillar 5 | PR1-PR6 | Coded action | Assignable task | Verified result |

Figure 3. NEDMP strategy-to-action hierarchy

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

| SO1 / Pillar 1 | SO2 / Pillar 2 | SO3 / Pillar 3 | SO4 / Pillar 4 | SO5 / Pillar 5 |
| --- | --- | --- | --- | --- |
| Governance actions | Quality actions | Interoperability actions | Sharing and transparency actions | Capacity and sustainability actions |

Figure 4. NEDMP objectives-to-pillars-to-actions flow

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 3. Diagnostic Basis for Action

The action register responds directly to validated gaps and implementation requirements. No major diagnostic challenge is left without a linked action.

## 3.1 National environmental data baseline

Table 3. National implementation baseline

| Indicator | Baseline | Implementation meaning | Source |
| --- | --- | --- | --- |
| Overall data availability | 70.9% | Build on an active production base while closing documented gaps. | S4III p. 5; S6 p. 21 |
| Environmental data gap | 29.1% | Prioritize dataset inventory, gap closure and recurring updates. | S4III p. 5; S6 p. 21 |
| Interoperability readiness | 74.1% | Move from active exchange to governed, machine-readable recurrent flows. | S4III p. 5; S6 p. 21 |
| Data quality readiness | 73.4% | Convert partial quality practice into mandatory QA/QC and metadata controls. | S4III p. 5; S6 p. 21 |
| Governance readiness | 57.6% | Treat governance, stewardship, decision rights and SOPs as first implementation priority. | S4III p. 5; S6 p. 21 |
| Full public availability | 18.8% | Use classification and publication-readiness rules before scaling open data. | S6 p. 16 |
| Institutions with formal accessibility policies | 78.1% | Harmonize existing policies through national access procedures. | S6 p. 21 |
| Data sensitivity as access constraint | 80.6% | Integrate aggregation, anonymization, classification and approval pathways. | S6 p. 32 |
| Legal restrictions as access constraint | 63.3% | Embed legal review and documented release decisions into access workflows. | S6 p. 32 |

## 3.2 KEPA/EPA diagnostic findings

The department assessment identifies operational data production and system capabilities alongside gaps in coordination, metadata, QA/QC, SOPs, skills, infrastructure, financing, cybersecurity and continuity (S4II pp. 51-73).

## 3.3 All-stakeholder findings

The all-stakeholder assessment confirms substantial availability and readiness but lower governance maturity, continued request-based exchange, uneven public access and variable institutional capacity (S4III pp. 5-13).

## 3.4 Priority challenges

Table 4. Priority diagnostic challenge themes

| Theme | Challenge codes | Implementation focus |
| --- | --- | --- |
| Governance and coordination | C01-C03 | Mandate, governance bodies, focal points, owner and steward assignment |
| Quality, metadata and provenance | C04-C06 | Registry, metadata, QA/QC, versioning, traceability and gap closure |
| Interoperability, security and continuity | C07-C09 | Architecture, standards, governed exchange, cyber controls and recovery |
| Access, reporting and public value | C10-C12 | Classification, access workflow, publication, reporting and user feedback |
| Capacity, finance and sustainability | C13-C15 | Skills, institutional resources, recurrent financing, monitoring and succession |

## 3.5 Root-cause analysis

| Evidence | Root cause | Operational consequence | Required response | Coded action and KPI |
| --- | --- | --- | --- | --- |
| Validated diagnostic finding | Institutional, procedural, technical or resource cause | Effect on quality, access, reporting or sustainability | Governance-first intervention | Assigned action, task, target and verification |

Figure 5. Challenge-to-action response framework

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

## 3.6 Challenge-to-objective mapping

Challenges are mapped to the objective and pillar that holds primary accountability. Cross-pillar dependencies prevent technology and publication actions from bypassing governance, quality, classification, security and capacity prerequisites.

## 3.7 Challenge-to-action mapping

Table 5. Challenge-to-action summary

| Challenge group | Primary action range | Expected result |
| --- | --- | --- |
| C01-C03 | SO1-P1-PR1-A01 to SO1-P1-PR6-A06 | Approved authority, coordination, roles and governance instruments |
| C04-C06 | SO2-P2-PR1-A01 to SO2-P2-PR6-A06 | Trusted, documented and quality-controlled priority data |
| C07-C09 | SO3-P3-PR1-A01 to SO3-P3-PR6-A06 | Secure, resilient and interoperable national data flows |
| C10-C12 | SO4-P4-PR1-A01 to SO4-P4-PR6-A06 | Governed access, reporting and environmental information services |
| C13-C15 | SO5-P5-PR1-A01 to SO5-P5-PR6-A06 | Sustained capabilities, resources, monitoring and adaptive management |

## 3.8 Implementation readiness

Existing data production, eMISK, institutional systems, reported accessibility policies and prior diagnostic work provide a practical base. Readiness is constrained by incomplete governance, national standards, role assignment and sustained financing.

## 3.9 Priority-setting methodology

Each action is scored on twelve criteria from 1 to 5: legal urgency, strategic importance, challenge severity, dependency value, institutional readiness, technical feasibility, cost and resource demand, environmental-governance benefit, reporting relevance, public value, non-implementation risk and quick-win potential.

| Critical | High priority | Medium priority | Longer-term |
| --- | --- | --- | --- |
| Immediate dependency, legal or high-risk control | High strategic value and early enabling role | Important scale-up or service action | Deferred until prerequisites and resources are available |

Figure 6. Action prioritization matrix

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 4. Action-Planning Framework

The framework defines the codes, categories, responsibility, status, timing, resource and results rules used consistently in the Word report and Excel monitoring workbook.

## 4.1 Results hierarchy

Mandate and vision flow through objectives, pillars, outcomes, programmes, actions, tasks, deliverables, milestones, KPIs, targets and verification.

## 4.2 Action coding

Codes use SOx-Px-PRx-Axx-Txx. KPI, milestone, risk and dependency records inherit the action code so all registers can be joined and audited.

## 4.3 Action categories

Foundational actions establish authority and controls; enabling actions operationalize standards and services; transformational actions scale integrated capabilities; continuous actions sustain performance.

## 4.4 Prioritization criteria

Scores are transparent planning aids. High-cost technology cannot outrank unmet governance, quality, classification, security or institutional dependencies.

## 4.5 Responsibility model

RACI distinguishes Responsible, Accountable, Consulted and Informed roles. Proposed roles require approval and do not create legal mandates.

## 4.6 Status model

Permitted statuses are Not started, Planned, In progress, At risk, Delayed, On hold, Completed and Cancelled or superseded. The initial register recognizes existing and ongoing work where sources provide evidence.

## 4.7 Timeline model

Dates use the proposed 2027-2031 horizon. Annual workplans must confirm dates, procurement and budgets before execution.

## 4.8 Resource model

Each action records human, technical, institutional and financial categories, a cost band and a detailed-costing responsibility. Exact costs remain to be determined.

## 4.9 KPI and target methodology

Every action has a KPI, baseline or baseline-establishment requirement, annual milestone, final target, date, source, verification and reporting frequency.

## 4.10 Reporting and verification approach

Programme managers collect evidence quarterly, validate it against agreed criteria, update risk and dependency records and submit decisions for governance review.

| Pillar 1 | Pillar 2 | Pillar 3 | Pillar 4 | Pillar 5 |
| --- | --- | --- | --- | --- |
| Authority and coordination | Registry, metadata and QA/QC | Standards, integration and resilience | Classification, access and information services | Skills, finance, monitoring and continuity |

Figure 7. Five-pillar action architecture

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

Table 6. Status and traffic-light model

| Status | Traffic light | Definition | Required response |
| --- | --- | --- | --- |
| Not started / Planned | Grey | No implementation evidence or approved start pending | Confirm owner, baseline and start gate |
| In progress | Green | Work is active and within agreed tolerance | Continue and verify milestones |
| At risk | Amber | Minor delay or constraint may affect target | Corrective action and closer monitoring |
| Delayed | Red | Approved milestone or completion date missed | Escalate, replan and record decision |
| On hold | Amber | Paused by decision or unresolved dependency | Resolve gate or approve closure |
| Completed | Blue | Deliverable and verification accepted | Close action and track benefits |

# Chapter 5. Pillar 1 Strategic Actions

This chapter operationalizes Pillar 1, Data Governance and Institutional Management, through six coded actions and their tasks, responsibilities, resources, milestones, KPIs, targets, risks and dependencies.

## 5.1 Pillar objective and expected outcome

A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability.

## 5.2 Challenges addressed

Primary challenge codes: C01, C02, C03, C04. Secondary dependencies are recorded in each action profile and the dependency register.

## 5.3 Programme and action summary

Table 7. Pillar 1 strategic action matrix

| Action ID | Action | Priority | Start | Completion | Status | Final target |
| --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Endorse the NEDMP implementation instruments and governance charter | Critical | 2027-01-01 | 2027-06-30 | Planned | Governance charter endorsed and first decision calendar issued by 2027-06-30 |
| SO1-P1-PR2-A02 | Activate the NEDMP programme management and coordination function | Critical | 2027-01-01 | 2027-06-30 | Planned | Programme coordination function operating with monthly delivery review by 2027-06-30 |
| SO1-P1-PR3-A03 | Establish the institutional environmental data focal-point network | Critical | 2027-03-01 | 2027-09-30 | Planned | All priority participating institutions nominate a focal point by 2027-09-30 |
| SO1-P1-PR4-A04 | Assign data owners, stewards and custodians for priority datasets | Critical | 2027-06-01 | 2028-03-31 | Planned | Owner, steward and custodian assigned for 100 per cent of priority datasets by 2028-03-31 |
| SO1-P1-PR5-A05 | Complete the environmental data legal and policy gap assessment | High priority | 2027-04-01 | 2027-12-31 | Planned | Gap assessment completed and management response approved by 2027-12-31 |
| SO1-P1-PR6-A06 | Approve the core governance policy, SOP and data-sharing instrument package | Critical | 2027-09-01 | 2028-06-30 | Planned | Core instrument package approved and used by all pilot institutions by 2028-06-30 |

## 5.4 Detailed actions

The pillar lead consolidates task evidence quarterly, verifies KPI records, updates risks and dependencies, and submits corrective actions and decisions through the proposed programme management and governance structure.

### SO1-P1-PR1-A01 | Endorse the NEDMP implementation instruments and governance charter

Deliver approved governance charter, endorsement record and decision calendar to address governance readiness is lower than technical readiness. and contribute to a nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability.. Deliverable: Approved governance charter, endorsement record and decision calendar. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA NEDMP coordinating function (proposed); period: 2027-01-01 to 2027-06-30. KPI-SO1-P1-PR1-A01 target: Governance charter endorsed and first decision calendar issued by 2027-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO1-P1-PR2-A02 | Activate the NEDMP programme management and coordination function

Deliver operational programme charter, workplan, issue register and reporting calendar to address institutional coordination and reporting responsibilities are fragmented. and contribute to a nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability.. Deliverable: Operational programme charter, workplan, issue register and reporting calendar. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA NEDMP coordinating function (proposed); period: 2027-01-01 to 2027-06-30. KPI-SO1-P1-PR2-A02 target: Programme coordination function operating with monthly delivery review by 2027-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO1-P1-PR3-A03 | Establish the institutional environmental data focal-point network

Deliver approved focal-point register, role profile and engagement schedule to address institutional coordination and reporting responsibilities are fragmented. and contribute to a nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability.. Deliverable: Approved focal-point register, role profile and engagement schedule. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA NEDMP coordinating function (proposed); period: 2027-03-01 to 2027-09-30. KPI-SO1-P1-PR3-A03 target: All priority participating institutions nominate a focal point by 2027-09-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO1-P1-PR4-A04 | Assign data owners, stewards and custodians for priority datasets

Deliver dataset-level responsibility and decision-rights register to address data ownership, stewardship and custodianship are not consistently assigned. and contribute to a nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability.. Deliverable: Dataset-level responsibility and decision-rights register. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA NEDMP coordinating function (proposed); period: 2027-06-01 to 2028-03-31. KPI-SO1-P1-PR4-A04 target: Owner, steward and custodian assigned for 100 per cent of priority datasets by 2028-03-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO1-P1-PR5-A05 | Complete the environmental data legal and policy gap assessment

Deliver legal-policy gap report and prioritized amendment or guidance register to address legal, policy, data-sharing and sop arrangements are incomplete or uneven. and contribute to a nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability.. Deliverable: Legal-policy gap report and prioritized amendment or guidance register. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA NEDMP coordinating function (proposed); period: 2027-04-01 to 2027-12-31. KPI-SO1-P1-PR5-A05 target: Gap assessment completed and management response approved by 2027-12-31. Key control: Use competent legal authorities and clearly separate legal requirements from proposed administrative measures.

### SO1-P1-PR6-A06 | Approve the core governance policy, SOP and data-sharing instrument package

Deliver governance policy, core sop library, agreement templates and compliance checklist to address legal, policy, data-sharing and sop arrangements are incomplete or uneven. and contribute to a nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability.. Deliverable: Governance policy, core SOP library, agreement templates and compliance checklist. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA NEDMP coordinating function (proposed); period: 2027-09-01 to 2028-06-30. KPI-SO1-P1-PR6-A06 target: Core instrument package approved and used by all pilot institutions by 2028-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

# Chapter 6. Pillar 2 Strategic Actions

This chapter operationalizes Pillar 2, Data Quality, through six coded actions and their tasks, responsibilities, resources, milestones, KPIs, targets, risks and dependencies.

## 6.1 Pillar objective and expected outcome

Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse.

## 6.2 Challenges addressed

Primary challenge codes: C05, C06. Secondary dependencies are recorded in each action profile and the dependency register.

## 6.3 Programme and action summary

Table 8. Pillar 2 strategic action matrix

| Action ID | Action | Priority | Start | Completion | Status | Final target |
| --- | --- | --- | --- | --- | --- | --- |
| SO2-P2-PR1-A01 | Complete the national environmental dataset inventory and registry | Critical | 2027-03-01 | 2028-06-30 | In progress | 100 per cent of priority datasets registered by 2028-06-30 |
| SO2-P2-PR2-A02 | Approve the priority and authoritative dataset list and indicator catalogue | Critical | 2027-09-01 | 2028-09-30 | Planned | Priority list and catalogue approved, with annual review, by 2028-09-30 |
| SO2-P2-PR3-A03 | Issue the national environmental metadata profile, dictionaries and vocabularies | Critical | 2027-09-01 | 2028-09-30 | Planned | Mandatory metadata complete for at least 90 per cent of priority datasets by 2029-12-31 |
| SO2-P2-PR4-A04 | Implement minimum QA/QC, validation and reliability grading | Critical | 2028-01-01 | 2029-12-31 | Planned | At least 85 per cent of priority datasets pass minimum QA/QC by 2029-12-31 |
| SO2-P2-PR5-A05 | Establish version control, provenance, traceability and methodology records | High priority | 2028-04-01 | 2030-06-30 | Planned | Traceability record complete for 100 per cent of priority datasets by 2030-06-30 |
| SO2-P2-PR6-A06 | Implement data-quality improvement and priority gap-closure plans | High priority | 2028-07-01 | 2031-12-31 | Planned | All critical dataset gaps have an approved treatment and annual status report by 2031-12-31 |

## 6.4 Detailed actions

The pillar lead consolidates task evidence quarterly, verifies KPI records, updates risks and dependencies, and submits corrective actions and decisions through the proposed programme management and governance structure.

### SO2-P2-PR1-A01 | Complete the national environmental dataset inventory and registry

Deliver national registry of priority datasets, owners, sources, update cycles and gaps to address environmental data gaps, time-series breaks and irregular update cycles remain. and contribute to priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse.. Deliverable: National registry of priority datasets, owners, sources, update cycles and gaps. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA data quality and registry function (proposed); period: 2027-03-01 to 2028-06-30. KPI-SO2-P2-PR1-A01 target: 100 per cent of priority datasets registered by 2028-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO2-P2-PR2-A02 | Approve the priority and authoritative dataset list and indicator catalogue

Deliver approved priority dataset list and environmental indicator catalogue to address environmental data gaps, time-series breaks and irregular update cycles remain. and contribute to priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse.. Deliverable: Approved priority dataset list and environmental indicator catalogue. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA data quality and registry function (proposed); period: 2027-09-01 to 2028-09-30. KPI-SO2-P2-PR2-A02 target: Priority list and catalogue approved, with annual review, by 2028-09-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO2-P2-PR3-A03 | Issue the national environmental metadata profile, dictionaries and vocabularies

Deliver minimum metadata profile, data dictionary template and controlled vocabularies to address metadata, methodological documentation and qa/qc practices are uneven. and contribute to priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse.. Deliverable: Minimum metadata profile, data dictionary template and controlled vocabularies. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA data quality and registry function (proposed); period: 2027-09-01 to 2028-09-30. KPI-SO2-P2-PR3-A03 target: Mandatory metadata complete for at least 90 per cent of priority datasets by 2029-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO2-P2-PR4-A04 | Implement minimum QA/QC, validation and reliability grading

Deliver national quality-control standard, validation checklist and reliability register to address metadata, methodological documentation and qa/qc practices are uneven. and contribute to priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse.. Deliverable: National quality-control standard, validation checklist and reliability register. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA data quality and registry function (proposed); period: 2028-01-01 to 2029-12-31. KPI-SO2-P2-PR4-A04 target: At least 85 per cent of priority datasets pass minimum QA/QC by 2029-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO2-P2-PR5-A05 | Establish version control, provenance, traceability and methodology records

Deliver provenance and methodology record linked to each priority dataset to address metadata, methodological documentation and qa/qc practices are uneven. and contribute to priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse.. Deliverable: Provenance and methodology record linked to each priority dataset. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA data quality and registry function (proposed); period: 2028-04-01 to 2030-06-30. KPI-SO2-P2-PR5-A05 target: Traceability record complete for 100 per cent of priority datasets by 2030-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO2-P2-PR6-A06 | Implement data-quality improvement and priority gap-closure plans

Deliver annual thematic quality and gap-closure plans with tracked corrective actions to address environmental data gaps, time-series breaks and irregular update cycles remain. and contribute to priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse.. Deliverable: Annual thematic quality and gap-closure plans with tracked corrective actions. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA data quality and registry function (proposed); period: 2028-07-01 to 2031-12-31. KPI-SO2-P2-PR6-A06 target: All critical dataset gaps have an approved treatment and annual status report by 2031-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

# Chapter 7. Pillar 3 Strategic Actions

This chapter operationalizes Pillar 3, Data Interoperability and System Integration, through six coded actions and their tasks, responsibilities, resources, milestones, KPIs, targets, risks and dependencies.

## 7.1 Pillar objective and expected outcome

Priority environmental data flows move securely between systems through agreed standards and governed integration services.

## 7.2 Challenges addressed

Primary challenge codes: C07, C08, C14. Secondary dependencies are recorded in each action profile and the dependency register.

## 7.3 Programme and action summary

Table 9. Pillar 3 strategic action matrix

| Action ID | Action | Priority | Start | Completion | Status | Final target |
| --- | --- | --- | --- | --- | --- | --- |
| SO3-P3-PR1-A01 | Complete the systems inventory, digital-readiness assessment and target architecture | Critical | 2027-04-01 | 2028-03-31 | In progress | All priority systems assessed and architecture principles approved by 2028-03-31 |
| SO3-P3-PR2-A02 | Approve the national environmental data interoperability framework | Critical | 2027-10-01 | 2028-12-31 | Planned | Framework approved and applied to all new integration projects by 2028-12-31 |
| SO3-P3-PR3-A03 | Establish identity, cybersecurity, backup and business-continuity controls | Critical | 2027-10-01 | 2030-06-30 | Planned | All priority repositories document controls and complete recovery testing by 2030-06-30 |
| SO3-P3-PR4-A04 | Pilot governed recurrent data flows linked to eMISK | High priority | 2028-07-01 | 2029-12-31 | Planned | At least 10 recurrent priority data flows pass acceptance testing by 2029-12-31 |
| SO3-P3-PR5-A05 | Approve and implement the National Environmental Data Portal operating model | High priority | 2028-01-01 | 2030-06-30 | Planned | Operating model approved by 2028-12-31 and minimum services operational by 2030-06-30 |
| SO3-P3-PR6-A06 | Scale integration, migration, service management and technology renewal | Medium priority | 2030-01-01 | 2031-12-31 | Planned | All approved priority flows operate under service levels and renewal plans by 2031-12-31 |

## 7.4 Detailed actions

The pillar lead consolidates task evidence quarterly, verifies KPI records, updates risks and dependencies, and submits corrective actions and decisions through the proposed programme management and governance structure.

### SO3-P3-PR1-A01 | Complete the systems inventory, digital-readiness assessment and target architecture

Deliver systems inventory, readiness scorecard and approved target architecture principles to address existing systems and portal options require an agreed national operating model. and contribute to priority environmental data flows move securely between systems through agreed standards and governed integration services.. Deliverable: Systems inventory, readiness scorecard and approved target architecture principles. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA technical implementation unit and system owners (proposed); period: 2027-04-01 to 2028-03-31. KPI-SO3-P3-PR1-A01 target: All priority systems assessed and architecture principles approved by 2028-03-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO3-P3-PR2-A02 | Approve the national environmental data interoperability framework

Deliver interoperability framework covering formats, apis, identifiers, spatial and statistical exchange to address data exchange remains partly request-based and insufficiently machine-readable. and contribute to priority environmental data flows move securely between systems through agreed standards and governed integration services.. Deliverable: Interoperability framework covering formats, APIs, identifiers, spatial and statistical exchange. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA technical implementation unit and system owners (proposed); period: 2027-10-01 to 2028-12-31. KPI-SO3-P3-PR2-A02 target: Framework approved and applied to all new integration projects by 2028-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO3-P3-PR3-A03 | Establish identity, cybersecurity, backup and business-continuity controls

Deliver minimum security and continuity control baseline with tested recovery plans to address cybersecurity, backup, disaster-recovery and continuity readiness are uneven. and contribute to priority environmental data flows move securely between systems through agreed standards and governed integration services.. Deliverable: Minimum security and continuity control baseline with tested recovery plans. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA technical implementation unit and system owners (proposed); period: 2027-10-01 to 2030-06-30. KPI-SO3-P3-PR3-A03 target: All priority repositories document controls and complete recovery testing by 2030-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO3-P3-PR4-A04 | Pilot governed recurrent data flows linked to eMISK

Deliver validated integration pilots with metadata, qa/qc, classification and audit controls to address data exchange remains partly request-based and insufficiently machine-readable. and contribute to priority environmental data flows move securely between systems through agreed standards and governed integration services.. Deliverable: Validated integration pilots with metadata, QA/QC, classification and audit controls. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA technical implementation unit and system owners (proposed); period: 2028-07-01 to 2029-12-31. KPI-SO3-P3-PR4-A04 target: At least 10 recurrent priority data flows pass acceptance testing by 2029-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO3-P3-PR5-A05 | Approve and implement the National Environmental Data Portal operating model

Deliver approved federated or hybrid operating model and operational minimum viable portal services to address existing systems and portal options require an agreed national operating model. and contribute to priority environmental data flows move securely between systems through agreed standards and governed integration services.. Deliverable: Approved federated or hybrid operating model and operational minimum viable portal services. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA technical implementation unit and system owners (proposed); period: 2028-01-01 to 2030-06-30. KPI-SO3-P3-PR5-A05 target: Operating model approved by 2028-12-31 and minimum services operational by 2030-06-30. Key control: Use architecture and governance decision gates before procurement and release funding by stage.

### SO3-P3-PR6-A06 | Scale integration, migration, service management and technology renewal

Deliver scaled integration portfolio, migration records, service levels and renewal plan to address data exchange remains partly request-based and insufficiently machine-readable. and contribute to priority environmental data flows move securely between systems through agreed standards and governed integration services.. Deliverable: Scaled integration portfolio, migration records, service levels and renewal plan. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA technical implementation unit and system owners (proposed); period: 2030-01-01 to 2031-12-31. KPI-SO3-P3-PR6-A06 target: All approved priority flows operate under service levels and renewal plans by 2031-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

# Chapter 8. Pillar 4 Strategic Actions

This chapter operationalizes Pillar 4, Data Sharing, Accessibility and Transparency, through six coded actions and their tasks, responsibilities, resources, milestones, KPIs, targets, risks and dependencies.

## 8.1 Pillar objective and expected outcome

Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways.

## 8.2 Challenges addressed

Primary challenge codes: C09, C10, C13. Secondary dependencies are recorded in each action profile and the dependency register.

## 8.3 Programme and action summary

Table 10. Pillar 4 strategic action matrix

| Action ID | Action | Priority | Start | Completion | Status | Final target |
| --- | --- | --- | --- | --- | --- | --- |
| SO4-P4-PR1-A01 | Operationalize the five-level environmental data classification model | Critical | 2027-04-01 | 2028-12-31 | Planned | 100 per cent of priority datasets classified by 2028-12-31 |
| SO4-P4-PR2-A02 | Implement access request, approval, release, licensing and appeal workflows | Critical | 2027-10-01 | 2029-06-30 | Planned | 100 per cent of formal access decisions logged through the workflow by 2029-06-30 |
| SO4-P4-PR3-A03 | Operate a publication-readiness and open environmental data calendar | High priority | 2028-01-01 | 2030-12-31 | In progress | All datasets classified as public have an approved publication decision and schedule by 2030-12-31 |
| SO4-P4-PR4-A04 | Develop national environmental dashboards, maps and information services | Medium priority | 2029-01-01 | 2031-06-30 | Planned | At least five priority thematic services operational and accessibility-tested by 2031-06-30 |
| SO4-P4-PR5-A05 | Standardize national, SDG, MEA and State of the Environment reporting workflows | High priority | 2028-07-01 | 2030-12-31 | Planned | 100 per cent of priority recurring reports have documented data flows and responsible providers by 2030-12-31 |
| SO4-P4-PR6-A06 | Operate user feedback, data correction, researcher access and data-use monitoring | Medium priority | 2029-01-01 | 2031-12-31 | Planned | All public services provide tracked feedback and annual use reporting by 2031-12-31 |

## 8.4 Detailed actions

The pillar lead consolidates task evidence quarterly, verifies KPI records, updates risks and dependencies, and submits corrective actions and decisions through the proposed programme management and governance structure.

### SO4-P4-PR1-A01 | Operationalize the five-level environmental data classification model

Deliver approved classification policy, assessment tool and classification register to address sensitivity and legal restrictions constrain access and sharing. and contribute to environmental data are shared and published through proportionate, transparent and legally reviewed access pathways.. Deliverable: Approved classification policy, assessment tool and classification register. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA portal, access and publication function (proposed); period: 2027-04-01 to 2028-12-31. KPI-SO4-P4-PR1-A01 target: 100 per cent of priority datasets classified by 2028-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO4-P4-PR2-A02 | Implement access request, approval, release, licensing and appeal workflows

Deliver controlled access workflow with decision log, conditions, licensing and appeal route to address sensitivity and legal restrictions constrain access and sharing. and contribute to environmental data are shared and published through proportionate, transparent and legally reviewed access pathways.. Deliverable: Controlled access workflow with decision log, conditions, licensing and appeal route. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA portal, access and publication function (proposed); period: 2027-10-01 to 2029-06-30. KPI-SO4-P4-PR2-A02 target: 100 per cent of formal access decisions logged through the workflow by 2029-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO4-P4-PR3-A03 | Operate a publication-readiness and open environmental data calendar

Deliver approved publication checklist, annual calendar and release catalogue to address public availability and open-data practice are limited and inconsistent. and contribute to environmental data are shared and published through proportionate, transparent and legally reviewed access pathways.. Deliverable: Approved publication checklist, annual calendar and release catalogue. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA portal, access and publication function (proposed); period: 2028-01-01 to 2030-12-31. KPI-SO4-P4-PR3-A03 target: All datasets classified as public have an approved publication decision and schedule by 2030-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO4-P4-PR4-A04 | Develop national environmental dashboards, maps and information services

Deliver prioritized dashboards, map services and environmental information products to address public availability and open-data practice are limited and inconsistent. and contribute to environmental data are shared and published through proportionate, transparent and legally reviewed access pathways.. Deliverable: Prioritized dashboards, map services and environmental information products. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA portal, access and publication function (proposed); period: 2029-01-01 to 2031-06-30. KPI-SO4-P4-PR4-A04 target: At least five priority thematic services operational and accessibility-tested by 2031-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO4-P4-PR5-A05 | Standardize national, SDG, MEA and State of the Environment reporting workflows

Deliver reporting workflow register linking indicators, providers, calendars and verification to address environmental data use across the policy and reporting cycle is inconsistent. and contribute to environmental data are shared and published through proportionate, transparent and legally reviewed access pathways.. Deliverable: Reporting workflow register linking indicators, providers, calendars and verification. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA portal, access and publication function (proposed); period: 2028-07-01 to 2030-12-31. KPI-SO4-P4-PR5-A05 target: 100 per cent of priority recurring reports have documented data flows and responsible providers by 2030-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO4-P4-PR6-A06 | Operate user feedback, data correction, researcher access and data-use monitoring

Deliver feedback and correction service, researcher-access protocol and data-use report to address environmental data use across the policy and reporting cycle is inconsistent. and contribute to environmental data are shared and published through proportionate, transparent and legally reviewed access pathways.. Deliverable: Feedback and correction service, researcher-access protocol and data-use report. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA portal, access and publication function (proposed); period: 2029-01-01 to 2031-12-31. KPI-SO4-P4-PR6-A06 target: All public services provide tracked feedback and annual use reporting by 2031-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

# Chapter 9. Pillar 5 Strategic Actions

This chapter operationalizes Pillar 5, Capacity Development and Sustainability, through six coded actions and their tasks, responsibilities, resources, milestones, KPIs, targets, risks and dependencies.

## 9.1 Pillar objective and expected outcome

Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP.

## 9.2 Challenges addressed

Primary challenge codes: C11, C12, C15. Secondary dependencies are recorded in each action profile and the dependency register.

## 9.3 Programme and action summary

Table 11. Pillar 5 strategic action matrix

| Action ID | Action | Priority | Start | Completion | Status | Final target |
| --- | --- | --- | --- | --- | --- | --- |
| SO5-P5-PR1-A01 | Complete institutional capacity, staffing and training-needs assessments | Critical | 2027-03-01 | 2027-12-31 | In progress | All priority institutions complete the capacity baseline by 2027-12-31 |
| SO5-P5-PR2-A02 | Approve the NEDMP competency framework and role-based learning pathways | Critical | 2027-09-01 | 2028-06-30 | Planned | Competency framework approved and annual learning plan funded by 2028-06-30 |
| SO5-P5-PR3-A03 | Deliver and certify role-based NEDMP training | High priority | 2028-04-01 | 2030-12-31 | Planned | At least 80 per cent of designated focal points, stewards and technical staff complete required modules by 2030-12-31 |
| SO5-P5-PR4-A04 | Establish train-the-trainer, communities of practice and knowledge management | High priority | 2028-07-01 | 2031-12-31 | Planned | National trainer pool established and communities meet quarterly from 2029 onward |
| SO5-P5-PR5-A05 | Establish multi-year resource, costing and financing arrangements | Critical | 2027-06-01 | 2031-12-31 | Planned | Annual NEDMP resource plan and recurrent-cost review completed from 2028 onward |
| SO5-P5-PR6-A06 | Institutionalize monitoring, adaptive management, succession and responsible AI readiness | Critical | 2027-01-01 | 2031-12-31 | Planned | Quarterly reviews, annual management responses and final evaluation completed through 2031 |

## 9.4 Detailed actions

The pillar lead consolidates task evidence quarterly, verifies KPI records, updates risks and dependencies, and submits corrective actions and decisions through the proposed programme management and governance structure.

### SO5-P5-PR1-A01 | Complete institutional capacity, staffing and training-needs assessments

Deliver institutional capacity baseline, role profiles and prioritized learning-needs register to address specialist skills, staffing and coordinated training remain insufficient. and contribute to institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the nedmp.. Deliverable: Institutional capacity baseline, role profiles and prioritized learning-needs register. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA capacity, finance and monitoring functions (proposed); period: 2027-03-01 to 2027-12-31. KPI-SO5-P5-PR1-A01 target: All priority institutions complete the capacity baseline by 2027-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO5-P5-PR2-A02 | Approve the NEDMP competency framework and role-based learning pathways

Deliver competency framework, curricula and annual learning plan to address specialist skills, staffing and coordinated training remain insufficient. and contribute to institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the nedmp.. Deliverable: Competency framework, curricula and annual learning plan. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA capacity, finance and monitoring functions (proposed); period: 2027-09-01 to 2028-06-30. KPI-SO5-P5-PR2-A02 target: Competency framework approved and annual learning plan funded by 2028-06-30. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO5-P5-PR3-A03 | Deliver and certify role-based NEDMP training

Deliver completed learning cohorts, competency assessments and certification records to address specialist skills, staffing and coordinated training remain insufficient. and contribute to institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the nedmp.. Deliverable: Completed learning cohorts, competency assessments and certification records. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA capacity, finance and monitoring functions (proposed); period: 2028-04-01 to 2030-12-31. KPI-SO5-P5-PR3-A03 target: At least 80 per cent of designated focal points, stewards and technical staff complete required modules by 2030-12-31. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO5-P5-PR4-A04 | Establish train-the-trainer, communities of practice and knowledge management

Deliver trainer pool, quarterly communities of practice and controlled knowledge repository to address specialist skills, staffing and coordinated training remain insufficient. and contribute to institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the nedmp.. Deliverable: Trainer pool, quarterly communities of practice and controlled knowledge repository. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA capacity, finance and monitoring functions (proposed); period: 2028-07-01 to 2031-12-31. KPI-SO5-P5-PR4-A04 target: National trainer pool established and communities meet quarterly from 2029 onward. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO5-P5-PR5-A05 | Establish multi-year resource, costing and financing arrangements

Deliver costing model, multi-year resource profile, annual budget responsibilities and funding-gap register to address funding and recurrent financing are fragmented or uncertain. and contribute to institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the nedmp.. Deliverable: Costing model, multi-year resource profile, annual budget responsibilities and funding-gap register. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA capacity, finance and monitoring functions (proposed); period: 2027-06-01 to 2031-12-31. KPI-SO5-P5-PR5-A05 target: Annual NEDMP resource plan and recurrent-cost review completed from 2028 onward. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

### SO5-P5-PR6-A06 | Institutionalize monitoring, adaptive management, succession and responsible AI readiness

Deliver operational monitoring dashboard, review cycle, succession controls and ai-readiness gate to address implementation performance, benefits and corrective actions require a common monitoring system. and contribute to institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the nedmp.. Deliverable: Operational monitoring dashboard, review cycle, succession controls and AI-readiness gate. Accountable: Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority; lead: EPA/KEPA capacity, finance and monitoring functions (proposed); period: 2027-01-01 to 2031-12-31. KPI-SO5-P5-PR6-A06 target: Quarterly reviews, annual management responses and final evaluation completed through 2031. Key control: Use a decision gate, named owner, escalation deadline and documented management response.

# Chapter 10. Cross-Cutting Actions

Cross-cutting controls apply across all five pillars and are embedded in the action register rather than managed as disconnected support activities.

Table 12. Cross-cutting action responsibilities

| Cross-cutting area | Primary pillar | Operational mechanism | Primary action IDs |
| --- | --- | --- | --- |
| Programme management | Pillar 1 | Action register, annual planning, issue and document control | SO1-P1-PR2-A02 |
| Legal and policy coordination | Pillar 1 | Legal gap review, governance policy and data-sharing instruments | SO1-P1-PR5-A05; SO1-P1-PR6-A06 |
| Change management | Pillar 5 | Capacity assessment, role pathways, communications and adoption | SO5-P5-PR1-A01; SO5-P5-PR2-A02 |
| Communication and stakeholder engagement | Pillar 4 | Publication guidance, feedback, researcher access and use monitoring | SO4-P4-PR3-A03; SO4-P4-PR6-A06 |
| Cybersecurity and data sovereignty | Pillar 3 | Identity, security, backup, recovery and continuity controls | SO3-P3-PR3-A03 |
| Risk management | Pillar 5 | Action-level risk register, triggers and corrective responses | SO5-P5-PR6-A06 |
| Monitoring, evaluation and learning | Pillar 5 | KPIs, status, quarterly review, annual management response | SO5-P5-PR6-A06 |
| Resource mobilization | Pillar 5 | Costing, multi-year resource profile, budget and funding-gap tracking | SO5-P5-PR5-A05 |
| Sustainability and institutionalization | Pillar 5 | Succession, knowledge, recurrent financing and next-cycle review | SO5-P5-PR4-A04; SO5-P5-PR6-A06 |

| Programme control | Legal and security | Change and engagement | Resources | Monitoring and learning |
| --- | --- | --- | --- | --- |
| Planning, issues, quality and document control | Legal review, classification, cybersecurity and sovereignty | Training, communication, feedback and adoption | Costing, budgets, staffing and partnerships | KPIs, risk, evaluation and adaptive action |

Figure 8. Cross-cutting controls across the five pillars

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 11. Institutional Responsibilities

Responsibilities are proposed for planning purposes and must be confirmed through national approval, legal review and institutional nomination.

## 11.1 Governance and oversight

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

## 11.2 Programme management

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

## 11.3 Institutional focal points

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

## 11.4 Data owners and stewards

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

## 11.5 Technical working groups

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

## 11.6 Participating institutions

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

## 11.7 Decision rights

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

## 11.8 Accountability and escalation

The applicable role, decision authority, evidence requirement and escalation route are recorded in the action register, responsibility matrix and proposed RACI model. Formal authority remains subject to national confirmation.

| National oversight | Steering and governance | EPA/KEPA programme function | Workstream and technical groups | Institutional owners, stewards and focal points |
| --- | --- | --- | --- | --- |
| Endorse and resolve national issues | Approve priorities, standards and decisions | Coordinate delivery, reporting and evidence | Develop and implement technical controls | Own datasets, execute tasks and provide verification |

Figure 9. Institutional responsibility structure

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

## 11.9 RACI matrix

Table 13. Strategic responsibility summary

| Role | RACI function | Primary responsibility |
| --- | --- | --- |
| National oversight / Steering Committee | A | Endorse priorities, resolve escalated issues and approve national decisions |
| EPA/KEPA programme function | R / A as approved | Coordinate implementation, evidence, reporting, risks and corrective action |
| Institutional data owners and stewards | R / A | Authorize, document, quality-control and maintain assigned datasets |
| Legal, cybersecurity and technical groups | C / R | Review compliance, classification, standards, security and architecture |
| Participating institutions and users | R / C / I | Provide data, implement tasks, validate services and receive approved information |

| R - Responsible | A - Accountable | C - Consulted | I - Informed |
| --- | --- | --- | --- |
| Performs the work | Owns the decision and result | Provides required input or review | Receives status and decisions |

Figure 10. RACI responsibility model

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 12. Implementation Schedule

The proposed schedule follows a governance-first critical path and uses a five-year horizon subject to national approval.

## 12.1 Action-plan horizon

Proposed five-year horizon, subject to national approval: 2027-01-01 to 2031-12-31.

## 12.2 Implementation phases

Table 14. Strategic Action Plan implementation phases

| Phase | Indicative period | Primary focus | Decision gate |
| --- | --- | --- | --- |
| Mobilization | 2027 H1 | Endorsement, programme function, focal points and baselines | Authority, roles and workplan approved |
| Foundations | 2027 H2-2028 | Registry, ownership, legal review, classification, metadata, QA/QC and security | Minimum governance and standards package operational |
| Priority implementation | 2028-2029 | Integration pilots, access workflow, training and reporting flows | Pilot acceptance and benefits evidence |
| Scale-up | 2030 | Portal services, recurrent integration, public services and institutional coverage | Service, budget and continuity readiness |
| Institutionalization | 2031 | Sustained operation, evaluation, renewal and next cycle | Final evaluation and next-cycle decision |

## 12.3 Immediate actions

Approve governance, programme management, focal points, baseline instruments, classification and dataset inventory initiation.

## 12.4 Short-term actions

Complete legal review, role assignment, metadata, QA/QC, security and interoperability foundations.

## 12.5 Medium-term actions

Operate pilots, access workflows, reporting flows, capacity programmes and phased portal services.

## 12.6 Long-term actions

Scale approved integration and information services, maintain recurrent funding and prepare the next cycle.

## 12.7 Quick wins

Focal-point nominations, registry template, classification assessment, metadata profile and first low-risk publication decisions can produce visible early value.

## 12.8 Milestones

Every action has a mid-point review milestone and final approval or acceptance milestone.

## 12.9 Dependencies

The dependency register records predecessor actions, decision gates, critical-path status and management responses.

## 12.10 Critical path

Governance and programme activation precede owner assignment; owner assignment and the registry precede classification and standards; quality, security and interoperability controls precede integration and publication scale-up.

## 12.11 Consolidated Gantt chart

The detailed 60-month chart is provided in Annex G and in the live Excel workbook.

| 2027 Mobilize | 2028 Foundations | 2029 Priority implementation | 2030 Scale | 2031 Institutionalize |
| --- | --- | --- | --- | --- |
| Authority and baselines | Rules, registry and standards | Pilots, access and capacity | Services and institutional coverage | Evaluation, renewal and next cycle |

Figure 11. Implementation phases

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

| Gate 1 | Gate 2 | Gate 3 | Gate 4 | Gate 5 |
| --- | --- | --- | --- | --- |
| Governance endorsed | Priority datasets governed | Standards and controls operational | Pilots accepted and services scaled | Benefits sustained and next cycle approved |

Figure 12. Milestone roadmap

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

| Governance | Owners and registry | Metadata, QA/QC and classification | Security and interoperability | Integration and publication | Scale and institutionalization |
| --- | --- | --- | --- | --- | --- |
| Approve authority and programme control | Assign roles and establish inventory | Apply minimum national controls | Approve technical and resilience gates | Pilot and accept services | Expand only with resources and review evidence |

Figure 13. Critical-path diagram

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 13. Resources and Financing

Resource planning distinguishes human, institutional, technical, capital and recurrent needs and avoids unsupported exact budgets.

## 13.1 Human resources

Programme management, governance, stewardship, metadata, QA/QC, GIS, database, API, security, legal, monitoring and training capabilities are assigned by action.

## 13.2 Institutional resources

Governance bodies, working groups, focal points, legal instruments, SOPs, agreements, procurement and partnerships are recorded as enabling resources.

## 13.3 Technical resources

Existing systems, eMISK, registry, metadata catalogue, APIs, GIS, portal, hosting, cybersecurity, backup and analytical tools are reused and expanded according to approved architecture.

## 13.4 Capital requirements

High-cost integration, portal, hosting, cybersecurity and continuity investments require stage-gated capital approval.

## 13.5 Recurrent requirements

Coordination, stewardship, quality control, hosting, maintenance, training, monitoring and renewal require visible recurrent allocations.

## 13.6 Indicative costing method

Actions use low, medium and high bands. Detailed costing must define quantities, unit costs, assumptions, procurement route, inflation, contingency, capital and recurrent ownership.

## 13.7 Multi-year resource profile

The workbook provides editable Year 1-Year 5 budget fields and distinguishes detailed costing from approved budget.

## 13.8 Potential funding sources

Government budgets remain the core source; approved technical assistance, training allocations and partner support may supplement national resources.

## 13.9 Funding gaps

Unfunded requirements are logged with consequence, decision date and response rather than treated as approved resources.

## 13.10 Budget preparation responsibilities

The proposed programme and finance functions coordinate costing; competent authorities approve allocations.

## 13.11 Financial sustainability

No service moves to scale without confirmed recurrent ownership, maintenance, staffing, security and renewal resources.

Table 15. Resource requirements by category

| Resource category | Illustrative requirements | Approval and sustainability control |
| --- | --- | --- |
| Human | Programme, governance, stewardship, metadata, QA/QC, GIS, database, security, legal, monitoring and training expertise | Approved role assignments, workload and succession arrangements |
| Institutional | Governance bodies, focal points, SOPs, agreements, procurement and partnerships | Mandate validation and annual workplan integration |
| Technical | eMISK, registry, catalogue, APIs, GIS, portal, hosting, backup and analytical tools | Architecture, security, acceptance and lifecycle gates |
| Capital | Integration, portal, hosting, cyber and continuity investments | Detailed costing, procurement and stage-gated approval |
| Recurrent | Coordination, quality control, hosting, maintenance, training, monitoring and renewal | Named budget owner and multi-year financing before scale-up |

| Identify needs | Cost and prioritize | Approve resources | Procure and deploy | Monitor use and benefits | Renew or close |
| --- | --- | --- | --- | --- | --- |
| Human, technical, institutional and financial | Cost bands and detailed assumptions | National budget and approved support | Stage-gated delivery | Expenditure, outputs and outcomes | Recurrent ownership and lifecycle decision |

Figure 14. Resource mobilization framework

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 14. KPI and Target Framework

The KPI register connects action delivery to verified outputs and outcomes and treats missing baselines as explicit Year 1 tasks.

## 14.1 Results-measurement approach

Indicators are coded to actions and include definition, purpose, method, baseline, target, source, frequency, provider, reporting role, disaggregation, limitations and assumptions.

## 14.2 Impact indicators

Long-term indicators assess policy use, environmental governance, transparency and resilience.

## 14.3 Outcome indicators

Outcome indicators assess operational governance, trusted data, recurrent exchange, access and sustainable capabilities.

## 14.4 Output indicators

Output indicators confirm approved instruments, registries, standards, services, training and reports.

## 14.5 Process indicators

Process indicators monitor decisions, timeliness, compliance, issue resolution and reporting.

## 14.6 Baselines

Unsupported values are not invented. Registers and readiness assessments establish denominators in Year 1.

## 14.7 Annual targets

Annual milestones show the path from baseline and approval to operational use, scale and institutionalization.

## 14.8 Final targets

Each target is time-bound and linked to a final action date.

## 14.9 Data collection

Lead entities collect evidence; programme management validates completeness and consistency.

## 14.10 Means of verification

Decision records, registries, audit logs, acceptance reports, training records, service analytics and evaluation reports provide verification.

## 14.11 Reporting responsibilities

Data providers submit KPI evidence; the proposed EPA/KEPA programme function consolidates reporting; governance bodies review performance.

## 14.12 KPI register

The complete KPI register and metadata sheets are provided in Annexes L-M and the Excel workbook.

| Level | Management question | Typical evidence |
| --- | --- | --- |
| Impact | Is the plan improving policy use, environmental governance, transparency and resilience? | Evaluation, policy-use evidence and national reporting |
| Outcome | Are governance, trusted data, exchange, access and institutional capabilities operational? | Operational records, service analytics and institutional verification |
| Output | Were approved instruments, registries, standards, services, training and reports delivered? | Decision records, accepted deliverables and audit trails |
| Process | Are actions timely, compliant and effectively managed? | Task, milestone, issue, risk and corrective-action records |

Table 16. KPI framework summary

# Chapter 15. Status Monitoring and Reporting

Status reporting converts action evidence into management decisions, corrective action and transparent performance reporting.

## 15.1 Status definitions

Only the eight approved status categories may be used, with documented status date and evidence.

## 15.2 Percentage-completion method

Completion is based on weighted verified tasks and accepted deliverables, not elapsed time or subjective estimates.

## 15.3 Traffic-light reporting

Grey indicates not started or no information; green on track; amber at risk or on hold; red significantly delayed; blue completed.

## 15.4 Monthly or quarterly implementation reporting

Critical actions are reviewed monthly by programme management and all actions are reported quarterly.

## 15.5 Annual progress report

The annual report consolidates results, targets, budget, risks, benefits, lessons and management responses.

## 15.6 Management dashboard

The workbook dashboard summarizes actions by pillar, objective, status and priority, completion, risk, overdue actions, milestones and KPI performance.

## 15.7 Issue escalation

Issues are escalated by threshold, owner and deadline through the proposed programme, technical, governance and steering levels.

## 15.8 Corrective-action tracking

Each delayed or at-risk action records cause, corrective action, owner, due date and closure evidence.

## 15.9 Change-control process

Changes to scope, target, date, owner or budget require an impact assessment, decision record and version update.

| Grey | Green | Amber | Red | Blue |
| --- | --- | --- | --- | --- |
| Not started / no information | On track | At risk / on hold | Delayed / blocked | Completed and verified |

Figure 16. Status and traffic-light dashboard

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

| Collect | Validate | Update | Review | Decide | Correct | Report |
| --- | --- | --- | --- | --- | --- | --- |
| Task and KPI evidence | Completeness and quality | Status, risk and dependencies | Programme and governance review | Approve response or change | Track corrective action | Quarterly and annual results |

Figure 17. Monitoring and reporting cycle

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 16. Risks, Dependencies and Assumptions

Risk management follows ISO 31000 principles and integrates security, continuity, legal, institutional, financial and capacity risks into action delivery.

## 16.1 Risk-management approach

Risks record cause, consequence, likelihood, impact, inherent rating, mitigation, owner, residual rating, trigger and review frequency.

## 16.2 Strategic risks

Strategic risks include weak endorsement, misaligned priorities and insufficient national ownership.

## 16.3 Institutional risks

Institutional risks include participation gaps, role ambiguity, staff turnover and delayed decisions.

## 16.4 Technical risks

Technical risks include incompatible systems, poor data quality, migration failure, vendor lock-in and obsolescence.

## 16.5 Financial risks

Financial risks include incomplete costing, delayed procurement and lack of recurrent ownership.

## 16.6 Capacity risks

Capacity risks include specialist shortages, limited training uptake and weak succession.

## 16.7 Cybersecurity risks

Cybersecurity and sovereignty risks include unauthorized access, data loss, service disruption and inappropriate release.

## 16.8 Dependencies

Dependencies are coded and linked to predecessor actions and decision gates.

## 16.9 Assumptions

Core assumptions concern national validation, institutional participation, budget availability, competent legal review and timely evidence.

## 16.10 Risk register

The complete action-level register is in Annex R and the Excel workbook.

## 16.11 Risk heatmap

High-likelihood and high-impact risks require immediate treatment and governance attention; residual risk is reviewed after controls are evidenced.

Table 17. Strategic risk-category summary

| Category | Principal exposure | Primary control |
| --- | --- | --- |
| Strategic | Weak endorsement or misaligned priorities | Governance charter, decision gates and annual reprioritization |
| Institutional | Participation gaps, role ambiguity, staff turnover or delayed decisions | Confirmed RACI, focal points, escalation and succession |
| Technical | Incompatibility, poor quality, migration failure, lock-in or obsolescence | Standards, pilots, acceptance testing and lifecycle review |
| Financial | Incomplete costing, delayed procurement or absent recurrent ownership | Costing deadlines, stage gates and multi-year budget tracking |
| Capacity | Specialist shortages or limited training uptake | Competency pathways, certification, train-the-trainer and communities of practice |
| Cybersecurity and sovereignty | Unauthorized access, data loss, disruption or inappropriate release | Classification, identity controls, security review, backup and continuity |

| Lower impact | Medium impact | High impact |
| --- | --- | --- |
| Monitor and accept within tolerance | Treat through action management | Escalate and apply immediate controls |
| Routine review | Corrective action and owner | Decision gate, contingency and governance review |

Figure 18. Risk heatmap

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Chapter 17. Review and Adaptive Management

The action plan is a controlled living instrument. Review changes priorities and delivery methods while preserving source traceability and approved strategic architecture.

## 17.1 Quarterly review

Validate evidence, targets, risks, dependencies, issues and corrective actions.

## 17.2 Annual review

Assess results, benefits, budget, institutional participation, data gaps and standards implementation.

## 17.3 Mid-term review

At the end of 2029, test sequencing, targets, governance, resource adequacy and service benefits.

## 17.4 Final evaluation

Before the end of 2031, independently assess relevance, effectiveness, efficiency, sustainability and impact contribution.

## 17.5 Target revision

Revise a target only after documented baseline evidence, rationale, impact assessment and approval.

## 17.6 Action reprioritization

Use the same transparent scoring criteria and preserve the decision history.

## 17.7 Lessons learned

Record lessons with the affected action, consequence, recommendation, owner and adoption decision.

## 17.8 Preparation of annual workplans

Translate approved tasks into named institutional units, budgets, procurement and quarterly deliverables.

## 17.9 Preparation of the next action-plan cycle

Use final evaluation, updated diagnostics, benefits evidence and new legal or reporting requirements to prepare the next cycle.

| Plan | Implement | Monitor | Review | Decide | Adapt | Institutionalize |
| --- | --- | --- | --- | --- | --- | --- |
| Approve actions and resources | Execute coded tasks | Collect evidence and status | Assess results, risk and benefits | Approve correction or change | Update workplan, target or control | Embed successful practice and next cycle |

Figure 19. Adaptive-management feedback loop

Source: Developed for the Kuwait NEDMP Strategic Action Plan from the cited NEDMP evidence base.

# Annexes

The annexes provide editable operational registers and templates. The Excel workbook is the authoritative live register for filtering, formulas, status updates and dashboard reporting.

## Annex A. Consolidated Strategic Action Matrix - identity and results

Table 18. Consolidated Strategic Action Matrix, block 1

| Action ID | Objective | Pillar | Secondary | Challenge | Programme | Action | Deliverable | Outcome | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | SO1. Institutionalize Environmental Data Governance | Pillar 1. Data Governance and Institutional Management | Cross-pillar dependency | C01: Governance readiness is lower than technical readiness. | PR1. Endorse the NEDMP implementation instruments and governance charter | Endorse the NEDMP implementation instruments and governance charter | Approved governance charter, endorsement record and decision calendar | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Critical |
| SO1-P1-PR2-A02 | SO1. Institutionalize Environmental Data Governance | Pillar 1. Data Governance and Institutional Management | Cross-pillar dependency | C02: Institutional coordination and reporting responsibilities are fragmented. | PR2. Activate the NEDMP programme management and coordination function | Activate the NEDMP programme management and coordination function | Operational programme charter, workplan, issue register and reporting calendar | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Critical |
| SO1-P1-PR3-A03 | SO1. Institutionalize Environmental Data Governance | Pillar 1. Data Governance and Institutional Management | Cross-pillar dependency | C02: Institutional coordination and reporting responsibilities are fragmented. | PR3. Establish the institutional environmental data focal-point network | Establish the institutional environmental data focal-point network | Approved focal-point register, role profile and engagement schedule | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Critical |
| SO1-P1-PR4-A04 | SO1. Institutionalize Environmental Data Governance | Pillar 1. Data Governance and Institutional Management | Cross-pillar dependency | C03: Data ownership, stewardship and custodianship are not consistently assigned. | PR4. Assign data owners, stewards and custodians for priority datasets | Assign data owners, stewards and custodians for priority datasets | Dataset-level responsibility and decision-rights register | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Critical |
| SO1-P1-PR5-A05 | SO1. Institutionalize Environmental Data Governance | Pillar 1. Data Governance and Institutional Management | Cross-pillar dependency | C04: Legal, policy, data-sharing and SOP arrangements are incomplete or uneven. | PR5. Complete the environmental data legal and policy gap assessment | Complete the environmental data legal and policy gap assessment | Legal-policy gap report and prioritized amendment or guidance register | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | High priority |
| SO1-P1-PR6-A06 | SO1. Institutionalize Environmental Data Governance | Pillar 1. Data Governance and Institutional Management | Cross-pillar dependency | C04: Legal, policy, data-sharing and SOP arrangements are incomplete or uneven. | PR6. Approve the core governance policy, SOP and data-sharing instrument package | Approve the core governance policy, SOP and data-sharing instrument package | Governance policy, core SOP library, agreement templates and compliance checklist | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Critical |
| SO2-P2-PR1-A01 | SO2. Ensure High-Quality and Standardized Environmental Data | Pillar 2. Data Quality | Cross-pillar dependency | C06: Environmental data gaps, time-series breaks and irregular update cycles remain. | PR1. Complete the national environmental dataset inventory and registry | Complete the national environmental dataset inventory and registry | National registry of priority datasets, owners, sources, update cycles and gaps | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Critical |
| SO2-P2-PR2-A02 | SO2. Ensure High-Quality and Standardized Environmental Data | Pillar 2. Data Quality | Cross-pillar dependency | C06: Environmental data gaps, time-series breaks and irregular update cycles remain. | PR2. Approve the priority and authoritative dataset list and indicator catalogue | Approve the priority and authoritative dataset list and indicator catalogue | Approved priority dataset list and environmental indicator catalogue | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Critical |
| SO2-P2-PR3-A03 | SO2. Ensure High-Quality and Standardized Environmental Data | Pillar 2. Data Quality | Cross-pillar dependency | C05: Metadata, methodological documentation and QA/QC practices are uneven. | PR3. Issue the national environmental metadata profile, dictionaries and vocabularies | Issue the national environmental metadata profile, dictionaries and vocabularies | Minimum metadata profile, data dictionary template and controlled vocabularies | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Critical |
| SO2-P2-PR4-A04 | SO2. Ensure High-Quality and Standardized Environmental Data | Pillar 2. Data Quality | Cross-pillar dependency | C05: Metadata, methodological documentation and QA/QC practices are uneven. | PR4. Implement minimum QA/QC, validation and reliability grading | Implement minimum QA/QC, validation and reliability grading | National quality-control standard, validation checklist and reliability register | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Critical |
| SO2-P2-PR5-A05 | SO2. Ensure High-Quality and Standardized Environmental Data | Pillar 2. Data Quality | Cross-pillar dependency | C05: Metadata, methodological documentation and QA/QC practices are uneven. | PR5. Establish version control, provenance, traceability and methodology records | Establish version control, provenance, traceability and methodology records | Provenance and methodology record linked to each priority dataset | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | High priority |
| SO2-P2-PR6-A06 | SO2. Ensure High-Quality and Standardized Environmental Data | Pillar 2. Data Quality | Cross-pillar dependency | C06: Environmental data gaps, time-series breaks and irregular update cycles remain. | PR6. Implement data-quality improvement and priority gap-closure plans | Implement data-quality improvement and priority gap-closure plans | Annual thematic quality and gap-closure plans with tracked corrective actions | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | High priority |
| SO3-P3-PR1-A01 | SO3. Enable Interoperability and System Integration | Pillar 3. Data Interoperability and System Integration | Cross-pillar dependency | C14: Existing systems and portal options require an agreed national operating model. | PR1. Complete the systems inventory, digital-readiness assessment and target architecture | Complete the systems inventory, digital-readiness assessment and target architecture | Systems inventory, readiness scorecard and approved target architecture principles | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Critical |
| SO3-P3-PR2-A02 | SO3. Enable Interoperability and System Integration | Pillar 3. Data Interoperability and System Integration | Cross-pillar dependency | C07: Data exchange remains partly request-based and insufficiently machine-readable. | PR2. Approve the national environmental data interoperability framework | Approve the national environmental data interoperability framework | Interoperability framework covering formats, APIs, identifiers, spatial and statistical exchange | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Critical |
| SO3-P3-PR3-A03 | SO3. Enable Interoperability and System Integration | Pillar 3. Data Interoperability and System Integration | Cross-pillar dependency | C08: Cybersecurity, backup, disaster-recovery and continuity readiness are uneven. | PR3. Establish identity, cybersecurity, backup and business-continuity controls | Establish identity, cybersecurity, backup and business-continuity controls | Minimum security and continuity control baseline with tested recovery plans | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Critical |
| SO3-P3-PR4-A04 | SO3. Enable Interoperability and System Integration | Pillar 3. Data Interoperability and System Integration | Cross-pillar dependency | C07: Data exchange remains partly request-based and insufficiently machine-readable. | PR4. Pilot governed recurrent data flows linked to eMISK | Pilot governed recurrent data flows linked to eMISK | Validated integration pilots with metadata, QA/QC, classification and audit controls | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | High priority |
| SO3-P3-PR5-A05 | SO3. Enable Interoperability and System Integration | Pillar 3. Data Interoperability and System Integration | Cross-pillar dependency | C14: Existing systems and portal options require an agreed national operating model. | PR5. Approve and implement the National Environmental Data Portal operating model | Approve and implement the National Environmental Data Portal operating model | Approved federated or hybrid operating model and operational minimum viable portal services | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | High priority |
| SO3-P3-PR6-A06 | SO3. Enable Interoperability and System Integration | Pillar 3. Data Interoperability and System Integration | Cross-pillar dependency | C07: Data exchange remains partly request-based and insufficiently machine-readable. | PR6. Scale integration, migration, service management and technology renewal | Scale integration, migration, service management and technology renewal | Scaled integration portfolio, migration records, service levels and renewal plan | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Medium priority |
| SO4-P4-PR1-A01 | SO4. Strengthen Data Sharing, Accessibility and Transparency | Pillar 4. Data Sharing, Accessibility and Transparency | Cross-pillar dependency | C10: Sensitivity and legal restrictions constrain access and sharing. | PR1. Operationalize the five-level environmental data classification model | Operationalize the five-level environmental data classification model | Approved classification policy, assessment tool and classification register | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Critical |
| SO4-P4-PR2-A02 | SO4. Strengthen Data Sharing, Accessibility and Transparency | Pillar 4. Data Sharing, Accessibility and Transparency | Cross-pillar dependency | C10: Sensitivity and legal restrictions constrain access and sharing. | PR2. Implement access request, approval, release, licensing and appeal workflows | Implement access request, approval, release, licensing and appeal workflows | Controlled access workflow with decision log, conditions, licensing and appeal route | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Critical |
| SO4-P4-PR3-A03 | SO4. Strengthen Data Sharing, Accessibility and Transparency | Pillar 4. Data Sharing, Accessibility and Transparency | Cross-pillar dependency | C09: Public availability and open-data practice are limited and inconsistent. | PR3. Operate a publication-readiness and open environmental data calendar | Operate a publication-readiness and open environmental data calendar | Approved publication checklist, annual calendar and release catalogue | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | High priority |
| SO4-P4-PR4-A04 | SO4. Strengthen Data Sharing, Accessibility and Transparency | Pillar 4. Data Sharing, Accessibility and Transparency | Cross-pillar dependency | C09: Public availability and open-data practice are limited and inconsistent. | PR4. Develop national environmental dashboards, maps and information services | Develop national environmental dashboards, maps and information services | Prioritized dashboards, map services and environmental information products | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Medium priority |
| SO4-P4-PR5-A05 | SO4. Strengthen Data Sharing, Accessibility and Transparency | Pillar 4. Data Sharing, Accessibility and Transparency | Cross-pillar dependency | C13: Environmental data use across the policy and reporting cycle is inconsistent. | PR5. Standardize national, SDG, MEA and State of the Environment reporting workflows | Standardize national, SDG, MEA and State of the Environment reporting workflows | Reporting workflow register linking indicators, providers, calendars and verification | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | High priority |
| SO4-P4-PR6-A06 | SO4. Strengthen Data Sharing, Accessibility and Transparency | Pillar 4. Data Sharing, Accessibility and Transparency | Cross-pillar dependency | C13: Environmental data use across the policy and reporting cycle is inconsistent. | PR6. Operate user feedback, data correction, researcher access and data-use monitoring | Operate user feedback, data correction, researcher access and data-use monitoring | Feedback and correction service, researcher-access protocol and data-use report | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Medium priority |
| SO5-P5-PR1-A01 | SO5. Build Sustainable National Capacities | Pillar 5. Capacity Development and Sustainability | Cross-pillar dependency | C11: Specialist skills, staffing and coordinated training remain insufficient. | PR1. Complete institutional capacity, staffing and training-needs assessments | Complete institutional capacity, staffing and training-needs assessments | Institutional capacity baseline, role profiles and prioritized learning-needs register | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Critical |
| SO5-P5-PR2-A02 | SO5. Build Sustainable National Capacities | Pillar 5. Capacity Development and Sustainability | Cross-pillar dependency | C11: Specialist skills, staffing and coordinated training remain insufficient. | PR2. Approve the NEDMP competency framework and role-based learning pathways | Approve the NEDMP competency framework and role-based learning pathways | Competency framework, curricula and annual learning plan | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Critical |
| SO5-P5-PR3-A03 | SO5. Build Sustainable National Capacities | Pillar 5. Capacity Development and Sustainability | Cross-pillar dependency | C11: Specialist skills, staffing and coordinated training remain insufficient. | PR3. Deliver and certify role-based NEDMP training | Deliver and certify role-based NEDMP training | Completed learning cohorts, competency assessments and certification records | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | High priority |
| SO5-P5-PR4-A04 | SO5. Build Sustainable National Capacities | Pillar 5. Capacity Development and Sustainability | Cross-pillar dependency | C11: Specialist skills, staffing and coordinated training remain insufficient. | PR4. Establish train-the-trainer, communities of practice and knowledge management | Establish train-the-trainer, communities of practice and knowledge management | Trainer pool, quarterly communities of practice and controlled knowledge repository | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | High priority |
| SO5-P5-PR5-A05 | SO5. Build Sustainable National Capacities | Pillar 5. Capacity Development and Sustainability | Cross-pillar dependency | C12: Funding and recurrent financing are fragmented or uncertain. | PR5. Establish multi-year resource, costing and financing arrangements | Establish multi-year resource, costing and financing arrangements | Costing model, multi-year resource profile, annual budget responsibilities and funding-gap register | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Critical |
| SO5-P5-PR6-A06 | SO5. Build Sustainable National Capacities | Pillar 5. Capacity Development and Sustainability | Cross-pillar dependency | C15: Implementation performance, benefits and corrective actions require a common monitoring system. | PR6. Institutionalize monitoring, adaptive management, succession and responsible AI readiness | Institutionalize monitoring, adaptive management, succession and responsible AI readiness | Operational monitoring dashboard, review cycle, succession controls and AI-readiness gate | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Critical |

## Annex A continued. Governance, schedule and status

Table 19. Consolidated Strategic Action Matrix, block 2

| Action ID | Accountable | Lead | Supporting | Consulted | Oversight | Start | Completion | Months | Milestones | Dependencies | Status | % | RAG |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | 2027-01-01 | 2027-06-30 | 6 | M-SO1-P1-PR1-A01-01; M-SO1-P1-PR1-A01-02 | None - initiating action | Planned | 0 | Grey |
| SO1-P1-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | 2027-01-01 | 2027-06-30 | 6 | M-SO1-P1-PR2-A02-01; M-SO1-P1-PR2-A02-02 | SO1-P1-PR1-A01 | Planned | 0 | Grey |
| SO1-P1-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | 2027-03-01 | 2027-09-30 | 7 | M-SO1-P1-PR3-A03-01; M-SO1-P1-PR3-A03-02 | SO1-P1-PR1-A01 | Planned | 0 | Grey |
| SO1-P1-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | 2027-06-01 | 2028-03-31 | 10 | M-SO1-P1-PR4-A04-01; M-SO1-P1-PR4-A04-02 | SO1-P1-PR1-A03; SO2-P2-PR1-A01 | Planned | 0 | Grey |
| SO1-P1-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | 2027-04-01 | 2027-12-31 | 9 | M-SO1-P1-PR5-A05-01; M-SO1-P1-PR5-A05-02 | SO1-P1-PR1-A01 | Planned | 0 | Grey |
| SO1-P1-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | 2027-09-01 | 2028-06-30 | 10 | M-SO1-P1-PR6-A06-01; M-SO1-P1-PR6-A06-02 | SO1-P1-PR1-A05; SO1-P1-PR1-A04 | Planned | 0 | Grey |
| SO2-P2-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | National Environmental Data Governance Committee (proposed) | 2027-03-01 | 2028-06-30 | 16 | M-SO2-P2-PR1-A01-01; M-SO2-P2-PR1-A01-02 | SO1-P1-PR1-A03 | In progress | 25 | Green |
| SO2-P2-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | National Environmental Data Governance Committee (proposed) | 2027-09-01 | 2028-09-30 | 13 | M-SO2-P2-PR2-A02-01; M-SO2-P2-PR2-A02-02 | SO2-P2-PR1-A01 | Planned | 0 | Grey |
| SO2-P2-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | National Environmental Data Governance Committee (proposed) | 2027-09-01 | 2028-09-30 | 13 | M-SO2-P2-PR3-A03-01; M-SO2-P2-PR3-A03-02 | SO2-P2-PR1-A01; SO2-P2-PR1-A02 | Planned | 0 | Grey |
| SO2-P2-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | National Environmental Data Governance Committee (proposed) | 2028-01-01 | 2029-12-31 | 24 | M-SO2-P2-PR4-A04-01; M-SO2-P2-PR4-A04-02 | SO2-P2-PR1-A03; SO1-P1-PR1-A04 | Planned | 0 | Grey |
| SO2-P2-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | National Environmental Data Governance Committee (proposed) | 2028-04-01 | 2030-06-30 | 27 | M-SO2-P2-PR5-A05-01; M-SO2-P2-PR5-A05-02 | SO2-P2-PR1-A03; SO2-P2-PR1-A04 | Planned | 0 | Grey |
| SO2-P2-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | National Environmental Data Governance Committee (proposed) | 2028-07-01 | 2031-12-31 | 42 | M-SO2-P2-PR6-A06-01; M-SO2-P2-PR6-A06-02 | SO2-P2-PR1-A01; SO2-P2-PR1-A04 | Planned | 0 | Grey |
| SO3-P3-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | NEDMP Steering Committee and technical governance bodies (proposed) | 2027-04-01 | 2028-03-31 | 12 | M-SO3-P3-PR1-A01-01; M-SO3-P3-PR1-A01-02 | SO1-P1-PR1-A03 | In progress | 35 | Green |
| SO3-P3-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | NEDMP Steering Committee and technical governance bodies (proposed) | 2027-10-01 | 2028-12-31 | 15 | M-SO3-P3-PR2-A02-01; M-SO3-P3-PR2-A02-02 | SO3-P3-PR1-A01; SO2-P2-PR1-A03 | Planned | 0 | Grey |
| SO3-P3-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | NEDMP Steering Committee and technical governance bodies (proposed) | 2027-10-01 | 2030-06-30 | 33 | M-SO3-P3-PR3-A03-01; M-SO3-P3-PR3-A03-02 | SO3-P3-PR1-A01; SO1-P1-PR1-A05 | Planned | 0 | Grey |
| SO3-P3-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | NEDMP Steering Committee and technical governance bodies (proposed) | 2028-07-01 | 2029-12-31 | 18 | M-SO3-P3-PR4-A04-01; M-SO3-P3-PR4-A04-02 | SO3-P3-PR1-A02; SO3-P3-PR1-A03; SO4-P4-PR1-A01 | Planned | 0 | Grey |
| SO3-P3-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | NEDMP Steering Committee and technical governance bodies (proposed) | 2028-01-01 | 2030-06-30 | 30 | M-SO3-P3-PR5-A05-01; M-SO3-P3-PR5-A05-02 | SO3-P3-PR1-A01; SO1-P1-PR1-A06; SO4-P4-PR1-A01 | Planned | 0 | Grey |
| SO3-P3-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | NEDMP Steering Committee and technical governance bodies (proposed) | 2030-01-01 | 2031-12-31 | 24 | M-SO3-P3-PR6-A06-01; M-SO3-P3-PR6-A06-02 | SO3-P3-PR1-A04; SO3-P3-PR1-A05 | Planned | 0 | Grey |
| SO4-P4-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | National Environmental Data Governance Committee (proposed) | 2027-04-01 | 2028-12-31 | 21 | M-SO4-P4-PR1-A01-01; M-SO4-P4-PR1-A01-02 | SO1-P1-PR1-A05; SO2-P2-PR1-A01 | Planned | 0 | Grey |
| SO4-P4-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | National Environmental Data Governance Committee (proposed) | 2027-10-01 | 2029-06-30 | 21 | M-SO4-P4-PR2-A02-01; M-SO4-P4-PR2-A02-02 | SO4-P4-PR1-A01; SO1-P1-PR1-A06 | Planned | 0 | Grey |
| SO4-P4-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | National Environmental Data Governance Committee (proposed) | 2028-01-01 | 2030-12-31 | 36 | M-SO4-P4-PR3-A03-01; M-SO4-P4-PR3-A03-02 | SO4-P4-PR1-A01; SO2-P2-PR1-A04 | In progress | 20 | Green |
| SO4-P4-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | National Environmental Data Governance Committee (proposed) | 2029-01-01 | 2031-06-30 | 30 | M-SO4-P4-PR4-A04-01; M-SO4-P4-PR4-A04-02 | SO4-P4-PR1-A03; SO3-P3-PR1-A05 | Planned | 0 | Grey |
| SO4-P4-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | National Environmental Data Governance Committee (proposed) | 2028-07-01 | 2030-12-31 | 30 | M-SO4-P4-PR5-A05-01; M-SO4-P4-PR5-A05-02 | SO2-P2-PR1-A02; SO3-P3-PR1-A04 | Planned | 0 | Grey |
| SO4-P4-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | National Environmental Data Governance Committee (proposed) | 2029-01-01 | 2031-12-31 | 36 | M-SO4-P4-PR6-A06-01; M-SO4-P4-PR6-A06-02 | SO4-P4-PR1-A02; SO4-P4-PR1-A03 | Planned | 0 | Grey |
| SO5-P5-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | NEDMP Steering Committee (proposed, subject to approval) | 2027-03-01 | 2027-12-31 | 10 | M-SO5-P5-PR1-A01-01; M-SO5-P5-PR1-A01-02 | SO1-P1-PR1-A03 | In progress | 30 | Green |
| SO5-P5-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | NEDMP Steering Committee (proposed, subject to approval) | 2027-09-01 | 2028-06-30 | 10 | M-SO5-P5-PR2-A02-01; M-SO5-P5-PR2-A02-02 | SO5-P5-PR1-A01 | Planned | 0 | Grey |
| SO5-P5-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | NEDMP Steering Committee (proposed, subject to approval) | 2028-04-01 | 2030-12-31 | 33 | M-SO5-P5-PR3-A03-01; M-SO5-P5-PR3-A03-02 | SO5-P5-PR1-A02 | Planned | 0 | Grey |
| SO5-P5-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | NEDMP Steering Committee (proposed, subject to approval) | 2028-07-01 | 2031-12-31 | 42 | M-SO5-P5-PR4-A04-01; M-SO5-P5-PR4-A04-02 | SO5-P5-PR1-A02; SO5-P5-PR1-A03 | Planned | 0 | Grey |
| SO5-P5-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | NEDMP Steering Committee (proposed, subject to approval) | 2027-06-01 | 2031-12-31 | 55 | M-SO5-P5-PR5-A05-01; M-SO5-P5-PR5-A05-02 | SO1-P1-PR1-A02 | Planned | 0 | Grey |
| SO5-P5-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | NEDMP Steering Committee (proposed, subject to approval) | 2027-01-01 | 2031-12-31 | 60 | M-SO5-P5-PR6-A06-01; M-SO5-P5-PR6-A06-02 | SO1-P1-PR1-A02; SO5-P5-PR1-A05 | Planned | 0 | Grey |

## Annex A continued. Resources, performance and risk

Table 20. Consolidated Strategic Action Matrix, block 3

| Action ID | Human | Technical | Finance | Cost | Funding | KPI | Baseline | Annual target | Final target | Target date | Verification | Risk | Mitigation | Assumptions | Decision note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | Primarily recurrent with defined set-up costs | Low | Core government programme budget; approved technical assistance | KPI-SO1-P1-PR1-A01 | Implementation governance not yet formally approved | Annual milestone to be confirmed in the approved workplan | Governance charter endorsed and first decision calendar issued by 2027-06-30 | 2027-06-30 | Approved record and implementation evidence | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO1-P1-PR2-A02 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | Primarily recurrent with defined set-up costs | Medium | Core government programme budget; approved technical assistance | KPI-SO1-P1-PR2-A02 | Baseline to be established during inception | Annual milestone to be confirmed in the approved workplan | Programme coordination function operating with monthly delivery review by 2027-06-30 | 2027-06-30 | Approved record and implementation evidence | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO1-P1-PR3-A03 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | Primarily recurrent with defined set-up costs | Low | Core government programme budget; approved technical assistance | KPI-SO1-P1-PR3-A03 | Coverage to be established at mobilization | Annual milestone to be confirmed in the approved workplan | All priority participating institutions nominate a focal point by 2027-09-30 | 2027-09-30 | Signed nominations and focal-point register | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO1-P1-PR4-A04 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | Primarily recurrent with defined set-up costs | Low | Core government programme budget; approved technical assistance | KPI-SO1-P1-PR4-A04 | No consolidated national role register | Annual milestone to be confirmed in the approved workplan | Owner, steward and custodian assigned for 100 per cent of priority datasets by 2028-03-31 | 2028-03-31 | Approved record and implementation evidence | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO1-P1-PR5-A05 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | Primarily recurrent with defined set-up costs | Medium | Core government programme budget; approved technical assistance | KPI-SO1-P1-PR5-A05 | Requirements are dispersed across sources and institutional procedures | Annual milestone to be confirmed in the approved workplan | Gap assessment completed and management response approved by 2027-12-31 | 2027-12-31 | Approved legal-policy gap report and response register | Unverified legal interpretation or delayed cross-government review | Use competent legal authorities and clearly separate legal requirements from proposed administrative measures. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO1-P1-PR6-A06 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | Primarily recurrent with defined set-up costs | Medium | Core government programme budget; approved technical assistance | KPI-SO1-P1-PR6-A06 | Documented SOPs and agreements are uneven | Annual milestone to be confirmed in the approved workplan | Core instrument package approved and used by all pilot institutions by 2028-06-30 | 2028-06-30 | Approved record and implementation evidence | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO2-P2-PR1-A01 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | Primarily recurrent with defined set-up costs | Medium | Core government data-management budget; targeted technical assistance | KPI-SO2-P2-PR1-A01 | No consolidated national registry; source assessments provide partial inventories | Annual milestone to be confirmed in the approved workplan | 100 per cent of priority datasets registered by 2028-06-30 | 2028-06-30 | Registry export, completeness check and owner sign-off | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO2-P2-PR2-A02 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | Primarily recurrent with defined set-up costs | Low | Core government data-management budget; targeted technical assistance | KPI-SO2-P2-PR2-A02 | Priority datasets and indicator responsibilities are not consolidated | Annual milestone to be confirmed in the approved workplan | Priority list and catalogue approved, with annual review, by 2028-09-30 | 2028-09-30 | Approved record and implementation evidence | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO2-P2-PR3-A03 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | Primarily recurrent with defined set-up costs | Medium | Core government data-management budget; targeted technical assistance | KPI-SO2-P2-PR3-A03 | Metadata documentation is uneven | Annual milestone to be confirmed in the approved workplan | Mandatory metadata complete for at least 90 per cent of priority datasets by 2029-12-31 | 2028-09-30 | Approved profile and quarterly metadata completeness report | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO2-P2-PR4-A04 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | Primarily recurrent with defined set-up costs | Medium | Core government data-management budget; targeted technical assistance | KPI-SO2-P2-PR4-A04 | Data-quality readiness 73.4 per cent; practices are not uniform | Annual milestone to be confirmed in the approved workplan | At least 85 per cent of priority datasets pass minimum QA/QC by 2029-12-31 | 2029-12-31 | Validation logs, reliability register and audit sample | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO2-P2-PR5-A05 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | Primarily recurrent with defined set-up costs | Medium | Core government data-management budget; targeted technical assistance | KPI-SO2-P2-PR5-A05 | Version and methodology documentation varies by institution | Annual milestone to be confirmed in the approved workplan | Traceability record complete for 100 per cent of priority datasets by 2030-06-30 | 2030-06-30 | Approved record and implementation evidence | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO2-P2-PR6-A06 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | Capital and recurrent | High | Core government data-management budget; targeted technical assistance | KPI-SO2-P2-PR6-A06 | Environmental data gap 29.1 per cent | Annual reduction plan approved for all critical gaps | All critical dataset gaps have an approved treatment and annual status report by 2031-12-31 | 2031-12-31 | Annual gap register and approved closure evidence | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO3-P3-PR1-A01 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | Primarily recurrent with defined set-up costs | Medium | Approved capital programme; recurrent ICT budget; partner technical assistance | KPI-SO3-P3-PR1-A01 | Source reports provide partial system mapping | Annual milestone to be confirmed in the approved workplan | All priority systems assessed and architecture principles approved by 2028-03-31 | 2028-03-31 | Approved systems inventory and readiness report | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO3-P3-PR2-A02 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | Primarily recurrent with defined set-up costs | Medium | Approved capital programme; recurrent ICT budget; partner technical assistance | KPI-SO3-P3-PR2-A02 | Exchange is active but only partly standardized | Annual milestone to be confirmed in the approved workplan | Framework approved and applied to all new integration projects by 2028-12-31 | 2028-12-31 | Approved framework and conformance-test records | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO3-P3-PR3-A03 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | Capital and recurrent | High | Approved capital programme; recurrent ICT budget; partner technical assistance | KPI-SO3-P3-PR3-A03 | Resilience arrangements are uneven across institutions | Annual milestone to be confirmed in the approved workplan | All priority repositories document controls and complete recovery testing by 2030-06-30 | 2030-06-30 | Security assessment, access review and recovery-test reports | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO3-P3-PR4-A04 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | Capital and recurrent | High | Approved capital programme; recurrent ICT budget; partner technical assistance | KPI-SO3-P3-PR4-A04 | Recurrent machine-readable flows are partial | Annual milestone to be confirmed in the approved workplan | At least 10 recurrent priority data flows pass acceptance testing by 2029-12-31 | 2029-12-31 | Acceptance reports and operational flow monitoring | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO3-P3-PR5-A05 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | Capital and recurrent | High | Approved capital programme; recurrent ICT budget; partner technical assistance | KPI-SO3-P3-PR5-A05 | Portal priority is established; operating model is not approved | Annual milestone to be confirmed in the approved workplan | Operating model approved by 2028-12-31 and minimum services operational by 2030-06-30 | 2030-06-30 | Architecture decision record, acceptance report and service dashboard | Technology procurement precedes governance and service-design decisions | Use architecture and governance decision gates before procurement and release funding by stage. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO3-P3-PR6-A06 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | Capital and recurrent | High | Approved capital programme; recurrent ICT budget; partner technical assistance | KPI-SO3-P3-PR6-A06 | To be established after integration pilots | Annual milestone to be confirmed in the approved workplan | All approved priority flows operate under service levels and renewal plans by 2031-12-31 | 2031-12-31 | Service-level reports, migration sign-off and renewal plan | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO4-P4-PR1-A01 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | Primarily recurrent with defined set-up costs | Low | Core public-information budget; approved digital-service funding | KPI-SO4-P4-PR1-A01 | No uniform national classification model is operational | Annual milestone to be confirmed in the approved workplan | 100 per cent of priority datasets classified by 2028-12-31 | 2028-12-31 | Classification register and quality-assurance sample | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO4-P4-PR2-A02 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | Primarily recurrent with defined set-up costs | Medium | Core public-information budget; approved digital-service funding | KPI-SO4-P4-PR2-A02 | Access processes are institution-specific and request-based | Annual milestone to be confirmed in the approved workplan | 100 per cent of formal access decisions logged through the workflow by 2029-06-30 | 2029-06-30 | Access decision log, service-level report and audit sample | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO4-P4-PR3-A03 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | Primarily recurrent with defined set-up costs | Medium | Core public-information budget; approved digital-service funding | KPI-SO4-P4-PR3-A03 | Full public availability 18.8 per cent | Annual milestone to be confirmed in the approved workplan | All datasets classified as public have an approved publication decision and schedule by 2030-12-31 | 2030-12-31 | Publication catalogue, release record and calendar performance report | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO4-P4-PR4-A04 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | Capital and recurrent | High | Core public-information budget; approved digital-service funding | KPI-SO4-P4-PR4-A04 | Existing services are distributed and not governed through one catalogue | Annual milestone to be confirmed in the approved workplan | At least five priority thematic services operational and accessibility-tested by 2031-06-30 | 2031-06-30 | Service acceptance, analytics and user-testing reports | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO4-P4-PR5-A05 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | Primarily recurrent with defined set-up costs | Medium | Core public-information budget; approved digital-service funding | KPI-SO4-P4-PR5-A05 | Reporting responsibilities and data flows are not consolidated | Annual milestone to be confirmed in the approved workplan | 100 per cent of priority recurring reports have documented data flows and responsible providers by 2030-12-31 | 2030-12-31 | Reporting workflow register and submission quality records | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO4-P4-PR6-A06 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | Primarily recurrent with defined set-up costs | Medium | Core public-information budget; approved digital-service funding | KPI-SO4-P4-PR6-A06 | Feedback and correction mechanisms are uneven | Annual milestone to be confirmed in the approved workplan | All public services provide tracked feedback and annual use reporting by 2031-12-31 | 2031-12-31 | Service log, researcher register and annual user report | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO5-P5-PR1-A01 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | Primarily recurrent with defined set-up costs | Medium | Annual government budgets; approved partner support; institutional training allocations | KPI-SO5-P5-PR1-A01 | Source assessments identify gaps but no consolidated competency baseline | Annual milestone to be confirmed in the approved workplan | All priority institutions complete the capacity baseline by 2027-12-31 | 2027-12-31 | Validated institutional capacity assessments | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO5-P5-PR2-A02 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | Primarily recurrent with defined set-up costs | Medium | Annual government budgets; approved partner support; institutional training allocations | KPI-SO5-P5-PR2-A02 | Training is fragmented and not linked to common role profiles | Annual milestone to be confirmed in the approved workplan | Competency framework approved and annual learning plan funded by 2028-06-30 | 2028-06-30 | Approved framework, curricula and annual learning plan | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO5-P5-PR3-A03 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | Capital and recurrent | High | Annual government budgets; approved partner support; institutional training allocations | KPI-SO5-P5-PR3-A03 | Baseline number and competency level to be confirmed in capacity assessment | Annual milestone to be confirmed in the approved workplan | At least 80 per cent of designated focal points, stewards and technical staff complete required modules by 2030-12-31 | 2030-12-31 | Attendance, assessment and certification records | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO5-P5-PR4-A04 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | Primarily recurrent with defined set-up costs | Medium | Annual government budgets; approved partner support; institutional training allocations | KPI-SO5-P5-PR4-A04 | No consolidated NEDMP trainer pool or knowledge repository | Annual milestone to be confirmed in the approved workplan | National trainer pool established and communities meet quarterly from 2029 onward | 2031-12-31 | Trainer register, meeting records and repository audit | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO5-P5-PR5-A05 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | Primarily recurrent with defined set-up costs | Medium | Annual government budgets; approved partner support; institutional training allocations | KPI-SO5-P5-PR5-A05 | Funding arrangements and recurrent needs are not consolidated | Annual resource plan submitted before the national budget cycle | Annual NEDMP resource plan and recurrent-cost review completed from 2028 onward | 2031-12-31 | Approved costing model, budget submissions and funding-gap register | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |
| SO5-P5-PR6-A06 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | Primarily recurrent with defined set-up costs | Medium | Annual government budgets; approved partner support; institutional training allocations | KPI-SO5-P5-PR6-A06 | Implementation-level KPIs exist; no action-level integrated tracker | Four quarterly reviews and one annual management response completed each year | Quarterly reviews, annual management responses and final evaluation completed through 2031 | 2031-12-31 | Dashboard exports, review reports and approved management responses | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. | Proposed action and indicative timing; requires national validation, legal review where relevant and budget approval. |

## Annex B. Detailed Task Register

Table 21. Detailed task register

| Task ID | Action ID | Task | Deliverable | Predecessor | Start | Completion | Lead | Support | Milestone | Verification | Status | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01-T01 | SO1-P1-PR1-A01 | Confirm the approval pathway and competent decision authority. | Task 1 working output for Endorse the NEDMP implementation instruments and governance charter | None | 2027-01-01 | 2027-02-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Working output | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR1-A01-T02 | SO1-P1-PR1-A01 | Prepare and consult the governance charter and committee terms of reference. | Task 2 working output for Endorse the NEDMP implementation instruments and governance charter | SO1-P1-PR1-A01-T01 | 2027-03-01 | 2027-04-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR1-A01-01 | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR1-A01-T03 | SO1-P1-PR1-A01 | Secure endorsement and publish the initial decision calendar. | Approved governance charter, endorsement record and decision calendar | SO1-P1-PR1-A01-T02 | 2027-05-01 | 2027-06-30 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR1-A01-02 | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR2-A02-T01 | SO1-P1-PR2-A02 | Approve the programme charter, staffing model and delegated authorities. | Task 1 working output for Activate the NEDMP programme management and coordination function | SO1-P1-PR1-A01 | 2027-01-01 | 2027-02-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Working output | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR2-A02-T02 | SO1-P1-PR2-A02 | Establish the action register, issue log, document control and reporting templates. | Task 2 working output for Activate the NEDMP programme management and coordination function | SO1-P1-PR2-A02-T01 | 2027-03-01 | 2027-04-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR2-A02-01 | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR2-A02-T03 | SO1-P1-PR2-A02 | Launch monthly delivery review and quarterly governance reporting. | Operational programme charter, workplan, issue register and reporting calendar | SO1-P1-PR2-A02-T02 | 2027-05-01 | 2027-06-30 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR2-A02-02 | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR3-A03-T01 | SO1-P1-PR3-A03 | Confirm priority institutions and issue the nomination request. | Task 1 working output for Establish the institutional environmental data focal-point network | SO1-P1-PR1-A01 | 2027-03-01 | 2027-04-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Working output | Signed nominations and focal-point register | Planned | 0 |
| SO1-P1-PR3-A03-T02 | SO1-P1-PR3-A03 | Validate nominees, alternates and role expectations. | Task 2 working output for Establish the institutional environmental data focal-point network | SO1-P1-PR3-A03-T01 | 2027-05-01 | 2027-06-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR3-A03-01 | Signed nominations and focal-point register | Planned | 0 |
| SO1-P1-PR3-A03-T03 | SO1-P1-PR3-A03 | Operate quarterly focal-point clinics and maintain the register. | Approved focal-point register, role profile and engagement schedule | SO1-P1-PR3-A03-T02 | 2027-07-01 | 2027-09-30 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR3-A03-02 | Signed nominations and focal-point register | Planned | 0 |
| SO1-P1-PR4-A04-T01 | SO1-P1-PR4-A04 | Approve national role definitions and decision rights. | Task 1 working output for Assign data owners, stewards and custodians for priority datasets | SO1-P1-PR1-A03; SO2-P2-PR1-A01 | 2027-06-01 | 2027-08-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Working output | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR4-A04-T02 | SO1-P1-PR4-A04 | Map roles to priority datasets and institutional systems. | Task 2 working output for Assign data owners, stewards and custodians for priority datasets | SO1-P1-PR4-A04-T01 | 2027-09-01 | 2027-11-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR4-A04-01 | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR4-A04-T03 | SO1-P1-PR4-A04 | Validate assignments and integrate them into registry and access workflows. | Dataset-level responsibility and decision-rights register | SO1-P1-PR4-A04-T02 | 2027-12-01 | 2028-03-31 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR4-A04-02 | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR5-A05-T01 | SO1-P1-PR5-A05 | Compile applicable legal, policy, confidentiality and reporting requirements. | Task 1 working output for Complete the environmental data legal and policy gap assessment | SO1-P1-PR1-A01 | 2027-04-01 | 2027-06-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Working output | Approved legal-policy gap report and response register | Planned | 0 |
| SO1-P1-PR5-A05-T02 | SO1-P1-PR5-A05 | Assess gaps affecting classification, sharing, publication, retention and security. | Task 2 working output for Complete the environmental data legal and policy gap assessment | SO1-P1-PR5-A05-T01 | 2027-07-01 | 2027-09-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR5-A05-01 | Approved legal-policy gap report and response register | Planned | 0 |
| SO1-P1-PR5-A05-T03 | SO1-P1-PR5-A05 | Validate a response register identifying legal review, policy and administrative actions. | Legal-policy gap report and prioritized amendment or guidance register | SO1-P1-PR5-A05-T02 | 2027-10-01 | 2027-12-31 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR5-A05-02 | Approved legal-policy gap report and response register | Planned | 0 |
| SO1-P1-PR6-A06-T01 | SO1-P1-PR6-A06 | Draft governance, dataset registration, quality, access and escalation SOPs. | Task 1 working output for Approve the core governance policy, SOP and data-sharing instrument package | SO1-P1-PR1-A05; SO1-P1-PR1-A04 | 2027-09-01 | 2027-11-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Working output | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR6-A06-T02 | SO1-P1-PR6-A06 | Prepare data-sharing agreement, memorandum and release-decision templates. | Task 2 working output for Approve the core governance policy, SOP and data-sharing instrument package | SO1-P1-PR6-A06-T01 | 2027-12-01 | 2028-02-01 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR6-A06-01 | Approved record and implementation evidence | Planned | 0 |
| SO1-P1-PR6-A06-T03 | SO1-P1-PR6-A06 | Pilot, revise, approve and place the instruments under document control. | Governance policy, core SOP library, agreement templates and compliance checklist | SO1-P1-PR6-A06-T02 | 2028-03-01 | 2028-06-30 | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | M-SO1-P1-PR6-A06-02 | Approved record and implementation evidence | Planned | 0 |
| SO2-P2-PR1-A01-T01 | SO2-P2-PR1-A01 | Approve the registry data model and institutional submission template. | Task 1 working output for Complete the national environmental dataset inventory and registry | SO1-P1-PR1-A03 | 2027-03-01 | 2027-07-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Working output | Registry export, completeness check and owner sign-off | In progress | 25 |
| SO2-P2-PR1-A01-T02 | SO2-P2-PR1-A01 | Collect and validate dataset records from priority institutions. | Task 2 working output for Complete the national environmental dataset inventory and registry | SO2-P2-PR1-A01-T01 | 2027-08-01 | 2027-12-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR1-A01-01 | Registry export, completeness check and owner sign-off | Planned | 0 |
| SO2-P2-PR1-A01-T03 | SO2-P2-PR1-A01 | Publish the governed internal registry and establish quarterly updates. | National registry of priority datasets, owners, sources, update cycles and gaps | SO2-P2-PR1-A01-T02 | 2028-01-01 | 2028-06-30 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR1-A01-02 | Registry export, completeness check and owner sign-off | Planned | 0 |
| SO2-P2-PR2-A02-T01 | SO2-P2-PR2-A02 | Define prioritization criteria linked to law, assessment, SDGs, MEAs and public value. | Task 1 working output for Approve the priority and authoritative dataset list and indicator catalogue | SO2-P2-PR1-A01 | 2027-09-01 | 2027-12-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Working output | Approved record and implementation evidence | Planned | 0 |
| SO2-P2-PR2-A02-T02 | SO2-P2-PR2-A02 | Review candidate datasets and reconcile conflicting indicator definitions. | Task 2 working output for Approve the priority and authoritative dataset list and indicator catalogue | SO2-P2-PR2-A02-T01 | 2028-01-01 | 2028-04-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR2-A02-01 | Approved record and implementation evidence | Planned | 0 |
| SO2-P2-PR2-A02-T03 | SO2-P2-PR2-A02 | Approve the catalogue, responsible providers and review cycle. | Approved priority dataset list and environmental indicator catalogue | SO2-P2-PR2-A02-T02 | 2028-05-01 | 2028-09-30 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR2-A02-02 | Approved record and implementation evidence | Planned | 0 |
| SO2-P2-PR3-A03-T01 | SO2-P2-PR3-A03 | Define mandatory discovery, methodology, quality, spatial and access metadata. | Task 1 working output for Issue the national environmental metadata profile, dictionaries and vocabularies | SO2-P2-PR1-A01; SO2-P2-PR1-A02 | 2027-09-01 | 2027-12-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Working output | Approved profile and quarterly metadata completeness report | Planned | 0 |
| SO2-P2-PR3-A03-T02 | SO2-P2-PR3-A03 | Develop environmental data dictionaries and controlled vocabularies. | Task 2 working output for Issue the national environmental metadata profile, dictionaries and vocabularies | SO2-P2-PR3-A03-T01 | 2028-01-01 | 2028-04-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR3-A03-01 | Approved profile and quarterly metadata completeness report | Planned | 0 |
| SO2-P2-PR3-A03-T03 | SO2-P2-PR3-A03 | Pilot the profile, approve it and embed validation in the registry. | Minimum metadata profile, data dictionary template and controlled vocabularies | SO2-P2-PR3-A03-T02 | 2028-05-01 | 2028-09-30 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR3-A03-02 | Approved profile and quarterly metadata completeness report | Planned | 0 |
| SO2-P2-PR4-A04-T01 | SO2-P2-PR4-A04 | Approve data-quality dimensions, thresholds and exception rules. | Task 1 working output for Implement minimum QA/QC, validation and reliability grading | SO2-P2-PR1-A03; SO1-P1-PR1-A04 | 2028-01-01 | 2028-08-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Working output | Validation logs, reliability register and audit sample | Planned | 0 |
| SO2-P2-PR4-A04-T02 | SO2-P2-PR4-A04 | Assign quality reviewers and implement validation and reliability grading. | Task 2 working output for Implement minimum QA/QC, validation and reliability grading | SO2-P2-PR4-A04-T01 | 2028-09-01 | 2029-04-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR4-A04-01 | Validation logs, reliability register and audit sample | Planned | 0 |
| SO2-P2-PR4-A04-T03 | SO2-P2-PR4-A04 | Report failures, corrective actions and approved exceptions quarterly. | National quality-control standard, validation checklist and reliability register | SO2-P2-PR4-A04-T02 | 2029-05-01 | 2029-12-31 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR4-A04-02 | Validation logs, reliability register and audit sample | Planned | 0 |
| SO2-P2-PR5-A05-T01 | SO2-P2-PR5-A05 | Define dataset identifiers, version rules and provenance requirements. | Task 1 working output for Establish version control, provenance, traceability and methodology records | SO2-P2-PR1-A03; SO2-P2-PR1-A04 | 2028-04-01 | 2028-12-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Working output | Approved record and implementation evidence | Planned | 0 |
| SO2-P2-PR5-A05-T02 | SO2-P2-PR5-A05 | Document source methods, transformations, limitations and custody history. | Task 2 working output for Establish version control, provenance, traceability and methodology records | SO2-P2-PR5-A05-T01 | 2029-01-01 | 2029-09-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR5-A05-01 | Approved record and implementation evidence | Planned | 0 |
| SO2-P2-PR5-A05-T03 | SO2-P2-PR5-A05 | Implement audit trails and periodic traceability checks. | Provenance and methodology record linked to each priority dataset | SO2-P2-PR5-A05-T02 | 2029-10-01 | 2030-06-30 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR5-A05-02 | Approved record and implementation evidence | Planned | 0 |
| SO2-P2-PR6-A06-T01 | SO2-P2-PR6-A06 | Rank gaps by legal, assessment, reporting and environmental-governance impact. | Task 1 working output for Implement data-quality improvement and priority gap-closure plans | SO2-P2-PR1-A01; SO2-P2-PR1-A04 | 2028-07-01 | 2029-08-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Working output | Annual gap register and approved closure evidence | Planned | 0 |
| SO2-P2-PR6-A06-T02 | SO2-P2-PR6-A06 | Approve dataset-specific corrective actions, owners, resources and schedules. | Task 2 working output for Implement data-quality improvement and priority gap-closure plans | SO2-P2-PR6-A06-T01 | 2029-09-01 | 2030-10-01 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR6-A06-01 | Annual gap register and approved closure evidence | Planned | 0 |
| SO2-P2-PR6-A06-T03 | SO2-P2-PR6-A06 | Review closure evidence annually and reprioritize unresolved gaps. | Annual thematic quality and gap-closure plans with tracked corrective actions | SO2-P2-PR6-A06-T02 | 2030-11-01 | 2031-12-31 | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | M-SO2-P2-PR6-A06-02 | Annual gap register and approved closure evidence | Planned | 0 |
| SO3-P3-PR1-A01-T01 | SO3-P3-PR1-A01 | Inventory eMISK, institutional repositories, GIS, monitoring and reporting systems. | Task 1 working output for Complete the systems inventory, digital-readiness assessment and target architecture | SO1-P1-PR1-A03 | 2027-04-01 | 2027-07-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Working output | Approved systems inventory and readiness report | In progress | 35 |
| SO3-P3-PR1-A01-T02 | SO3-P3-PR1-A01 | Assess interfaces, data models, hosting, security, backup and integration readiness. | Task 2 working output for Complete the systems inventory, digital-readiness assessment and target architecture | SO3-P3-PR1-A01-T01 | 2027-08-01 | 2027-11-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR1-A01-01 | Approved systems inventory and readiness report | Planned | 0 |
| SO3-P3-PR1-A01-T03 | SO3-P3-PR1-A01 | Approve technology-neutral target architecture principles and decision criteria. | Systems inventory, readiness scorecard and approved target architecture principles | SO3-P3-PR1-A01-T02 | 2027-12-01 | 2028-03-31 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR1-A01-02 | Approved systems inventory and readiness report | Planned | 0 |
| SO3-P3-PR2-A02-T01 | SO3-P3-PR2-A02 | Define standard exchange formats, identifiers, vocabularies and API requirements. | Task 1 working output for Approve the national environmental data interoperability framework | SO3-P3-PR1-A01; SO2-P2-PR1-A03 | 2027-10-01 | 2028-02-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Working output | Approved framework and conformance-test records | Planned | 0 |
| SO3-P3-PR2-A02-T02 | SO3-P3-PR2-A02 | Align spatial exchange, metadata harvesting and statistical data exchange profiles. | Task 2 working output for Approve the national environmental data interoperability framework | SO3-P3-PR2-A02-T01 | 2028-03-01 | 2028-07-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR2-A02-01 | Approved framework and conformance-test records | Planned | 0 |
| SO3-P3-PR2-A02-T03 | SO3-P3-PR2-A02 | Approve conformance tests, exception procedures and version management. | Interoperability framework covering formats, APIs, identifiers, spatial and statistical exchange | SO3-P3-PR2-A02-T02 | 2028-08-01 | 2028-12-31 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR2-A02-02 | Approved framework and conformance-test records | Planned | 0 |
| SO3-P3-PR3-A03-T01 | SO3-P3-PR3-A03 | Approve minimum identity, access, logging, security and data-sovereignty controls. | Task 1 working output for Establish identity, cybersecurity, backup and business-continuity controls | SO3-P3-PR1-A01; SO1-P1-PR1-A05 | 2027-10-01 | 2028-08-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Working output | Security assessment, access review and recovery-test reports | Planned | 0 |
| SO3-P3-PR3-A03-T02 | SO3-P3-PR3-A03 | Document backup, recovery, hosting responsibilities and service dependencies. | Task 2 working output for Establish identity, cybersecurity, backup and business-continuity controls | SO3-P3-PR3-A03-T01 | 2028-09-01 | 2029-07-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR3-A03-01 | Security assessment, access review and recovery-test reports | Planned | 0 |
| SO3-P3-PR3-A03-T03 | SO3-P3-PR3-A03 | Conduct annual recovery tests and track corrective actions. | Minimum security and continuity control baseline with tested recovery plans | SO3-P3-PR3-A03-T02 | 2029-08-01 | 2030-06-30 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR3-A03-02 | Security assessment, access review and recovery-test reports | Planned | 0 |
| SO3-P3-PR4-A04-T01 | SO3-P3-PR4-A04 | Select pilot flows using readiness, value, risk and dependency criteria. | Task 1 working output for Pilot governed recurrent data flows linked to eMISK | SO3-P3-PR1-A02; SO3-P3-PR1-A03; SO4-P4-PR1-A01 | 2028-07-01 | 2028-12-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Working output | Acceptance reports and operational flow monitoring | Planned | 0 |
| SO3-P3-PR4-A04-T02 | SO3-P3-PR4-A04 | Configure exchange specifications, metadata and quality gates. | Task 2 working output for Pilot governed recurrent data flows linked to eMISK | SO3-P3-PR4-A04-T01 | 2029-01-01 | 2029-06-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR4-A04-01 | Acceptance reports and operational flow monitoring | Planned | 0 |
| SO3-P3-PR4-A04-T03 | SO3-P3-PR4-A04 | Test performance, security, recovery and institutional acceptance before scale-up. | Validated integration pilots with metadata, QA/QC, classification and audit controls | SO3-P3-PR4-A04-T02 | 2029-07-01 | 2029-12-31 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR4-A04-02 | Acceptance reports and operational flow monitoring | Planned | 0 |
| SO3-P3-PR5-A05-T01 | SO3-P3-PR5-A05 | Evaluate enhancement, federated catalogue, central repository and hybrid options. | Task 1 working output for Approve and implement the National Environmental Data Portal operating model | SO3-P3-PR1-A01; SO1-P1-PR1-A06; SO4-P4-PR1-A01 | 2028-01-01 | 2028-10-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Working output | Architecture decision record, acceptance report and service dashboard | Planned | 0 |
| SO3-P3-PR5-A05-T02 | SO3-P3-PR5-A05 | Approve governance, service ownership, architecture, security and procurement approach. | Task 2 working output for Approve and implement the National Environmental Data Portal operating model | SO3-P3-PR5-A05-T01 | 2028-11-01 | 2029-08-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR5-A05-01 | Architecture decision record, acceptance report and service dashboard | Planned | 0 |
| SO3-P3-PR5-A05-T03 | SO3-P3-PR5-A05 | Implement registry, metadata, access and publication modules in phased releases. | Approved federated or hybrid operating model and operational minimum viable portal services | SO3-P3-PR5-A05-T02 | 2029-09-01 | 2030-06-30 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR5-A05-02 | Architecture decision record, acceptance report and service dashboard | Planned | 0 |
| SO3-P3-PR6-A06-T01 | SO3-P3-PR6-A06 | Prioritize scale-up based on pilot evidence and institutional readiness. | Task 1 working output for Scale integration, migration, service management and technology renewal | SO3-P3-PR1-A04; SO3-P3-PR1-A05 | 2030-01-01 | 2030-08-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Working output | Service-level reports, migration sign-off and renewal plan | Planned | 0 |
| SO3-P3-PR6-A06-T02 | SO3-P3-PR6-A06 | Execute approved migration and integration waves with acceptance criteria. | Task 2 working output for Scale integration, migration, service management and technology renewal | SO3-P3-PR6-A06-T01 | 2030-09-01 | 2031-04-01 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR6-A06-01 | Service-level reports, migration sign-off and renewal plan | Planned | 0 |
| SO3-P3-PR6-A06-T03 | SO3-P3-PR6-A06 | Operate service monitoring, vendor-exit, maintenance and technology-renewal controls. | Scaled integration portfolio, migration records, service levels and renewal plan | SO3-P3-PR6-A06-T02 | 2031-05-01 | 2031-12-31 | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | M-SO3-P3-PR6-A06-02 | Service-level reports, migration sign-off and renewal plan | Planned | 0 |
| SO4-P4-PR1-A01-T01 | SO4-P4-PR1-A01 | Approve classification criteria, decision authority and review triggers. | Task 1 working output for Operationalize the five-level environmental data classification model | SO1-P1-PR1-A05; SO2-P2-PR1-A01 | 2027-04-01 | 2027-10-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Working output | Classification register and quality-assurance sample | Planned | 0 |
| SO4-P4-PR1-A01-T02 | SO4-P4-PR1-A01 | Assess priority datasets and record rationale, owner and review date. | Task 2 working output for Operationalize the five-level environmental data classification model | SO4-P4-PR1-A01-T01 | 2027-11-01 | 2028-05-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR1-A01-01 | Classification register and quality-assurance sample | Planned | 0 |
| SO4-P4-PR1-A01-T03 | SO4-P4-PR1-A01 | Audit classification consistency and resolve disputed decisions. | Approved classification policy, assessment tool and classification register | SO4-P4-PR1-A01-T02 | 2028-06-01 | 2028-12-31 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR1-A01-02 | Classification register and quality-assurance sample | Planned | 0 |
| SO4-P4-PR2-A02-T01 | SO4-P4-PR2-A02 | Approve request categories, review triggers, service levels and decision authorities. | Task 1 working output for Implement access request, approval, release, licensing and appeal workflows | SO4-P4-PR1-A01; SO1-P1-PR1-A06 | 2027-10-01 | 2028-04-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Working output | Access decision log, service-level report and audit sample | Planned | 0 |
| SO4-P4-PR2-A02-T02 | SO4-P4-PR2-A02 | Configure request intake, legal/security review, release conditions and licensing. | Task 2 working output for Implement access request, approval, release, licensing and appeal workflows | SO4-P4-PR2-A02-T01 | 2028-05-01 | 2028-11-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR2-A02-01 | Access decision log, service-level report and audit sample | Planned | 0 |
| SO4-P4-PR2-A02-T03 | SO4-P4-PR2-A02 | Publish guidance and report request volumes, timeliness and outcomes. | Controlled access workflow with decision log, conditions, licensing and appeal route | SO4-P4-PR2-A02-T02 | 2028-12-01 | 2029-06-30 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR2-A02-02 | Access decision log, service-level report and audit sample | Planned | 0 |
| SO4-P4-PR3-A03-T01 | SO4-P4-PR3-A03 | Define publication readiness for metadata, QA/QC, limitations, licensing and accessibility. | Task 1 working output for Operate a publication-readiness and open environmental data calendar | SO4-P4-PR1-A01; SO2-P2-PR1-A04 | 2028-01-01 | 2028-12-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Working output | Publication catalogue, release record and calendar performance report | In progress | 20 |
| SO4-P4-PR3-A03-T02 | SO4-P4-PR3-A03 | Select low-risk datasets and indicators for phased release. | Task 2 working output for Operate a publication-readiness and open environmental data calendar | SO4-P4-PR3-A03-T01 | 2029-01-01 | 2029-12-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR3-A03-01 | Publication catalogue, release record and calendar performance report | Planned | 0 |
| SO4-P4-PR3-A03-T03 | SO4-P4-PR3-A03 | Publish the annual calendar and monitor timeliness, reuse and corrections. | Approved publication checklist, annual calendar and release catalogue | SO4-P4-PR3-A03-T02 | 2030-01-01 | 2030-12-31 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR3-A03-02 | Publication catalogue, release record and calendar performance report | Planned | 0 |
| SO4-P4-PR4-A04-T01 | SO4-P4-PR4-A04 | Prioritize user needs and policy questions using the indicator catalogue. | Task 1 working output for Develop national environmental dashboards, maps and information services | SO4-P4-PR1-A03; SO3-P3-PR1-A05 | 2029-01-01 | 2029-10-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Working output | Service acceptance, analytics and user-testing reports | Planned | 0 |
| SO4-P4-PR4-A04-T02 | SO4-P4-PR4-A04 | Design services using approved data, metadata, quality and accessibility standards. | Task 2 working output for Develop national environmental dashboards, maps and information services | SO4-P4-PR4-A04-T01 | 2029-11-01 | 2030-08-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR4-A04-01 | Service acceptance, analytics and user-testing reports | Planned | 0 |
| SO4-P4-PR4-A04-T03 | SO4-P4-PR4-A04 | Test with decision-makers and users, publish, maintain and monitor use. | Prioritized dashboards, map services and environmental information products | SO4-P4-PR4-A04-T02 | 2030-09-01 | 2031-06-30 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR4-A04-02 | Service acceptance, analytics and user-testing reports | Planned | 0 |
| SO4-P4-PR5-A05-T01 | SO4-P4-PR5-A05 | Inventory recurring national and international reporting obligations. | Task 1 working output for Standardize national, SDG, MEA and State of the Environment reporting workflows | SO2-P2-PR1-A02; SO3-P3-PR1-A04 | 2028-07-01 | 2029-04-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Working output | Reporting workflow register and submission quality records | Planned | 0 |
| SO4-P4-PR5-A05-T02 | SO4-P4-PR5-A05 | Map indicators to authoritative datasets, providers, validation and submission dates. | Task 2 working output for Standardize national, SDG, MEA and State of the Environment reporting workflows | SO4-P4-PR5-A05-T01 | 2029-05-01 | 2030-02-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR5-A05-01 | Reporting workflow register and submission quality records | Planned | 0 |
| SO4-P4-PR5-A05-T03 | SO4-P4-PR5-A05 | Pilot automated or semi-automated reporting workflows and verify outputs. | Reporting workflow register linking indicators, providers, calendars and verification | SO4-P4-PR5-A05-T02 | 2030-03-01 | 2030-12-31 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR5-A05-02 | Reporting workflow register and submission quality records | Planned | 0 |
| SO4-P4-PR6-A06-T01 | SO4-P4-PR6-A06 | Approve feedback, correction, response and escalation service levels. | Task 1 working output for Operate user feedback, data correction, researcher access and data-use monitoring | SO4-P4-PR1-A02; SO4-P4-PR1-A03 | 2029-01-01 | 2029-12-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Working output | Service log, researcher register and annual user report | Planned | 0 |
| SO4-P4-PR6-A06-T02 | SO4-P4-PR6-A06 | Establish researcher access safeguards and acknowledgement conditions. | Task 2 working output for Operate user feedback, data correction, researcher access and data-use monitoring | SO4-P4-PR6-A06-T01 | 2030-01-01 | 2030-12-01 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR6-A06-01 | Service log, researcher register and annual user report | Planned | 0 |
| SO4-P4-PR6-A06-T03 | SO4-P4-PR6-A06 | Analyse use, unmet demand, corrections and user satisfaction annually. | Feedback and correction service, researcher-access protocol and data-use report | SO4-P4-PR6-A06-T02 | 2031-01-01 | 2031-12-31 | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | M-SO4-P4-PR6-A06-02 | Service log, researcher register and annual user report | Planned | 0 |
| SO5-P5-PR1-A01-T01 | SO5-P5-PR1-A01 | Approve role and competency assessment instruments. | Task 1 working output for Complete institutional capacity, staffing and training-needs assessments | SO1-P1-PR1-A03 | 2027-03-01 | 2027-05-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Working output | Validated institutional capacity assessments | In progress | 30 |
| SO5-P5-PR1-A01-T02 | SO5-P5-PR1-A01 | Assess staffing, competencies, workload, retention and succession risks. | Task 2 working output for Complete institutional capacity, staffing and training-needs assessments | SO5-P5-PR1-A01-T01 | 2027-06-01 | 2027-08-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR1-A01-01 | Validated institutional capacity assessments | Planned | 0 |
| SO5-P5-PR1-A01-T03 | SO5-P5-PR1-A01 | Validate institutional learning and workforce action plans. | Institutional capacity baseline, role profiles and prioritized learning-needs register | SO5-P5-PR1-A01-T02 | 2027-09-01 | 2027-12-31 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR1-A01-02 | Validated institutional capacity assessments | Planned | 0 |
| SO5-P5-PR2-A02-T01 | SO5-P5-PR2-A02 | Define competencies for leaders, focal points, stewards and technical specialists. | Task 1 working output for Approve the NEDMP competency framework and role-based learning pathways | SO5-P5-PR1-A01 | 2027-09-01 | 2027-11-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Working output | Approved framework, curricula and annual learning plan | Planned | 0 |
| SO5-P5-PR2-A02-T02 | SO5-P5-PR2-A02 | Develop modular pathways for governance, metadata, QA/QC, GIS, APIs, security and reporting. | Task 2 working output for Approve the NEDMP competency framework and role-based learning pathways | SO5-P5-PR2-A02-T01 | 2027-12-01 | 2028-02-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR2-A02-01 | Approved framework, curricula and annual learning plan | Planned | 0 |
| SO5-P5-PR2-A02-T03 | SO5-P5-PR2-A02 | Approve assessment, certification, refresher and training-record requirements. | Competency framework, curricula and annual learning plan | SO5-P5-PR2-A02-T02 | 2028-03-01 | 2028-06-30 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR2-A02-02 | Approved framework, curricula and annual learning plan | Planned | 0 |
| SO5-P5-PR3-A03-T01 | SO5-P5-PR3-A03 | Nominate trainees and schedule role-based cohorts. | Task 1 working output for Deliver and certify role-based NEDMP training | SO5-P5-PR1-A02 | 2028-04-01 | 2029-02-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Working output | Attendance, assessment and certification records | Planned | 0 |
| SO5-P5-PR3-A03-T02 | SO5-P5-PR3-A03 | Deliver applied modules linked to dataset onboarding and integration pilots. | Task 2 working output for Deliver and certify role-based NEDMP training | SO5-P5-PR3-A03-T01 | 2029-03-01 | 2030-01-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR3-A03-01 | Attendance, assessment and certification records | Planned | 0 |
| SO5-P5-PR3-A03-T03 | SO5-P5-PR3-A03 | Assess competency, certify completion and address learning gaps. | Completed learning cohorts, competency assessments and certification records | SO5-P5-PR3-A03-T02 | 2030-02-01 | 2030-12-31 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR3-A03-02 | Attendance, assessment and certification records | Planned | 0 |
| SO5-P5-PR4-A04-T01 | SO5-P5-PR4-A04 | Select and prepare national trainers and technical mentors. | Task 1 working output for Establish train-the-trainer, communities of practice and knowledge management | SO5-P5-PR1-A02; SO5-P5-PR1-A03 | 2028-07-01 | 2029-08-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Working output | Trainer register, meeting records and repository audit | Planned | 0 |
| SO5-P5-PR4-A04-T02 | SO5-P5-PR4-A04 | Launch thematic communities of practice and quarterly problem-solving clinics. | Task 2 working output for Establish train-the-trainer, communities of practice and knowledge management | SO5-P5-PR4-A04-T01 | 2029-09-01 | 2030-10-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR4-A04-01 | Trainer register, meeting records and repository audit | Planned | 0 |
| SO5-P5-PR4-A04-T03 | SO5-P5-PR4-A04 | Maintain approved guidance, templates, lessons and version-controlled knowledge products. | Trainer pool, quarterly communities of practice and controlled knowledge repository | SO5-P5-PR4-A04-T02 | 2030-11-01 | 2031-12-31 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR4-A04-02 | Trainer register, meeting records and repository audit | Planned | 0 |
| SO5-P5-PR5-A05-T01 | SO5-P5-PR5-A05 | Approve cost categories, assumptions, cost bands and detailed-costing responsibilities. | Task 1 working output for Establish multi-year resource, costing and financing arrangements | SO1-P1-PR1-A02 | 2027-06-01 | 2028-11-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Working output | Approved costing model, budget submissions and funding-gap register | Planned | 0 |
| SO5-P5-PR5-A05-T02 | SO5-P5-PR5-A05 | Prepare the five-year resource profile and identify recurrent and capital requirements. | Task 2 working output for Establish multi-year resource, costing and financing arrangements | SO5-P5-PR5-A05-T01 | 2028-12-01 | 2030-05-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR5-A05-01 | Approved costing model, budget submissions and funding-gap register | Planned | 0 |
| SO5-P5-PR5-A05-T03 | SO5-P5-PR5-A05 | Integrate approved needs into annual budgets and track funding gaps and partner support. | Costing model, multi-year resource profile, annual budget responsibilities and funding-gap register | SO5-P5-PR5-A05-T02 | 2030-06-01 | 2031-12-31 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR5-A05-02 | Approved costing model, budget submissions and funding-gap register | Planned | 0 |
| SO5-P5-PR6-A06-T01 | SO5-P5-PR6-A06 | Operate action, KPI, risk, dependency and corrective-action registers. | Task 1 working output for Institutionalize monitoring, adaptive management, succession and responsible AI readiness | SO1-P1-PR1-A02; SO5-P5-PR1-A05 | 2027-01-01 | 2028-08-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Working output | Dashboard exports, review reports and approved management responses | Planned | 0 |
| SO5-P5-PR6-A06-T02 | SO5-P5-PR6-A06 | Conduct quarterly, annual, mid-term and final reviews with management responses. | Task 2 working output for Institutionalize monitoring, adaptive management, succession and responsible AI readiness | SO5-P5-PR6-A06-T01 | 2028-09-01 | 2030-04-01 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR6-A06-01 | Dashboard exports, review reports and approved management responses | Planned | 0 |
| SO5-P5-PR6-A06-T03 | SO5-P5-PR6-A06 | Maintain succession, continuity, standards-review and responsible AI readiness controls. | Operational monitoring dashboard, review cycle, succession controls and AI-readiness gate | SO5-P5-PR6-A06-T02 | 2030-05-01 | 2031-12-31 | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | M-SO5-P5-PR6-A06-02 | Dashboard exports, review reports and approved management responses | Planned | 0 |

## Annex C. NEDMP Objectives-Pillars-Actions Matrix

Table 22. Objectives, pillars and actions

| Action ID | Objective | Primary pillar | Secondary | Outcome | Challenge | Programme | Deliverable | KPI |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | SO1 | Pillar 1 | Cross-pillar dependency | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | C01 | PR1 | Approved governance charter, endorsement record and decision calendar | KPI-SO1-P1-PR1-A01 |
| SO1-P1-PR2-A02 | SO1 | Pillar 1 | Cross-pillar dependency | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | C02 | PR2 | Operational programme charter, workplan, issue register and reporting calendar | KPI-SO1-P1-PR2-A02 |
| SO1-P1-PR3-A03 | SO1 | Pillar 1 | Cross-pillar dependency | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | C02 | PR3 | Approved focal-point register, role profile and engagement schedule | KPI-SO1-P1-PR3-A03 |
| SO1-P1-PR4-A04 | SO1 | Pillar 1 | Cross-pillar dependency | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | C03 | PR4 | Dataset-level responsibility and decision-rights register | KPI-SO1-P1-PR4-A04 |
| SO1-P1-PR5-A05 | SO1 | Pillar 1 | Cross-pillar dependency | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | C04 | PR5 | Legal-policy gap report and prioritized amendment or guidance register | KPI-SO1-P1-PR5-A05 |
| SO1-P1-PR6-A06 | SO1 | Pillar 1 | Cross-pillar dependency | A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | C04 | PR6 | Governance policy, core SOP library, agreement templates and compliance checklist | KPI-SO1-P1-PR6-A06 |
| SO2-P2-PR1-A01 | SO2 | Pillar 2 | Cross-pillar dependency | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | C06 | PR1 | National registry of priority datasets, owners, sources, update cycles and gaps | KPI-SO2-P2-PR1-A01 |
| SO2-P2-PR2-A02 | SO2 | Pillar 2 | Cross-pillar dependency | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | C06 | PR2 | Approved priority dataset list and environmental indicator catalogue | KPI-SO2-P2-PR2-A02 |
| SO2-P2-PR3-A03 | SO2 | Pillar 2 | Cross-pillar dependency | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | C05 | PR3 | Minimum metadata profile, data dictionary template and controlled vocabularies | KPI-SO2-P2-PR3-A03 |
| SO2-P2-PR4-A04 | SO2 | Pillar 2 | Cross-pillar dependency | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | C05 | PR4 | National quality-control standard, validation checklist and reliability register | KPI-SO2-P2-PR4-A04 |
| SO2-P2-PR5-A05 | SO2 | Pillar 2 | Cross-pillar dependency | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | C05 | PR5 | Provenance and methodology record linked to each priority dataset | KPI-SO2-P2-PR5-A05 |
| SO2-P2-PR6-A06 | SO2 | Pillar 2 | Cross-pillar dependency | Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | C06 | PR6 | Annual thematic quality and gap-closure plans with tracked corrective actions | KPI-SO2-P2-PR6-A06 |
| SO3-P3-PR1-A01 | SO3 | Pillar 3 | Cross-pillar dependency | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | C14 | PR1 | Systems inventory, readiness scorecard and approved target architecture principles | KPI-SO3-P3-PR1-A01 |
| SO3-P3-PR2-A02 | SO3 | Pillar 3 | Cross-pillar dependency | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | C07 | PR2 | Interoperability framework covering formats, APIs, identifiers, spatial and statistical exchange | KPI-SO3-P3-PR2-A02 |
| SO3-P3-PR3-A03 | SO3 | Pillar 3 | Cross-pillar dependency | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | C08 | PR3 | Minimum security and continuity control baseline with tested recovery plans | KPI-SO3-P3-PR3-A03 |
| SO3-P3-PR4-A04 | SO3 | Pillar 3 | Cross-pillar dependency | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | C07 | PR4 | Validated integration pilots with metadata, QA/QC, classification and audit controls | KPI-SO3-P3-PR4-A04 |
| SO3-P3-PR5-A05 | SO3 | Pillar 3 | Cross-pillar dependency | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | C14 | PR5 | Approved federated or hybrid operating model and operational minimum viable portal services | KPI-SO3-P3-PR5-A05 |
| SO3-P3-PR6-A06 | SO3 | Pillar 3 | Cross-pillar dependency | Priority environmental data flows move securely between systems through agreed standards and governed integration services. | C07 | PR6 | Scaled integration portfolio, migration records, service levels and renewal plan | KPI-SO3-P3-PR6-A06 |
| SO4-P4-PR1-A01 | SO4 | Pillar 4 | Cross-pillar dependency | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | C10 | PR1 | Approved classification policy, assessment tool and classification register | KPI-SO4-P4-PR1-A01 |
| SO4-P4-PR2-A02 | SO4 | Pillar 4 | Cross-pillar dependency | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | C10 | PR2 | Controlled access workflow with decision log, conditions, licensing and appeal route | KPI-SO4-P4-PR2-A02 |
| SO4-P4-PR3-A03 | SO4 | Pillar 4 | Cross-pillar dependency | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | C09 | PR3 | Approved publication checklist, annual calendar and release catalogue | KPI-SO4-P4-PR3-A03 |
| SO4-P4-PR4-A04 | SO4 | Pillar 4 | Cross-pillar dependency | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | C09 | PR4 | Prioritized dashboards, map services and environmental information products | KPI-SO4-P4-PR4-A04 |
| SO4-P4-PR5-A05 | SO4 | Pillar 4 | Cross-pillar dependency | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | C13 | PR5 | Reporting workflow register linking indicators, providers, calendars and verification | KPI-SO4-P4-PR5-A05 |
| SO4-P4-PR6-A06 | SO4 | Pillar 4 | Cross-pillar dependency | Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | C13 | PR6 | Feedback and correction service, researcher-access protocol and data-use report | KPI-SO4-P4-PR6-A06 |
| SO5-P5-PR1-A01 | SO5 | Pillar 5 | Cross-pillar dependency | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | C11 | PR1 | Institutional capacity baseline, role profiles and prioritized learning-needs register | KPI-SO5-P5-PR1-A01 |
| SO5-P5-PR2-A02 | SO5 | Pillar 5 | Cross-pillar dependency | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | C11 | PR2 | Competency framework, curricula and annual learning plan | KPI-SO5-P5-PR2-A02 |
| SO5-P5-PR3-A03 | SO5 | Pillar 5 | Cross-pillar dependency | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | C11 | PR3 | Completed learning cohorts, competency assessments and certification records | KPI-SO5-P5-PR3-A03 |
| SO5-P5-PR4-A04 | SO5 | Pillar 5 | Cross-pillar dependency | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | C11 | PR4 | Trainer pool, quarterly communities of practice and controlled knowledge repository | KPI-SO5-P5-PR4-A04 |
| SO5-P5-PR5-A05 | SO5 | Pillar 5 | Cross-pillar dependency | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | C12 | PR5 | Costing model, multi-year resource profile, annual budget responsibilities and funding-gap register | KPI-SO5-P5-PR5-A05 |
| SO5-P5-PR6-A06 | SO5 | Pillar 5 | Cross-pillar dependency | Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | C15 | PR6 | Operational monitoring dashboard, review cycle, succession controls and AI-readiness gate | KPI-SO5-P5-PR6-A06 |

## Annex D. Challenge-to-Action Traceability Matrix

Table 23. Challenge-to-action traceability

| ID | Challenge | Evidence | Source | Root cause | Consequence | Objective | Pillar | Response | Action IDs | Priority | Expected result |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C01 | Governance readiness is lower than technical readiness. | Governance readiness 57.6 per cent compared with interoperability readiness 74.1 per cent. | S4III p. 5; S6 pp. 7, 21 | Roles, decision rights and national procedures are not uniformly formalized. | Technology investments may proceed without accountable data governance. | SO1 | Pillar 1 | Formalize governance bodies, decision rights and programme management. | SO1-P1-PR1-A01 | Critical | Formalize governance bodies, decision rights and programme management. |
| C02 | Institutional coordination and reporting responsibilities are fragmented. | Diagnostics identify uneven coordination and continued reliance on procedural requests. | S4II pp. 63-68; S4III pp. 10-11 | No consolidated focal-point, escalation and reporting network. | Delays, duplication and unresolved cross-institutional issues. | SO1 | Pillar 1 | Activate focal points, reporting cycles and escalation routes. | SO1-P1-PR2-A02; SO1-P1-PR3-A03 | Critical | Activate focal points, reporting cycles and escalation routes. |
| C03 | Data ownership, stewardship and custodianship are not consistently assigned. | The governance framework calls for formal owner, steward and custodian roles. | S6 pp. 29-31; IP Ch. 4 | Institutional responsibilities are operational but not recorded at dataset level. | Quality, access and correction decisions lack clear accountability. | SO1 | Pillar 1 | Create a dataset-level role register and approval model. | SO1-P1-PR4-A04 | Critical | Create a dataset-level role register and approval model. |
| C04 | Legal, policy, data-sharing and SOP arrangements are incomplete or uneven. | Source assessments report limited documented SOPs and legal constraints on access. | S1 p. 27; S4II p. 72; S6 p. 32 | Institution-specific practices are not consolidated into national instruments. | Inconsistent decisions, compliance risk and avoidable delay. | SO1 | Pillar 1 | Complete legal review and approve a core governance instrument package. | SO1-P1-PR5-A05; SO1-P1-PR6-A06 | High priority | Complete legal review and approve a core governance instrument package. |
| C05 | Metadata, methodological documentation and QA/QC practices are uneven. | Data-quality readiness is 73.4 per cent, but metadata and QA/QC are not uniformly mandatory. | S4III p. 11; S6 pp. 21, 31-32 | No national minimum profile, controlled vocabulary and validation gate. | Datasets are difficult to compare, trust and reuse. | SO2 | Pillar 2 | Implement metadata, quality, reliability and provenance controls. | SO2-P2-PR3-A03; SO2-P2-PR4-A04; SO2-P2-PR5-A05 | Critical | Implement metadata, quality, reliability and provenance controls. |
| C06 | Environmental data gaps, time-series breaks and irregular update cycles remain. | Overall availability is 70.9 per cent and the documented gap is 29.1 per cent. | S4III pp. 5, 9; S6 p. 21 | No consolidated dataset registry, priority list and gap-closure plan. | Assessment and reporting may use incomplete or outdated evidence. | SO2 | Pillar 2 | Register datasets, prioritize authoritative series and manage gap closure. | SO2-P2-PR1-A01; SO2-P2-PR2-A02; SO2-P2-PR6-A06 | Critical | Register datasets, prioritize authoritative series and manage gap closure. |
| C07 | Data exchange remains partly request-based and insufficiently machine-readable. | Interoperability readiness is 74.1 per cent, but recurrent standards-based exchange is partial. | S4III pp. 5, 10-11; S6 p. 13 | Formats, identifiers, vocabularies and API requirements vary. | Manual handling, delay and inconsistent integration. | SO3 | Pillar 3 | Approve interoperability standards and pilot governed recurrent flows. | SO3-P3-PR2-A02; SO3-P3-PR4-A04; SO3-P3-PR6-A06 | High priority | Approve interoperability standards and pilot governed recurrent flows. |
| C08 | Cybersecurity, backup, disaster-recovery and continuity readiness are uneven. | The governance framework identifies resilience and continuity controls as implementation prerequisites. | S6 pp. 13, 41; S4II pp. 4, 27 | Controls and service ownership vary across systems. | Data loss, service interruption and reduced trust. | SO3 | Pillar 3 | Establish security and continuity baselines before integration scale-up. | SO3-P3-PR3-A03 | Critical | Establish security and continuity baselines before integration scale-up. |
| C09 | Public availability and open-data practice are limited and inconsistent. | Full public availability is reported at 18.8 per cent. | S6 p. 16 | Publication readiness, quality and access decisions are not integrated. | Environmental information remains difficult to discover and reuse. | SO4 | Pillar 4 | Create a controlled publication pathway for validated public data. | SO4-P4-PR3-A03; SO4-P4-PR4-A04 | High priority | Create a controlled publication pathway for validated public data. |
| C10 | Sensitivity and legal restrictions constrain access and sharing. | Data sensitivity is reported as an access constraint by 80.6 per cent and legal restrictions by 63.3 per cent. | S6 p. 32 | Classification, aggregation and approval rules are not uniformly operationalized. | Institutions may over-restrict data or release it without adequate safeguards. | SO4 | Pillar 4 | Operationalize classification, controlled access and documented legal review. | SO4-P4-PR1-A01; SO4-P4-PR2-A02 | Critical | Operationalize classification, controlled access and documented legal review. |
| C11 | Specialist skills, staffing and coordinated training remain insufficient. | EPA and stakeholder assessments identify capacity and specialist staffing gaps. | S4II p. 72; S6 p. 30 | No national competency framework and repeated role-based learning pathway. | Governance, quality and integration controls cannot be sustained. | SO5 | Pillar 5 | Assess competencies and implement role-based training and certification. | SO5-P5-PR1-A01; SO5-P5-PR2-A02; SO5-P5-PR3-A03; SO5-P5-PR4-A04 | Critical | Assess competencies and implement role-based training and certification. |
| C12 | Funding and recurrent financing are fragmented or uncertain. | Source assessments identify financing divergence and sustainability risk. | S4II p. 73; S6 p. 14 | Set-up and recurrent costs are not consistently linked to annual workplans. | Systems, standards and staff capabilities may not be maintained. | SO5 | Pillar 5 | Establish multi-year costing, annual budget responsibilities and funding-gap review. | SO5-P5-PR5-A05 | High priority | Establish multi-year costing, annual budget responsibilities and funding-gap review. |
| C13 | Environmental data use across the policy and reporting cycle is inconsistent. | The NEDMP requires stronger links between datasets, indicators, assessment and reporting. | NEDMP pp. 17, 30; S2 pp. 13-16 | Reporting workflows and indicator responsibilities are not consolidated. | Evidence may not be timely or consistently used in policy decisions. | SO4 | Pillar 4 | Standardize reporting workflows, indicators and verification. | SO4-P4-PR5-A05; SO4-P4-PR6-A06 | High priority | Standardize reporting workflows, indicators and verification. |
| C14 | Existing systems and portal options require an agreed national operating model. | The sources identify eMISK and a national portal as priorities but do not require wholesale replacement. | S4II p. 71; S6 pp. 35-38; IP Ch. 7 | Architecture, ownership and integration decisions are pending. | Duplicated platforms or technology-led procurement may occur. | SO3 | Pillar 3 | Select a federated or hybrid operating model after governance and readiness decisions. | SO3-P3-PR1-A01; SO3-P3-PR5-A05 | High priority | Select a federated or hybrid operating model after governance and readiness decisions. |
| C15 | Implementation performance, benefits and corrective actions require a common monitoring system. | The Implementation Plan establishes KPIs, annual review and adaptive management requirements. | NEDMP p. 30; S6 p. 39; IP Chs. 10, 15 | No action-level status, milestone and corrective-action register exists. | Delays and performance gaps may not trigger timely decisions. | SO5 | Pillar 5 | Operate a coded action register, dashboard and review cycle. | SO5-P5-PR6-A06 | Critical | Operate a coded action register, dashboard and review cycle. |

## Annex E. RACI Matrix

Table 24. Strategic action RACI matrix

| Action ID | Action | Steering | EPA/KEPA | Owner/steward | Legal/security | Institutions | Users/public |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Endorse the NEDMP implementation instruments and governance charter | A | R | C | C | R | I |
| SO1-P1-PR2-A02 | Activate the NEDMP programme management and coordination function | A | R | C | C | R | I |
| SO1-P1-PR3-A03 | Establish the institutional environmental data focal-point network | A | R | C | C | R | I |
| SO1-P1-PR4-A04 | Assign data owners, stewards and custodians for priority datasets | A | R | C | C | R | I |
| SO1-P1-PR5-A05 | Complete the environmental data legal and policy gap assessment | A | R | C | R | R | I |
| SO1-P1-PR6-A06 | Approve the core governance policy, SOP and data-sharing instrument package | A | R | C | R | R | I |
| SO2-P2-PR1-A01 | Complete the national environmental dataset inventory and registry | A | R | R | C | R | I |
| SO2-P2-PR2-A02 | Approve the priority and authoritative dataset list and indicator catalogue | A | R | R | C | R | I |
| SO2-P2-PR3-A03 | Issue the national environmental metadata profile, dictionaries and vocabularies | A | R | R | C | R | I |
| SO2-P2-PR4-A04 | Implement minimum QA/QC, validation and reliability grading | A | R | R | C | R | I |
| SO2-P2-PR5-A05 | Establish version control, provenance, traceability and methodology records | A | R | R | C | R | I |
| SO2-P2-PR6-A06 | Implement data-quality improvement and priority gap-closure plans | A | R | R | C | R | I |
| SO3-P3-PR1-A01 | Complete the systems inventory, digital-readiness assessment and target architecture | A | R | C | C | C | I |
| SO3-P3-PR2-A02 | Approve the national environmental data interoperability framework | A | R | C | C | C | I |
| SO3-P3-PR3-A03 | Establish identity, cybersecurity, backup and business-continuity controls | A | R | C | R | C | I |
| SO3-P3-PR4-A04 | Pilot governed recurrent data flows linked to eMISK | A | R | C | C | C | I |
| SO3-P3-PR5-A05 | Approve and implement the National Environmental Data Portal operating model | A | R | C | C | C | I |
| SO3-P3-PR6-A06 | Scale integration, migration, service management and technology renewal | A | R | C | C | C | I |
| SO4-P4-PR1-A01 | Operationalize the five-level environmental data classification model | A | R | R | R | C | C |
| SO4-P4-PR2-A02 | Implement access request, approval, release, licensing and appeal workflows | A | R | R | R | C | C |
| SO4-P4-PR3-A03 | Operate a publication-readiness and open environmental data calendar | A | R | R | C | C | C |
| SO4-P4-PR4-A04 | Develop national environmental dashboards, maps and information services | A | R | R | C | C | C |
| SO4-P4-PR5-A05 | Standardize national, SDG, MEA and State of the Environment reporting workflows | A | R | R | C | C | C |
| SO4-P4-PR6-A06 | Operate user feedback, data correction, researcher access and data-use monitoring | A | R | R | C | C | C |
| SO5-P5-PR1-A01 | Complete institutional capacity, staffing and training-needs assessments | A | R | C | C | R | I |
| SO5-P5-PR2-A02 | Approve the NEDMP competency framework and role-based learning pathways | A | R | C | C | R | I |
| SO5-P5-PR3-A03 | Deliver and certify role-based NEDMP training | A | R | C | C | R | I |
| SO5-P5-PR4-A04 | Establish train-the-trainer, communities of practice and knowledge management | A | R | C | C | R | I |
| SO5-P5-PR5-A05 | Establish multi-year resource, costing and financing arrangements | A | R | C | C | R | I |
| SO5-P5-PR6-A06 | Institutionalize monitoring, adaptive management, succession and responsible AI readiness | A | R | C | C | R | I |

## Annex F. Institutional Responsibilities Matrix

Table 25. Institutional responsibilities

| Action ID | Accountable | Responsible | Supporting | Consulted | Informed | Oversight | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO1-P1-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO1-P1-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO1-P1-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO1-P1-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO1-P1-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA NEDMP coordinating function (proposed) | Participating institutions; legal and compliance functions; national planning entities | Institutional focal points; data owners; technical working groups | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO2-P2-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO2-P2-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO2-P2-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO2-P2-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO2-P2-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO2-P2-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA data quality and registry function (proposed) | Data-producing institutions; Central Statistical Bureau; thematic specialists | Data owners; data stewards; GIS and environmental statistics teams | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO3-P3-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and technical governance bodies (proposed) | Proposed and subject to national approval |
| SO3-P3-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and technical governance bodies (proposed) | Proposed and subject to national approval |
| SO3-P3-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and technical governance bodies (proposed) | Proposed and subject to national approval |
| SO3-P3-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and technical governance bodies (proposed) | Proposed and subject to national approval |
| SO3-P3-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and technical governance bodies (proposed) | Proposed and subject to national approval |
| SO3-P3-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA technical implementation unit and system owners (proposed) | eMISK team; participating institution IT/GIS teams; cybersecurity functions | Data owners and stewards; architecture, legal and procurement specialists | Participating institutions and approved stakeholder groups | NEDMP Steering Committee and technical governance bodies (proposed) | Proposed and subject to national approval |
| SO4-P4-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO4-P4-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO4-P4-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO4-P4-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO4-P4-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO4-P4-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA portal, access and publication function (proposed) | Data owners; legal/security functions; reporting and communication teams | Researchers; civil society; private sector; public information users | Participating institutions and approved stakeholder groups | National Environmental Data Governance Committee (proposed) | Proposed and subject to national approval |
| SO5-P5-PR1-A01 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | Participating institutions and approved stakeholder groups | NEDMP Steering Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO5-P5-PR2-A02 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | Participating institutions and approved stakeholder groups | NEDMP Steering Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO5-P5-PR3-A03 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | Participating institutions and approved stakeholder groups | NEDMP Steering Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO5-P5-PR4-A04 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | Participating institutions and approved stakeholder groups | NEDMP Steering Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO5-P5-PR5-A05 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | Participating institutions and approved stakeholder groups | NEDMP Steering Committee (proposed, subject to approval) | Proposed and subject to national approval |
| SO5-P5-PR6-A06 | Environment Public Authority / Kuwait Environment Public Authority, subject to confirmation of the competent approving authority | EPA/KEPA capacity, finance and monitoring functions (proposed) | Participating institutions; training providers; finance and human-resource functions | Workstream leads; professional and academic partners; development partners | Participating institutions and approved stakeholder groups | NEDMP Steering Committee (proposed, subject to approval) | Proposed and subject to national approval |

## Annex G. Five-Year Gantt Chart

Table 26. Five-year action schedule

| Action ID | Action | Start | Completion | Y1 | Y2 | Y3 | Y4 | Y5 | Critical path |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Endorse the NEDMP implementation instruments and governance charter | 2027-01-01 | 2027-06-30 | Active |  |  |  |  | Yes |
| SO1-P1-PR2-A02 | Activate the NEDMP programme management and coordination function | 2027-01-01 | 2027-06-30 | Active |  |  |  |  | Yes |
| SO1-P1-PR3-A03 | Establish the institutional environmental data focal-point network | 2027-03-01 | 2027-09-30 | Active |  |  |  |  | Yes |
| SO1-P1-PR4-A04 | Assign data owners, stewards and custodians for priority datasets | 2027-06-01 | 2028-03-31 | Active | Active |  |  |  | Yes |
| SO1-P1-PR5-A05 | Complete the environmental data legal and policy gap assessment | 2027-04-01 | 2027-12-31 | Active |  |  |  |  | Conditional |
| SO1-P1-PR6-A06 | Approve the core governance policy, SOP and data-sharing instrument package | 2027-09-01 | 2028-06-30 | Active | Active |  |  |  | Yes |
| SO2-P2-PR1-A01 | Complete the national environmental dataset inventory and registry | 2027-03-01 | 2028-06-30 | Active | Active |  |  |  | Yes |
| SO2-P2-PR2-A02 | Approve the priority and authoritative dataset list and indicator catalogue | 2027-09-01 | 2028-09-30 | Active | Active |  |  |  | Yes |
| SO2-P2-PR3-A03 | Issue the national environmental metadata profile, dictionaries and vocabularies | 2027-09-01 | 2028-09-30 | Active | Active |  |  |  | Yes |
| SO2-P2-PR4-A04 | Implement minimum QA/QC, validation and reliability grading | 2028-01-01 | 2029-12-31 |  | Active | Active |  |  | Yes |
| SO2-P2-PR5-A05 | Establish version control, provenance, traceability and methodology records | 2028-04-01 | 2030-06-30 |  | Active | Active | Active |  | Conditional |
| SO2-P2-PR6-A06 | Implement data-quality improvement and priority gap-closure plans | 2028-07-01 | 2031-12-31 |  | Active | Active | Active | Active | Conditional |
| SO3-P3-PR1-A01 | Complete the systems inventory, digital-readiness assessment and target architecture | 2027-04-01 | 2028-03-31 | Active | Active |  |  |  | Yes |
| SO3-P3-PR2-A02 | Approve the national environmental data interoperability framework | 2027-10-01 | 2028-12-31 | Active | Active |  |  |  | Yes |
| SO3-P3-PR3-A03 | Establish identity, cybersecurity, backup and business-continuity controls | 2027-10-01 | 2030-06-30 | Active | Active | Active | Active |  | Yes |
| SO3-P3-PR4-A04 | Pilot governed recurrent data flows linked to eMISK | 2028-07-01 | 2029-12-31 |  | Active | Active |  |  | Conditional |
| SO3-P3-PR5-A05 | Approve and implement the National Environmental Data Portal operating model | 2028-01-01 | 2030-06-30 |  | Active | Active | Active |  | Conditional |
| SO3-P3-PR6-A06 | Scale integration, migration, service management and technology renewal | 2030-01-01 | 2031-12-31 |  |  |  | Active | Active | Conditional |
| SO4-P4-PR1-A01 | Operationalize the five-level environmental data classification model | 2027-04-01 | 2028-12-31 | Active | Active |  |  |  | Yes |
| SO4-P4-PR2-A02 | Implement access request, approval, release, licensing and appeal workflows | 2027-10-01 | 2029-06-30 | Active | Active | Active |  |  | Yes |
| SO4-P4-PR3-A03 | Operate a publication-readiness and open environmental data calendar | 2028-01-01 | 2030-12-31 |  | Active | Active | Active |  | Conditional |
| SO4-P4-PR4-A04 | Develop national environmental dashboards, maps and information services | 2029-01-01 | 2031-06-30 |  |  | Active | Active | Active | Conditional |
| SO4-P4-PR5-A05 | Standardize national, SDG, MEA and State of the Environment reporting workflows | 2028-07-01 | 2030-12-31 |  | Active | Active | Active |  | Conditional |
| SO4-P4-PR6-A06 | Operate user feedback, data correction, researcher access and data-use monitoring | 2029-01-01 | 2031-12-31 |  |  | Active | Active | Active | Conditional |
| SO5-P5-PR1-A01 | Complete institutional capacity, staffing and training-needs assessments | 2027-03-01 | 2027-12-31 | Active |  |  |  |  | Yes |
| SO5-P5-PR2-A02 | Approve the NEDMP competency framework and role-based learning pathways | 2027-09-01 | 2028-06-30 | Active | Active |  |  |  | Yes |
| SO5-P5-PR3-A03 | Deliver and certify role-based NEDMP training | 2028-04-01 | 2030-12-31 |  | Active | Active | Active |  | Conditional |
| SO5-P5-PR4-A04 | Establish train-the-trainer, communities of practice and knowledge management | 2028-07-01 | 2031-12-31 |  | Active | Active | Active | Active | Conditional |
| SO5-P5-PR5-A05 | Establish multi-year resource, costing and financing arrangements | 2027-06-01 | 2031-12-31 | Active | Active | Active | Active | Active | Yes |
| SO5-P5-PR6-A06 | Institutionalize monitoring, adaptive management, succession and responsible AI readiness | 2027-01-01 | 2031-12-31 | Active | Active | Active | Active | Active | Conditional |

## Annex H. Annual Milestone Schedule

Table 27. Annual milestone schedule

| Milestone ID | Action ID | Milestone | Planned date | Status | Verification | Decision gate |
| --- | --- | --- | --- | --- | --- | --- |
| M-SO1-P1-PR1-A01-01 | SO1-P1-PR1-A01 | Draft or pilot completed and reviewed | 2027-04-01 | Planned | Review record | Proceed, revise or pause |
| M-SO1-P1-PR1-A01-02 | SO1-P1-PR1-A01 | Final deliverable approved or accepted | 2027-06-30 | Planned | Approved record and implementation evidence | Close action or initiate scale-up |
| M-SO1-P1-PR2-A02-01 | SO1-P1-PR2-A02 | Draft or pilot completed and reviewed | 2027-04-01 | Planned | Review record | Proceed, revise or pause |
| M-SO1-P1-PR2-A02-02 | SO1-P1-PR2-A02 | Final deliverable approved or accepted | 2027-06-30 | Planned | Approved record and implementation evidence | Close action or initiate scale-up |
| M-SO1-P1-PR3-A03-01 | SO1-P1-PR3-A03 | Draft or pilot completed and reviewed | 2027-06-01 | Planned | Review record | Proceed, revise or pause |
| M-SO1-P1-PR3-A03-02 | SO1-P1-PR3-A03 | Final deliverable approved or accepted | 2027-09-30 | Planned | Signed nominations and focal-point register | Close action or initiate scale-up |
| M-SO1-P1-PR4-A04-01 | SO1-P1-PR4-A04 | Draft or pilot completed and reviewed | 2027-11-01 | Planned | Review record | Proceed, revise or pause |
| M-SO1-P1-PR4-A04-02 | SO1-P1-PR4-A04 | Final deliverable approved or accepted | 2028-03-31 | Planned | Approved record and implementation evidence | Close action or initiate scale-up |
| M-SO1-P1-PR5-A05-01 | SO1-P1-PR5-A05 | Draft or pilot completed and reviewed | 2027-08-01 | Planned | Review record | Proceed, revise or pause |
| M-SO1-P1-PR5-A05-02 | SO1-P1-PR5-A05 | Final deliverable approved or accepted | 2027-12-31 | Planned | Approved legal-policy gap report and response register | Close action or initiate scale-up |
| M-SO1-P1-PR6-A06-01 | SO1-P1-PR6-A06 | Draft or pilot completed and reviewed | 2028-02-01 | Planned | Review record | Proceed, revise or pause |
| M-SO1-P1-PR6-A06-02 | SO1-P1-PR6-A06 | Final deliverable approved or accepted | 2028-06-30 | Planned | Approved record and implementation evidence | Close action or initiate scale-up |
| M-SO2-P2-PR1-A01-01 | SO2-P2-PR1-A01 | Draft or pilot completed and reviewed | 2027-11-01 | Planned | Review record | Proceed, revise or pause |
| M-SO2-P2-PR1-A01-02 | SO2-P2-PR1-A01 | Final deliverable approved or accepted | 2028-06-30 | Planned | Registry export, completeness check and owner sign-off | Close action or initiate scale-up |
| M-SO2-P2-PR2-A02-01 | SO2-P2-PR2-A02 | Draft or pilot completed and reviewed | 2028-03-01 | Planned | Review record | Proceed, revise or pause |
| M-SO2-P2-PR2-A02-02 | SO2-P2-PR2-A02 | Final deliverable approved or accepted | 2028-09-30 | Planned | Approved record and implementation evidence | Close action or initiate scale-up |
| M-SO2-P2-PR3-A03-01 | SO2-P2-PR3-A03 | Draft or pilot completed and reviewed | 2028-03-01 | Planned | Review record | Proceed, revise or pause |
| M-SO2-P2-PR3-A03-02 | SO2-P2-PR3-A03 | Final deliverable approved or accepted | 2028-09-30 | Planned | Approved profile and quarterly metadata completeness report | Close action or initiate scale-up |
| M-SO2-P2-PR4-A04-01 | SO2-P2-PR4-A04 | Draft or pilot completed and reviewed | 2029-01-01 | Planned | Review record | Proceed, revise or pause |
| M-SO2-P2-PR4-A04-02 | SO2-P2-PR4-A04 | Final deliverable approved or accepted | 2029-12-31 | Planned | Validation logs, reliability register and audit sample | Close action or initiate scale-up |
| M-SO2-P2-PR5-A05-01 | SO2-P2-PR5-A05 | Draft or pilot completed and reviewed | 2029-05-01 | Planned | Review record | Proceed, revise or pause |
| M-SO2-P2-PR5-A05-02 | SO2-P2-PR5-A05 | Final deliverable approved or accepted | 2030-06-30 | Planned | Approved record and implementation evidence | Close action or initiate scale-up |
| M-SO2-P2-PR6-A06-01 | SO2-P2-PR6-A06 | Draft or pilot completed and reviewed | 2030-04-01 | Planned | Review record | Proceed, revise or pause |
| M-SO2-P2-PR6-A06-02 | SO2-P2-PR6-A06 | Final deliverable approved or accepted | 2031-12-31 | Planned | Annual gap register and approved closure evidence | Close action or initiate scale-up |
| M-SO3-P3-PR1-A01-01 | SO3-P3-PR1-A01 | Draft or pilot completed and reviewed | 2027-10-01 | Planned | Review record | Proceed, revise or pause |
| M-SO3-P3-PR1-A01-02 | SO3-P3-PR1-A01 | Final deliverable approved or accepted | 2028-03-31 | Planned | Approved systems inventory and readiness report | Close action or initiate scale-up |
| M-SO3-P3-PR2-A02-01 | SO3-P3-PR2-A02 | Draft or pilot completed and reviewed | 2028-05-01 | Planned | Review record | Proceed, revise or pause |
| M-SO3-P3-PR2-A02-02 | SO3-P3-PR2-A02 | Final deliverable approved or accepted | 2028-12-31 | Planned | Approved framework and conformance-test records | Close action or initiate scale-up |
| M-SO3-P3-PR3-A03-01 | SO3-P3-PR3-A03 | Draft or pilot completed and reviewed | 2029-02-01 | Planned | Review record | Proceed, revise or pause |
| M-SO3-P3-PR3-A03-02 | SO3-P3-PR3-A03 | Final deliverable approved or accepted | 2030-06-30 | Planned | Security assessment, access review and recovery-test reports | Close action or initiate scale-up |
| M-SO3-P3-PR4-A04-01 | SO3-P3-PR4-A04 | Draft or pilot completed and reviewed | 2029-04-01 | Planned | Review record | Proceed, revise or pause |
| M-SO3-P3-PR4-A04-02 | SO3-P3-PR4-A04 | Final deliverable approved or accepted | 2029-12-31 | Planned | Acceptance reports and operational flow monitoring | Close action or initiate scale-up |
| M-SO3-P3-PR5-A05-01 | SO3-P3-PR5-A05 | Draft or pilot completed and reviewed | 2029-04-01 | Planned | Review record | Proceed, revise or pause |
| M-SO3-P3-PR5-A05-02 | SO3-P3-PR5-A05 | Final deliverable approved or accepted | 2030-06-30 | Planned | Architecture decision record, acceptance report and service dashboard | Close action or initiate scale-up |
| M-SO3-P3-PR6-A06-01 | SO3-P3-PR6-A06 | Draft or pilot completed and reviewed | 2031-01-01 | Planned | Review record | Proceed, revise or pause |
| M-SO3-P3-PR6-A06-02 | SO3-P3-PR6-A06 | Final deliverable approved or accepted | 2031-12-31 | Planned | Service-level reports, migration sign-off and renewal plan | Close action or initiate scale-up |
| M-SO4-P4-PR1-A01-01 | SO4-P4-PR1-A01 | Draft or pilot completed and reviewed | 2028-02-01 | Planned | Review record | Proceed, revise or pause |
| M-SO4-P4-PR1-A01-02 | SO4-P4-PR1-A01 | Final deliverable approved or accepted | 2028-12-31 | Planned | Classification register and quality-assurance sample | Close action or initiate scale-up |
| M-SO4-P4-PR2-A02-01 | SO4-P4-PR2-A02 | Draft or pilot completed and reviewed | 2028-08-01 | Planned | Review record | Proceed, revise or pause |
| M-SO4-P4-PR2-A02-02 | SO4-P4-PR2-A02 | Final deliverable approved or accepted | 2029-06-30 | Planned | Access decision log, service-level report and audit sample | Close action or initiate scale-up |
| M-SO4-P4-PR3-A03-01 | SO4-P4-PR3-A03 | Draft or pilot completed and reviewed | 2029-07-01 | Planned | Review record | Proceed, revise or pause |
| M-SO4-P4-PR3-A03-02 | SO4-P4-PR3-A03 | Final deliverable approved or accepted | 2030-12-31 | Planned | Publication catalogue, release record and calendar performance report | Close action or initiate scale-up |
| M-SO4-P4-PR4-A04-01 | SO4-P4-PR4-A04 | Draft or pilot completed and reviewed | 2030-04-01 | Planned | Review record | Proceed, revise or pause |
| M-SO4-P4-PR4-A04-02 | SO4-P4-PR4-A04 | Final deliverable approved or accepted | 2031-06-30 | Planned | Service acceptance, analytics and user-testing reports | Close action or initiate scale-up |
| M-SO4-P4-PR5-A05-01 | SO4-P4-PR5-A05 | Draft or pilot completed and reviewed | 2029-10-01 | Planned | Review record | Proceed, revise or pause |
| M-SO4-P4-PR5-A05-02 | SO4-P4-PR5-A05 | Final deliverable approved or accepted | 2030-12-31 | Planned | Reporting workflow register and submission quality records | Close action or initiate scale-up |
| M-SO4-P4-PR6-A06-01 | SO4-P4-PR6-A06 | Draft or pilot completed and reviewed | 2030-07-01 | Planned | Review record | Proceed, revise or pause |
| M-SO4-P4-PR6-A06-02 | SO4-P4-PR6-A06 | Final deliverable approved or accepted | 2031-12-31 | Planned | Service log, researcher register and annual user report | Close action or initiate scale-up |
| M-SO5-P5-PR1-A01-01 | SO5-P5-PR1-A01 | Draft or pilot completed and reviewed | 2027-08-01 | Planned | Review record | Proceed, revise or pause |
| M-SO5-P5-PR1-A01-02 | SO5-P5-PR1-A01 | Final deliverable approved or accepted | 2027-12-31 | Planned | Validated institutional capacity assessments | Close action or initiate scale-up |
| M-SO5-P5-PR2-A02-01 | SO5-P5-PR2-A02 | Draft or pilot completed and reviewed | 2028-02-01 | Planned | Review record | Proceed, revise or pause |
| M-SO5-P5-PR2-A02-02 | SO5-P5-PR2-A02 | Final deliverable approved or accepted | 2028-06-30 | Planned | Approved framework, curricula and annual learning plan | Close action or initiate scale-up |
| M-SO5-P5-PR3-A03-01 | SO5-P5-PR3-A03 | Draft or pilot completed and reviewed | 2029-08-01 | Planned | Review record | Proceed, revise or pause |
| M-SO5-P5-PR3-A03-02 | SO5-P5-PR3-A03 | Final deliverable approved or accepted | 2030-12-31 | Planned | Attendance, assessment and certification records | Close action or initiate scale-up |
| M-SO5-P5-PR4-A04-01 | SO5-P5-PR4-A04 | Draft or pilot completed and reviewed | 2030-04-01 | Planned | Review record | Proceed, revise or pause |
| M-SO5-P5-PR4-A04-02 | SO5-P5-PR4-A04 | Final deliverable approved or accepted | 2031-12-31 | Planned | Trainer register, meeting records and repository audit | Close action or initiate scale-up |
| M-SO5-P5-PR5-A05-01 | SO5-P5-PR5-A05 | Draft or pilot completed and reviewed | 2029-09-01 | Planned | Review record | Proceed, revise or pause |
| M-SO5-P5-PR5-A05-02 | SO5-P5-PR5-A05 | Final deliverable approved or accepted | 2031-12-31 | Planned | Approved costing model, budget submissions and funding-gap register | Close action or initiate scale-up |
| M-SO5-P5-PR6-A06-01 | SO5-P5-PR6-A06 | Draft or pilot completed and reviewed | 2029-07-01 | Planned | Review record | Proceed, revise or pause |
| M-SO5-P5-PR6-A06-02 | SO5-P5-PR6-A06 | Final deliverable approved or accepted | 2031-12-31 | Planned | Dashboard exports, review reports and approved management responses | Close action or initiate scale-up |

## Annex I. Dependency and Critical-Path Matrix

Table 28. Dependencies and critical path

| Dependency ID | Action ID | Predecessor | Type | Critical | Risk if delayed | Response |
| --- | --- | --- | --- | --- | --- | --- |
| D-SO1-P1-PR1-A01-START | SO1-P1-PR1-A01 | National mobilization and approval | Initiation | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO1-P1-PR2-A02-SO1-P1-PR1-A01 | SO1-P1-PR2-A02 | SO1-P1-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO1-P1-PR3-A03-SO1-P1-PR1-A01 | SO1-P1-PR3-A03 | SO1-P1-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO1-P1-PR4-A04-SO1-P1-PR1-A03 | SO1-P1-PR4-A04 | SO1-P1-PR1-A03 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO1-P1-PR4-A04-SO2-P2-PR1-A01 | SO1-P1-PR4-A04 | SO2-P2-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO1-P1-PR5-A05-SO1-P1-PR1-A01 | SO1-P1-PR5-A05 | SO1-P1-PR1-A01 | Finish-to-start or decision gate | Conditional | Unverified legal interpretation or delayed cross-government review | Use competent legal authorities and clearly separate legal requirements from proposed administrative measures. |
| D-SO1-P1-PR6-A06-SO1-P1-PR1-A05 | SO1-P1-PR6-A06 | SO1-P1-PR1-A05 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO1-P1-PR6-A06-SO1-P1-PR1-A04 | SO1-P1-PR6-A06 | SO1-P1-PR1-A04 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR1-A01-SO1-P1-PR1-A03 | SO2-P2-PR1-A01 | SO1-P1-PR1-A03 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR2-A02-SO2-P2-PR1-A01 | SO2-P2-PR2-A02 | SO2-P2-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR3-A03-SO2-P2-PR1-A01 | SO2-P2-PR3-A03 | SO2-P2-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR3-A03-SO2-P2-PR1-A02 | SO2-P2-PR3-A03 | SO2-P2-PR1-A02 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR4-A04-SO2-P2-PR1-A03 | SO2-P2-PR4-A04 | SO2-P2-PR1-A03 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR4-A04-SO1-P1-PR1-A04 | SO2-P2-PR4-A04 | SO1-P1-PR1-A04 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR5-A05-SO2-P2-PR1-A03 | SO2-P2-PR5-A05 | SO2-P2-PR1-A03 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR5-A05-SO2-P2-PR1-A04 | SO2-P2-PR5-A05 | SO2-P2-PR1-A04 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR6-A06-SO2-P2-PR1-A01 | SO2-P2-PR6-A06 | SO2-P2-PR1-A01 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO2-P2-PR6-A06-SO2-P2-PR1-A04 | SO2-P2-PR6-A06 | SO2-P2-PR1-A04 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR1-A01-SO1-P1-PR1-A03 | SO3-P3-PR1-A01 | SO1-P1-PR1-A03 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR2-A02-SO3-P3-PR1-A01 | SO3-P3-PR2-A02 | SO3-P3-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR2-A02-SO2-P2-PR1-A03 | SO3-P3-PR2-A02 | SO2-P2-PR1-A03 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR3-A03-SO3-P3-PR1-A01 | SO3-P3-PR3-A03 | SO3-P3-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR3-A03-SO1-P1-PR1-A05 | SO3-P3-PR3-A03 | SO1-P1-PR1-A05 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR4-A04-SO3-P3-PR1-A02 | SO3-P3-PR4-A04 | SO3-P3-PR1-A02 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR4-A04-SO3-P3-PR1-A03 | SO3-P3-PR4-A04 | SO3-P3-PR1-A03 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR4-A04-SO4-P4-PR1-A01 | SO3-P3-PR4-A04 | SO4-P4-PR1-A01 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR5-A05-SO3-P3-PR1-A01 | SO3-P3-PR5-A05 | SO3-P3-PR1-A01 | Finish-to-start or decision gate | Conditional | Technology procurement precedes governance and service-design decisions | Use architecture and governance decision gates before procurement and release funding by stage. |
| D-SO3-P3-PR5-A05-SO1-P1-PR1-A06 | SO3-P3-PR5-A05 | SO1-P1-PR1-A06 | Finish-to-start or decision gate | Conditional | Technology procurement precedes governance and service-design decisions | Use architecture and governance decision gates before procurement and release funding by stage. |
| D-SO3-P3-PR5-A05-SO4-P4-PR1-A01 | SO3-P3-PR5-A05 | SO4-P4-PR1-A01 | Finish-to-start or decision gate | Conditional | Technology procurement precedes governance and service-design decisions | Use architecture and governance decision gates before procurement and release funding by stage. |
| D-SO3-P3-PR6-A06-SO3-P3-PR1-A04 | SO3-P3-PR6-A06 | SO3-P3-PR1-A04 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO3-P3-PR6-A06-SO3-P3-PR1-A05 | SO3-P3-PR6-A06 | SO3-P3-PR1-A05 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR1-A01-SO1-P1-PR1-A05 | SO4-P4-PR1-A01 | SO1-P1-PR1-A05 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR1-A01-SO2-P2-PR1-A01 | SO4-P4-PR1-A01 | SO2-P2-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR2-A02-SO4-P4-PR1-A01 | SO4-P4-PR2-A02 | SO4-P4-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR2-A02-SO1-P1-PR1-A06 | SO4-P4-PR2-A02 | SO1-P1-PR1-A06 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR3-A03-SO4-P4-PR1-A01 | SO4-P4-PR3-A03 | SO4-P4-PR1-A01 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR3-A03-SO2-P2-PR1-A04 | SO4-P4-PR3-A03 | SO2-P2-PR1-A04 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR4-A04-SO4-P4-PR1-A03 | SO4-P4-PR4-A04 | SO4-P4-PR1-A03 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR4-A04-SO3-P3-PR1-A05 | SO4-P4-PR4-A04 | SO3-P3-PR1-A05 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR5-A05-SO2-P2-PR1-A02 | SO4-P4-PR5-A05 | SO2-P2-PR1-A02 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR5-A05-SO3-P3-PR1-A04 | SO4-P4-PR5-A05 | SO3-P3-PR1-A04 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR6-A06-SO4-P4-PR1-A02 | SO4-P4-PR6-A06 | SO4-P4-PR1-A02 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO4-P4-PR6-A06-SO4-P4-PR1-A03 | SO4-P4-PR6-A06 | SO4-P4-PR1-A03 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR1-A01-SO1-P1-PR1-A03 | SO5-P5-PR1-A01 | SO1-P1-PR1-A03 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR2-A02-SO5-P5-PR1-A01 | SO5-P5-PR2-A02 | SO5-P5-PR1-A01 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR3-A03-SO5-P5-PR1-A02 | SO5-P5-PR3-A03 | SO5-P5-PR1-A02 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR4-A04-SO5-P5-PR1-A02 | SO5-P5-PR4-A04 | SO5-P5-PR1-A02 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR4-A04-SO5-P5-PR1-A03 | SO5-P5-PR4-A04 | SO5-P5-PR1-A03 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR5-A05-SO1-P1-PR1-A02 | SO5-P5-PR5-A05 | SO1-P1-PR1-A02 | Finish-to-start or decision gate | Yes | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR6-A06-SO1-P1-PR1-A02 | SO5-P5-PR6-A06 | SO1-P1-PR1-A02 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |
| D-SO5-P5-PR6-A06-SO5-P5-PR1-A05 | SO5-P5-PR6-A06 | SO5-P5-PR1-A05 | Finish-to-start or decision gate | Conditional | Delayed approval or insufficient institutional participation | Use a decision gate, named owner, escalation deadline and documented management response. |

## Annex J. Resource Requirements Matrix

Table 29. Resource requirements

| Action ID | Human | Technical | Institutional | Capex/recurrent | Cost | Timing | Costing responsibility | Deadline | Funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Low | 2027-01-01 to 2027-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q1 | Core government programme budget; approved technical assistance |
| SO1-P1-PR2-A02 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-01-01 to 2027-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q1 | Core government programme budget; approved technical assistance |
| SO1-P1-PR3-A03 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Low | 2027-03-01 to 2027-09-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q1 | Core government programme budget; approved technical assistance |
| SO1-P1-PR4-A04 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Low | 2027-06-01 to 2028-03-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q2 | Core government programme budget; approved technical assistance |
| SO1-P1-PR5-A05 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-04-01 to 2027-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q2 | Core government programme budget; approved technical assistance |
| SO1-P1-PR6-A06 | Programme manager; governance specialist; legal adviser; institutional focal points | Decision register; role register; document repository; workflow tools | NEDMP Steering Committee and National Environmental Data Governance Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-09-01 to 2028-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q3 | Core government programme budget; approved technical assistance |
| SO2-P2-PR1-A01 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-03-01 to 2028-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q1 | Core government data-management budget; targeted technical assistance |
| SO2-P2-PR2-A02 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Low | 2027-09-01 to 2028-09-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q3 | Core government data-management budget; targeted technical assistance |
| SO2-P2-PR3-A03 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-09-01 to 2028-09-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q3 | Core government data-management budget; targeted technical assistance |
| SO2-P2-PR4-A04 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2028-01-01 to 2029-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q1 | Core government data-management budget; targeted technical assistance |
| SO2-P2-PR5-A05 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2028-04-01 to 2030-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q2 | Core government data-management budget; targeted technical assistance |
| SO2-P2-PR6-A06 | Metadata specialist; QA/QC specialist; data stewards; environmental subject-matter experts | Dataset registry; metadata catalogue; validation tools; controlled vocabularies | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Capital and recurrent | High | 2028-07-01 to 2031-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q3 | Core government data-management budget; targeted technical assistance |
| SO3-P3-PR1-A01 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | NEDMP Steering Committee and technical governance bodies (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-04-01 to 2028-03-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q2 | Approved capital programme; recurrent ICT budget; partner technical assistance |
| SO3-P3-PR2-A02 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | NEDMP Steering Committee and technical governance bodies (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-10-01 to 2028-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q4 | Approved capital programme; recurrent ICT budget; partner technical assistance |
| SO3-P3-PR3-A03 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | NEDMP Steering Committee and technical governance bodies (proposed); focal points; approved instruments and procurement arrangements | Capital and recurrent | High | 2027-10-01 to 2030-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q4 | Approved capital programme; recurrent ICT budget; partner technical assistance |
| SO3-P3-PR4-A04 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | NEDMP Steering Committee and technical governance bodies (proposed); focal points; approved instruments and procurement arrangements | Capital and recurrent | High | 2028-07-01 to 2029-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q3 | Approved capital programme; recurrent ICT budget; partner technical assistance |
| SO3-P3-PR5-A05 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | NEDMP Steering Committee and technical governance bodies (proposed); focal points; approved instruments and procurement arrangements | Capital and recurrent | High | 2028-01-01 to 2030-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q1 | Approved capital programme; recurrent ICT budget; partner technical assistance |
| SO3-P3-PR6-A06 | Enterprise architect; database and API developers; GIS specialist; information-security specialist | eMISK; APIs; metadata harvesting; identity management; hosting, backup and recovery services | NEDMP Steering Committee and technical governance bodies (proposed); focal points; approved instruments and procurement arrangements | Capital and recurrent | High | 2030-01-01 to 2031-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2030 Q1 | Approved capital programme; recurrent ICT budget; partner technical assistance |
| SO4-P4-PR1-A01 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Low | 2027-04-01 to 2028-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q2 | Core public-information budget; approved digital-service funding |
| SO4-P4-PR2-A02 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-10-01 to 2029-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q4 | Core public-information budget; approved digital-service funding |
| SO4-P4-PR3-A03 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2028-01-01 to 2030-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q1 | Core public-information budget; approved digital-service funding |
| SO4-P4-PR4-A04 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Capital and recurrent | High | 2029-01-01 to 2031-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2029 Q1 | Core public-information budget; approved digital-service funding |
| SO4-P4-PR5-A05 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2028-07-01 to 2030-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q3 | Core public-information budget; approved digital-service funding |
| SO4-P4-PR6-A06 | Access officer; data steward; legal adviser; communications and reporting specialists | Classification register; access workflow; publication catalogue; dashboards and map services | National Environmental Data Governance Committee (proposed); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2029-01-01 to 2031-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2029 Q1 | Core public-information budget; approved digital-service funding |
| SO5-P5-PR1-A01 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | NEDMP Steering Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-03-01 to 2027-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q1 | Annual government budgets; approved partner support; institutional training allocations |
| SO5-P5-PR2-A02 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | NEDMP Steering Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-09-01 to 2028-06-30 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q3 | Annual government budgets; approved partner support; institutional training allocations |
| SO5-P5-PR3-A03 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | NEDMP Steering Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Capital and recurrent | High | 2028-04-01 to 2030-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q2 | Annual government budgets; approved partner support; institutional training allocations |
| SO5-P5-PR4-A04 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | NEDMP Steering Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2028-07-01 to 2031-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2028 Q3 | Annual government budgets; approved partner support; institutional training allocations |
| SO5-P5-PR5-A05 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | NEDMP Steering Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-06-01 to 2031-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q2 | Annual government budgets; approved partner support; institutional training allocations |
| SO5-P5-PR6-A06 | Capacity-development specialist; trainers; programme finance specialist; M&E specialist | Learning platform; knowledge repository; monitoring dashboard; budget and workforce tools | NEDMP Steering Committee (proposed, subject to approval); focal points; approved instruments and procurement arrangements | Primarily recurrent with defined set-up costs | Medium | 2027-01-01 to 2031-12-31 | EPA/KEPA programme and finance functions, subject to approval | 2027 Q1 | Annual government budgets; approved partner support; institutional training allocations |

## Annex K. Indicative Budget Template

Table 30. Indicative budget template

| Action ID | Category | Band | Y1 | Y2 | Y3 | Y4 | Y5 | Recurrent note | Approval |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Primarily recurrent with defined set-up costs | Low | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO1-P1-PR2-A02 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO1-P1-PR3-A03 | Primarily recurrent with defined set-up costs | Low | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO1-P1-PR4-A04 | Primarily recurrent with defined set-up costs | Low | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO1-P1-PR5-A05 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO1-P1-PR6-A06 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO2-P2-PR1-A01 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO2-P2-PR2-A02 | Primarily recurrent with defined set-up costs | Low | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO2-P2-PR3-A03 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO2-P2-PR4-A04 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO2-P2-PR5-A05 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO2-P2-PR6-A06 | Capital and recurrent | High | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO3-P3-PR1-A01 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO3-P3-PR2-A02 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO3-P3-PR3-A03 | Capital and recurrent | High | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO3-P3-PR4-A04 | Capital and recurrent | High | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO3-P3-PR5-A05 | Capital and recurrent | High | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO3-P3-PR6-A06 | Capital and recurrent | High | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO4-P4-PR1-A01 | Primarily recurrent with defined set-up costs | Low | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO4-P4-PR2-A02 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO4-P4-PR3-A03 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO4-P4-PR4-A04 | Capital and recurrent | High | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO4-P4-PR5-A05 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO4-P4-PR6-A06 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO5-P5-PR1-A01 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO5-P5-PR2-A02 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO5-P5-PR3-A03 | Capital and recurrent | High | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO5-P5-PR4-A04 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO5-P5-PR5-A05 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |
| SO5-P5-PR6-A06 | Primarily recurrent with defined set-up costs | Medium | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | TBD through detailed costing | Identify recurrent ownership before procurement or scale-up. | Requires budget approval |

## Annex L. KPI Register

Table 31. KPI register

| KPI ID | Name | SO | Pillar | Level | Baseline | Target | Date | Source | Frequency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KPI-SO1-P1-PR1-A01 | Governance charter endorsed and first decision calendar issued by 2027-06-30 | SO1 | Pillar 1 | Output/Outcome | Implementation governance not yet formally approved | Governance charter endorsed and first decision calendar issued by 2027-06-30 | 2027-06-30 | Approved record and implementation evidence | Quarterly |
| KPI-SO1-P1-PR2-A02 | Programme coordination function operating with monthly delivery review by 2027-06-30 | SO1 | Pillar 1 | Output/Outcome | Baseline to be established during inception | Programme coordination function operating with monthly delivery review by 2027-06-30 | 2027-06-30 | Approved record and implementation evidence | Quarterly |
| KPI-SO1-P1-PR3-A03 | All priority participating institutions nominate a focal point by 2027-09-30 | SO1 | Pillar 1 | Output/Outcome | Coverage to be established at mobilization | All priority participating institutions nominate a focal point by 2027-09-30 | 2027-09-30 | Signed nominations and focal-point register | Quarterly |
| KPI-SO1-P1-PR4-A04 | Owner, steward and custodian assigned for 100 per cent of priority datasets by 2028-03-31 | SO1 | Pillar 1 | Output/Outcome | No consolidated national role register | Owner, steward and custodian assigned for 100 per cent of priority datasets by 2028-03-31 | 2028-03-31 | Approved record and implementation evidence | Quarterly |
| KPI-SO1-P1-PR5-A05 | Gap assessment completed and management response approved by 2027-12-31 | SO1 | Pillar 1 | Output/Outcome | Requirements are dispersed across sources and institutional procedures | Gap assessment completed and management response approved by 2027-12-31 | 2027-12-31 | Approved legal-policy gap report and response register | Quarterly |
| KPI-SO1-P1-PR6-A06 | Core instrument package approved and used by all pilot institutions by 2028-06-30 | SO1 | Pillar 1 | Output/Outcome | Documented SOPs and agreements are uneven | Core instrument package approved and used by all pilot institutions by 2028-06-30 | 2028-06-30 | Approved record and implementation evidence | Quarterly |
| KPI-SO2-P2-PR1-A01 | 100 per cent of priority datasets registered by 2028-06-30 | SO2 | Pillar 2 | Output/Outcome | No consolidated national registry; source assessments provide partial inventories | 100 per cent of priority datasets registered by 2028-06-30 | 2028-06-30 | Registry export, completeness check and owner sign-off | Quarterly |
| KPI-SO2-P2-PR2-A02 | Priority list and catalogue approved, with annual review, by 2028-09-30 | SO2 | Pillar 2 | Output/Outcome | Priority datasets and indicator responsibilities are not consolidated | Priority list and catalogue approved, with annual review, by 2028-09-30 | 2028-09-30 | Approved record and implementation evidence | Quarterly |
| KPI-SO2-P2-PR3-A03 | Mandatory metadata complete for at least 90 per cent of priority datasets by 2029-12-31 | SO2 | Pillar 2 | Output/Outcome | Metadata documentation is uneven | Mandatory metadata complete for at least 90 per cent of priority datasets by 2029-12-31 | 2028-09-30 | Approved profile and quarterly metadata completeness report | Quarterly |
| KPI-SO2-P2-PR4-A04 | At least 85 per cent of priority datasets pass minimum QA/QC by 2029-12-31 | SO2 | Pillar 2 | Output/Outcome | Data-quality readiness 73.4 per cent; practices are not uniform | At least 85 per cent of priority datasets pass minimum QA/QC by 2029-12-31 | 2029-12-31 | Validation logs, reliability register and audit sample | Quarterly |
| KPI-SO2-P2-PR5-A05 | Traceability record complete for 100 per cent of priority datasets by 2030-06-30 | SO2 | Pillar 2 | Output/Outcome | Version and methodology documentation varies by institution | Traceability record complete for 100 per cent of priority datasets by 2030-06-30 | 2030-06-30 | Approved record and implementation evidence | Quarterly with annual consolidation |
| KPI-SO2-P2-PR6-A06 | All critical dataset gaps have an approved treatment and annual status report by 2031-12-31 | SO2 | Pillar 2 | Output/Outcome | Environmental data gap 29.1 per cent | All critical dataset gaps have an approved treatment and annual status report by 2031-12-31 | 2031-12-31 | Annual gap register and approved closure evidence | Quarterly with annual consolidation |
| KPI-SO3-P3-PR1-A01 | All priority systems assessed and architecture principles approved by 2028-03-31 | SO3 | Pillar 3 | Output/Outcome | Source reports provide partial system mapping | All priority systems assessed and architecture principles approved by 2028-03-31 | 2028-03-31 | Approved systems inventory and readiness report | Quarterly |
| KPI-SO3-P3-PR2-A02 | Framework approved and applied to all new integration projects by 2028-12-31 | SO3 | Pillar 3 | Output/Outcome | Exchange is active but only partly standardized | Framework approved and applied to all new integration projects by 2028-12-31 | 2028-12-31 | Approved framework and conformance-test records | Quarterly |
| KPI-SO3-P3-PR3-A03 | All priority repositories document controls and complete recovery testing by 2030-06-30 | SO3 | Pillar 3 | Output/Outcome | Resilience arrangements are uneven across institutions | All priority repositories document controls and complete recovery testing by 2030-06-30 | 2030-06-30 | Security assessment, access review and recovery-test reports | Quarterly with annual consolidation |
| KPI-SO3-P3-PR4-A04 | At least 10 recurrent priority data flows pass acceptance testing by 2029-12-31 | SO3 | Pillar 3 | Output/Outcome | Recurrent machine-readable flows are partial | At least 10 recurrent priority data flows pass acceptance testing by 2029-12-31 | 2029-12-31 | Acceptance reports and operational flow monitoring | Quarterly |
| KPI-SO3-P3-PR5-A05 | Operating model approved by 2028-12-31 and minimum services operational by 2030-06-30 | SO3 | Pillar 3 | Output/Outcome | Portal priority is established; operating model is not approved | Operating model approved by 2028-12-31 and minimum services operational by 2030-06-30 | 2030-06-30 | Architecture decision record, acceptance report and service dashboard | Quarterly with annual consolidation |
| KPI-SO3-P3-PR6-A06 | All approved priority flows operate under service levels and renewal plans by 2031-12-31 | SO3 | Pillar 3 | Output/Outcome | To be established after integration pilots | All approved priority flows operate under service levels and renewal plans by 2031-12-31 | 2031-12-31 | Service-level reports, migration sign-off and renewal plan | Quarterly |
| KPI-SO4-P4-PR1-A01 | 100 per cent of priority datasets classified by 2028-12-31 | SO4 | Pillar 4 | Output/Outcome | No uniform national classification model is operational | 100 per cent of priority datasets classified by 2028-12-31 | 2028-12-31 | Classification register and quality-assurance sample | Quarterly |
| KPI-SO4-P4-PR2-A02 | 100 per cent of formal access decisions logged through the workflow by 2029-06-30 | SO4 | Pillar 4 | Output/Outcome | Access processes are institution-specific and request-based | 100 per cent of formal access decisions logged through the workflow by 2029-06-30 | 2029-06-30 | Access decision log, service-level report and audit sample | Quarterly |
| KPI-SO4-P4-PR3-A03 | All datasets classified as public have an approved publication decision and schedule by 2030-12-31 | SO4 | Pillar 4 | Output/Outcome | Full public availability 18.8 per cent | All datasets classified as public have an approved publication decision and schedule by 2030-12-31 | 2030-12-31 | Publication catalogue, release record and calendar performance report | Quarterly with annual consolidation |
| KPI-SO4-P4-PR4-A04 | At least five priority thematic services operational and accessibility-tested by 2031-06-30 | SO4 | Pillar 4 | Output/Outcome | Existing services are distributed and not governed through one catalogue | At least five priority thematic services operational and accessibility-tested by 2031-06-30 | 2031-06-30 | Service acceptance, analytics and user-testing reports | Quarterly with annual consolidation |
| KPI-SO4-P4-PR5-A05 | 100 per cent of priority recurring reports have documented data flows and responsible providers by 2030-12-31 | SO4 | Pillar 4 | Output/Outcome | Reporting responsibilities and data flows are not consolidated | 100 per cent of priority recurring reports have documented data flows and responsible providers by 2030-12-31 | 2030-12-31 | Reporting workflow register and submission quality records | Quarterly with annual consolidation |
| KPI-SO4-P4-PR6-A06 | All public services provide tracked feedback and annual use reporting by 2031-12-31 | SO4 | Pillar 4 | Output/Outcome | Feedback and correction mechanisms are uneven | All public services provide tracked feedback and annual use reporting by 2031-12-31 | 2031-12-31 | Service log, researcher register and annual user report | Quarterly with annual consolidation |
| KPI-SO5-P5-PR1-A01 | All priority institutions complete the capacity baseline by 2027-12-31 | SO5 | Pillar 5 | Output/Outcome | Source assessments identify gaps but no consolidated competency baseline | All priority institutions complete the capacity baseline by 2027-12-31 | 2027-12-31 | Validated institutional capacity assessments | Quarterly |
| KPI-SO5-P5-PR2-A02 | Competency framework approved and annual learning plan funded by 2028-06-30 | SO5 | Pillar 5 | Output/Outcome | Training is fragmented and not linked to common role profiles | Competency framework approved and annual learning plan funded by 2028-06-30 | 2028-06-30 | Approved framework, curricula and annual learning plan | Quarterly |
| KPI-SO5-P5-PR3-A03 | At least 80 per cent of designated focal points, stewards and technical staff complete required modules by 2030-12-31 | SO5 | Pillar 5 | Output/Outcome | Baseline number and competency level to be confirmed in capacity assessment | At least 80 per cent of designated focal points, stewards and technical staff complete required modules by 2030-12-31 | 2030-12-31 | Attendance, assessment and certification records | Quarterly with annual consolidation |
| KPI-SO5-P5-PR4-A04 | National trainer pool established and communities meet quarterly from 2029 onward | SO5 | Pillar 5 | Output/Outcome | No consolidated NEDMP trainer pool or knowledge repository | National trainer pool established and communities meet quarterly from 2029 onward | 2031-12-31 | Trainer register, meeting records and repository audit | Quarterly with annual consolidation |
| KPI-SO5-P5-PR5-A05 | Annual NEDMP resource plan and recurrent-cost review completed from 2028 onward | SO5 | Pillar 5 | Output/Outcome | Funding arrangements and recurrent needs are not consolidated | Annual NEDMP resource plan and recurrent-cost review completed from 2028 onward | 2031-12-31 | Approved costing model, budget submissions and funding-gap register | Quarterly with annual consolidation |
| KPI-SO5-P5-PR6-A06 | Quarterly reviews, annual management responses and final evaluation completed through 2031 | SO5 | Pillar 5 | Output/Outcome | Implementation-level KPIs exist; no action-level integrated tracker | Quarterly reviews, annual management responses and final evaluation completed through 2031 | 2031-12-31 | Dashboard exports, review reports and approved management responses | Quarterly with annual consolidation |

## Annex M. KPI Metadata Sheets

Table 32. KPI metadata sheets

| KPI ID | Definition | Purpose | Method | Baseline | Target | Unit | Provider | Reporting institution | Disaggregation | Limitations | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KPI-SO1-P1-PR1-A01 | Measures completion and operational use of approved governance charter, endorsement record and decision calendar. | Confirm progress toward A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Implementation governance not yet formally approved | Governance charter endorsed and first decision calendar issued by 2027-06-30 | Action-specific count, proportion or completion status | EPA/KEPA NEDMP coordinating function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO1-P1-PR2-A02 | Measures completion and operational use of operational programme charter, workplan, issue register and reporting calendar. | Confirm progress toward A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Baseline to be established during inception | Programme coordination function operating with monthly delivery review by 2027-06-30 | Action-specific count, proportion or completion status | EPA/KEPA NEDMP coordinating function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO1-P1-PR3-A03 | Measures completion and operational use of approved focal-point register, role profile and engagement schedule. | Confirm progress toward A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Coverage to be established at mobilization | All priority participating institutions nominate a focal point by 2027-09-30 | Action-specific count, proportion or completion status | EPA/KEPA NEDMP coordinating function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO1-P1-PR4-A04 | Measures completion and operational use of dataset-level responsibility and decision-rights register. | Confirm progress toward A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | No consolidated national role register | Owner, steward and custodian assigned for 100 per cent of priority datasets by 2028-03-31 | Action-specific count, proportion or completion status | EPA/KEPA NEDMP coordinating function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO1-P1-PR5-A05 | Measures completion and operational use of legal-policy gap report and prioritized amendment or guidance register. | Confirm progress toward A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Requirements are dispersed across sources and institutional procedures | Gap assessment completed and management response approved by 2027-12-31 | Action-specific count, proportion or completion status | EPA/KEPA NEDMP coordinating function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO1-P1-PR6-A06 | Measures completion and operational use of governance policy, core sop library, agreement templates and compliance checklist. | Confirm progress toward A nationally coordinated, role-based environmental data governance system operates with traceable decisions and accountability. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Documented SOPs and agreements are uneven | Core instrument package approved and used by all pilot institutions by 2028-06-30 | Action-specific count, proportion or completion status | EPA/KEPA NEDMP coordinating function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO2-P2-PR1-A01 | Measures completion and operational use of national registry of priority datasets, owners, sources, update cycles and gaps. | Confirm progress toward Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | No consolidated national registry; source assessments provide partial inventories | 100 per cent of priority datasets registered by 2028-06-30 | Action-specific count, proportion or completion status | EPA/KEPA data quality and registry function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO2-P2-PR2-A02 | Measures completion and operational use of approved priority dataset list and environmental indicator catalogue. | Confirm progress toward Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Priority datasets and indicator responsibilities are not consolidated | Priority list and catalogue approved, with annual review, by 2028-09-30 | Action-specific count, proportion or completion status | EPA/KEPA data quality and registry function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO2-P2-PR3-A03 | Measures completion and operational use of minimum metadata profile, data dictionary template and controlled vocabularies. | Confirm progress toward Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Metadata documentation is uneven | Mandatory metadata complete for at least 90 per cent of priority datasets by 2029-12-31 | Action-specific count, proportion or completion status | EPA/KEPA data quality and registry function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO2-P2-PR4-A04 | Measures completion and operational use of national quality-control standard, validation checklist and reliability register. | Confirm progress toward Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Data-quality readiness 73.4 per cent; practices are not uniform | At least 85 per cent of priority datasets pass minimum QA/QC by 2029-12-31 | Action-specific count, proportion or completion status | EPA/KEPA data quality and registry function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO2-P2-PR5-A05 | Measures completion and operational use of provenance and methodology record linked to each priority dataset. | Confirm progress toward Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Version and methodology documentation varies by institution | Traceability record complete for 100 per cent of priority datasets by 2030-06-30 | Action-specific count, proportion or completion status | EPA/KEPA data quality and registry function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO2-P2-PR6-A06 | Measures completion and operational use of annual thematic quality and gap-closure plans with tracked corrective actions. | Confirm progress toward Priority environmental data are documented, quality-assured, comparable and fit for assessment, reporting and reuse. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Environmental data gap 29.1 per cent | All critical dataset gaps have an approved treatment and annual status report by 2031-12-31 | Action-specific count, proportion or completion status | EPA/KEPA data quality and registry function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO3-P3-PR1-A01 | Measures completion and operational use of systems inventory, readiness scorecard and approved target architecture principles. | Confirm progress toward Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Source reports provide partial system mapping | All priority systems assessed and architecture principles approved by 2028-03-31 | Action-specific count, proportion or completion status | EPA/KEPA technical implementation unit and system owners (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO3-P3-PR2-A02 | Measures completion and operational use of interoperability framework covering formats, apis, identifiers, spatial and statistical exchange. | Confirm progress toward Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Exchange is active but only partly standardized | Framework approved and applied to all new integration projects by 2028-12-31 | Action-specific count, proportion or completion status | EPA/KEPA technical implementation unit and system owners (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO3-P3-PR3-A03 | Measures completion and operational use of minimum security and continuity control baseline with tested recovery plans. | Confirm progress toward Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Resilience arrangements are uneven across institutions | All priority repositories document controls and complete recovery testing by 2030-06-30 | Action-specific count, proportion or completion status | EPA/KEPA technical implementation unit and system owners (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO3-P3-PR4-A04 | Measures completion and operational use of validated integration pilots with metadata, qa/qc, classification and audit controls. | Confirm progress toward Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Recurrent machine-readable flows are partial | At least 10 recurrent priority data flows pass acceptance testing by 2029-12-31 | Action-specific count, proportion or completion status | EPA/KEPA technical implementation unit and system owners (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO3-P3-PR5-A05 | Measures completion and operational use of approved federated or hybrid operating model and operational minimum viable portal services. | Confirm progress toward Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Portal priority is established; operating model is not approved | Operating model approved by 2028-12-31 and minimum services operational by 2030-06-30 | Action-specific count, proportion or completion status | EPA/KEPA technical implementation unit and system owners (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO3-P3-PR6-A06 | Measures completion and operational use of scaled integration portfolio, migration records, service levels and renewal plan. | Confirm progress toward Priority environmental data flows move securely between systems through agreed standards and governed integration services. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | To be established after integration pilots | All approved priority flows operate under service levels and renewal plans by 2031-12-31 | Action-specific count, proportion or completion status | EPA/KEPA technical implementation unit and system owners (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO4-P4-PR1-A01 | Measures completion and operational use of approved classification policy, assessment tool and classification register. | Confirm progress toward Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | No uniform national classification model is operational | 100 per cent of priority datasets classified by 2028-12-31 | Action-specific count, proportion or completion status | EPA/KEPA portal, access and publication function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO4-P4-PR2-A02 | Measures completion and operational use of controlled access workflow with decision log, conditions, licensing and appeal route. | Confirm progress toward Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Access processes are institution-specific and request-based | 100 per cent of formal access decisions logged through the workflow by 2029-06-30 | Action-specific count, proportion or completion status | EPA/KEPA portal, access and publication function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO4-P4-PR3-A03 | Measures completion and operational use of approved publication checklist, annual calendar and release catalogue. | Confirm progress toward Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Full public availability 18.8 per cent | All datasets classified as public have an approved publication decision and schedule by 2030-12-31 | Action-specific count, proportion or completion status | EPA/KEPA portal, access and publication function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO4-P4-PR4-A04 | Measures completion and operational use of prioritized dashboards, map services and environmental information products. | Confirm progress toward Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Existing services are distributed and not governed through one catalogue | At least five priority thematic services operational and accessibility-tested by 2031-06-30 | Action-specific count, proportion or completion status | EPA/KEPA portal, access and publication function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO4-P4-PR5-A05 | Measures completion and operational use of reporting workflow register linking indicators, providers, calendars and verification. | Confirm progress toward Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Reporting responsibilities and data flows are not consolidated | 100 per cent of priority recurring reports have documented data flows and responsible providers by 2030-12-31 | Action-specific count, proportion or completion status | EPA/KEPA portal, access and publication function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO4-P4-PR6-A06 | Measures completion and operational use of feedback and correction service, researcher-access protocol and data-use report. | Confirm progress toward Environmental data are shared and published through proportionate, transparent and legally reviewed access pathways. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Feedback and correction mechanisms are uneven | All public services provide tracked feedback and annual use reporting by 2031-12-31 | Action-specific count, proportion or completion status | EPA/KEPA portal, access and publication function (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO5-P5-PR1-A01 | Measures completion and operational use of institutional capacity baseline, role profiles and prioritized learning-needs register. | Confirm progress toward Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Source assessments identify gaps but no consolidated competency baseline | All priority institutions complete the capacity baseline by 2027-12-31 | Action-specific count, proportion or completion status | EPA/KEPA capacity, finance and monitoring functions (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO5-P5-PR2-A02 | Measures completion and operational use of competency framework, curricula and annual learning plan. | Confirm progress toward Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Training is fragmented and not linked to common role profiles | Competency framework approved and annual learning plan funded by 2028-06-30 | Action-specific count, proportion or completion status | EPA/KEPA capacity, finance and monitoring functions (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO5-P5-PR3-A03 | Measures completion and operational use of completed learning cohorts, competency assessments and certification records. | Confirm progress toward Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Baseline number and competency level to be confirmed in capacity assessment | At least 80 per cent of designated focal points, stewards and technical staff complete required modules by 2030-12-31 | Action-specific count, proportion or completion status | EPA/KEPA capacity, finance and monitoring functions (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO5-P5-PR4-A04 | Measures completion and operational use of trainer pool, quarterly communities of practice and controlled knowledge repository. | Confirm progress toward Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | No consolidated NEDMP trainer pool or knowledge repository | National trainer pool established and communities meet quarterly from 2029 onward | Action-specific count, proportion or completion status | EPA/KEPA capacity, finance and monitoring functions (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO5-P5-PR5-A05 | Measures completion and operational use of costing model, multi-year resource profile, annual budget responsibilities and funding-gap register. | Confirm progress toward Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Funding arrangements and recurrent needs are not consolidated | Annual NEDMP resource plan and recurrent-cost review completed from 2028 onward | Action-specific count, proportion or completion status | EPA/KEPA capacity, finance and monitoring functions (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |
| KPI-SO5-P5-PR6-A06 | Measures completion and operational use of operational monitoring dashboard, review cycle, succession controls and ai-readiness gate. | Confirm progress toward Institutions retain the skills, financing, knowledge and continuity arrangements required to sustain the NEDMP. | Count or proportion meeting the approved completion and verification criteria; denominator confirmed in the Year 1 baseline where required. | Implementation-level KPIs exist; no action-level integrated tracker | Quarterly reviews, annual management responses and final evaluation completed through 2031 | Action-specific count, proportion or completion status | EPA/KEPA capacity, finance and monitoring functions (proposed) | EPA/KEPA NEDMP programme management function (proposed) | Institution, dataset, thematic area or user group where applicable | Baseline and denominator require confirmation during inception for actions without a consolidated national register. | Competent authorities validate proposed roles, approve resources and participating institutions provide evidence on schedule. |

## Annex N. Annual Target Matrix

Table 33. Annual target matrix

| KPI ID | Action ID | Baseline | Y1 | Y2 | Y3 | Y4 | Y5 | Final date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KPI-SO1-P1-PR1-A01 | SO1-P1-PR1-A01 | Implementation governance not yet formally approved | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Governance charter endorsed and first decision calendar issued by 2027-06-30 | 2027-06-30 |
| KPI-SO1-P1-PR2-A02 | SO1-P1-PR2-A02 | Baseline to be established during inception | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Programme coordination function operating with monthly delivery review by 2027-06-30 | 2027-06-30 |
| KPI-SO1-P1-PR3-A03 | SO1-P1-PR3-A03 | Coverage to be established at mobilization | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All priority participating institutions nominate a focal point by 2027-09-30 | 2027-09-30 |
| KPI-SO1-P1-PR4-A04 | SO1-P1-PR4-A04 | No consolidated national role register | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Owner, steward and custodian assigned for 100 per cent of priority datasets by 2028-03-31 | 2028-03-31 |
| KPI-SO1-P1-PR5-A05 | SO1-P1-PR5-A05 | Requirements are dispersed across sources and institutional procedures | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Gap assessment completed and management response approved by 2027-12-31 | 2027-12-31 |
| KPI-SO1-P1-PR6-A06 | SO1-P1-PR6-A06 | Documented SOPs and agreements are uneven | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Core instrument package approved and used by all pilot institutions by 2028-06-30 | 2028-06-30 |
| KPI-SO2-P2-PR1-A01 | SO2-P2-PR1-A01 | No consolidated national registry; source assessments provide partial inventories | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | 100 per cent of priority datasets registered by 2028-06-30 | 2028-06-30 |
| KPI-SO2-P2-PR2-A02 | SO2-P2-PR2-A02 | Priority datasets and indicator responsibilities are not consolidated | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Priority list and catalogue approved, with annual review, by 2028-09-30 | 2028-09-30 |
| KPI-SO2-P2-PR3-A03 | SO2-P2-PR3-A03 | Metadata documentation is uneven | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Mandatory metadata complete for at least 90 per cent of priority datasets by 2029-12-31 | 2028-09-30 |
| KPI-SO2-P2-PR4-A04 | SO2-P2-PR4-A04 | Data-quality readiness 73.4 per cent; practices are not uniform | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | At least 85 per cent of priority datasets pass minimum QA/QC by 2029-12-31 | 2029-12-31 |
| KPI-SO2-P2-PR5-A05 | SO2-P2-PR5-A05 | Version and methodology documentation varies by institution | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Traceability record complete for 100 per cent of priority datasets by 2030-06-30 | 2030-06-30 |
| KPI-SO2-P2-PR6-A06 | SO2-P2-PR6-A06 | Environmental data gap 29.1 per cent | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All critical dataset gaps have an approved treatment and annual status report by 2031-12-31 | 2031-12-31 |
| KPI-SO3-P3-PR1-A01 | SO3-P3-PR1-A01 | Source reports provide partial system mapping | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All priority systems assessed and architecture principles approved by 2028-03-31 | 2028-03-31 |
| KPI-SO3-P3-PR2-A02 | SO3-P3-PR2-A02 | Exchange is active but only partly standardized | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Framework approved and applied to all new integration projects by 2028-12-31 | 2028-12-31 |
| KPI-SO3-P3-PR3-A03 | SO3-P3-PR3-A03 | Resilience arrangements are uneven across institutions | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All priority repositories document controls and complete recovery testing by 2030-06-30 | 2030-06-30 |
| KPI-SO3-P3-PR4-A04 | SO3-P3-PR4-A04 | Recurrent machine-readable flows are partial | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | At least 10 recurrent priority data flows pass acceptance testing by 2029-12-31 | 2029-12-31 |
| KPI-SO3-P3-PR5-A05 | SO3-P3-PR5-A05 | Portal priority is established; operating model is not approved | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Operating model approved by 2028-12-31 and minimum services operational by 2030-06-30 | 2030-06-30 |
| KPI-SO3-P3-PR6-A06 | SO3-P3-PR6-A06 | To be established after integration pilots | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All approved priority flows operate under service levels and renewal plans by 2031-12-31 | 2031-12-31 |
| KPI-SO4-P4-PR1-A01 | SO4-P4-PR1-A01 | No uniform national classification model is operational | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | 100 per cent of priority datasets classified by 2028-12-31 | 2028-12-31 |
| KPI-SO4-P4-PR2-A02 | SO4-P4-PR2-A02 | Access processes are institution-specific and request-based | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | 100 per cent of formal access decisions logged through the workflow by 2029-06-30 | 2029-06-30 |
| KPI-SO4-P4-PR3-A03 | SO4-P4-PR3-A03 | Full public availability 18.8 per cent | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All datasets classified as public have an approved publication decision and schedule by 2030-12-31 | 2030-12-31 |
| KPI-SO4-P4-PR4-A04 | SO4-P4-PR4-A04 | Existing services are distributed and not governed through one catalogue | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | At least five priority thematic services operational and accessibility-tested by 2031-06-30 | 2031-06-30 |
| KPI-SO4-P4-PR5-A05 | SO4-P4-PR5-A05 | Reporting responsibilities and data flows are not consolidated | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | 100 per cent of priority recurring reports have documented data flows and responsible providers by 2030-12-31 | 2030-12-31 |
| KPI-SO4-P4-PR6-A06 | SO4-P4-PR6-A06 | Feedback and correction mechanisms are uneven | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All public services provide tracked feedback and annual use reporting by 2031-12-31 | 2031-12-31 |
| KPI-SO5-P5-PR1-A01 | SO5-P5-PR1-A01 | Source assessments identify gaps but no consolidated competency baseline | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | All priority institutions complete the capacity baseline by 2027-12-31 | 2027-12-31 |
| KPI-SO5-P5-PR2-A02 | SO5-P5-PR2-A02 | Training is fragmented and not linked to common role profiles | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Competency framework approved and annual learning plan funded by 2028-06-30 | 2028-06-30 |
| KPI-SO5-P5-PR3-A03 | SO5-P5-PR3-A03 | Baseline number and competency level to be confirmed in capacity assessment | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | At least 80 per cent of designated focal points, stewards and technical staff complete required modules by 2030-12-31 | 2030-12-31 |
| KPI-SO5-P5-PR4-A04 | SO5-P5-PR4-A04 | No consolidated NEDMP trainer pool or knowledge repository | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | National trainer pool established and communities meet quarterly from 2029 onward | 2031-12-31 |
| KPI-SO5-P5-PR5-A05 | SO5-P5-PR5-A05 | Funding arrangements and recurrent needs are not consolidated | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Annual NEDMP resource plan and recurrent-cost review completed from 2028 onward | 2031-12-31 |
| KPI-SO5-P5-PR6-A06 | SO5-P5-PR6-A06 | Implementation-level KPIs exist; no action-level integrated tracker | Baseline confirmed and responsible roles assigned | Core instrument, standard or pilot completed | Operational use demonstrated and corrective actions tracked | Institutional coverage or service scale expanded | Quarterly reviews, annual management responses and final evaluation completed through 2031 | 2031-12-31 |

## Annex O. Status Reporting Template

Table 34. Status reporting template

| Action ID | Status date | Status | % | Schedule | Budget | Deliverable | Issue | Corrective action | Next review |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| [Action ID] | yyyy-mm-dd | Select category | 0-100 | On track / variance | Status | Status | Constraint | Action, owner and due date | yyyy-mm-dd |

## Annex P. Quarterly Progress Report Template

Table 35. Quarterly progress report template

| Section | Minimum content | Evidence |
| --- | --- | --- |
| Executive summary | Results, exceptions and decisions required | Dashboard and decision log |
| Action performance | Milestones, completion, target and variance | Task and KPI records |
| Resources | Budget, staffing, procurement and gaps | Finance and resource register |
| Risk and corrective action | New, changed and closed risks and actions | Risk and corrective-action logs |

## Annex Q. Corrective Action Log

Table 36. Corrective action log template

| Corrective ID | Action ID | Issue | Root cause | Corrective action | Owner | Due date | Status | Closure evidence |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CA-[Action ID]-01 | [Action ID] | Issue | Validated cause | Specific response | Named approved owner | yyyy-mm-dd | Open | Evidence reference |

## Annex R. Risk Register

Table 37. Action-level risk register

| Risk ID | Action ID | Risk | Cause | Consequence | Likelihood | Impact | Inherent | Mitigation | Owner | Residual | Trigger | Frequency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-SO1-P1-PR1-A01 | SO1-P1-PR1-A01 | Delayed approval or insufficient institutional participation | Roles, decision rights and national procedures are not uniformly formalized. | Technology investments may proceed without accountable data governance. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA NEDMP coordinating function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO1-P1-PR2-A02 | SO1-P1-PR2-A02 | Delayed approval or insufficient institutional participation | No consolidated focal-point, escalation and reporting network. | Delays, duplication and unresolved cross-institutional issues. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA NEDMP coordinating function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO1-P1-PR3-A03 | SO1-P1-PR3-A03 | Delayed approval or insufficient institutional participation | No consolidated focal-point, escalation and reporting network. | Delays, duplication and unresolved cross-institutional issues. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA NEDMP coordinating function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO1-P1-PR4-A04 | SO1-P1-PR4-A04 | Delayed approval or insufficient institutional participation | Institutional responsibilities are operational but not recorded at dataset level. | Quality, access and correction decisions lack clear accountability. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA NEDMP coordinating function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO1-P1-PR5-A05 | SO1-P1-PR5-A05 | Unverified legal interpretation or delayed cross-government review | Institution-specific practices are not consolidated into national instruments. | Inconsistent decisions, compliance risk and avoidable delay. | Medium | High | High | Use competent legal authorities and clearly separate legal requirements from proposed administrative measures. | EPA/KEPA NEDMP coordinating function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO1-P1-PR6-A06 | SO1-P1-PR6-A06 | Delayed approval or insufficient institutional participation | Institution-specific practices are not consolidated into national instruments. | Inconsistent decisions, compliance risk and avoidable delay. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA NEDMP coordinating function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO2-P2-PR1-A01 | SO2-P2-PR1-A01 | Delayed approval or insufficient institutional participation | No consolidated dataset registry, priority list and gap-closure plan. | Assessment and reporting may use incomplete or outdated evidence. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA data quality and registry function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO2-P2-PR2-A02 | SO2-P2-PR2-A02 | Delayed approval or insufficient institutional participation | No consolidated dataset registry, priority list and gap-closure plan. | Assessment and reporting may use incomplete or outdated evidence. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA data quality and registry function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO2-P2-PR3-A03 | SO2-P2-PR3-A03 | Delayed approval or insufficient institutional participation | No national minimum profile, controlled vocabulary and validation gate. | Datasets are difficult to compare, trust and reuse. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA data quality and registry function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO2-P2-PR4-A04 | SO2-P2-PR4-A04 | Delayed approval or insufficient institutional participation | No national minimum profile, controlled vocabulary and validation gate. | Datasets are difficult to compare, trust and reuse. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA data quality and registry function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO2-P2-PR5-A05 | SO2-P2-PR5-A05 | Delayed approval or insufficient institutional participation | No national minimum profile, controlled vocabulary and validation gate. | Datasets are difficult to compare, trust and reuse. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA data quality and registry function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO2-P2-PR6-A06 | SO2-P2-PR6-A06 | Delayed approval or insufficient institutional participation | No consolidated dataset registry, priority list and gap-closure plan. | Assessment and reporting may use incomplete or outdated evidence. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA data quality and registry function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO3-P3-PR1-A01 | SO3-P3-PR1-A01 | Delayed approval or insufficient institutional participation | Architecture, ownership and integration decisions are pending. | Duplicated platforms or technology-led procurement may occur. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA technical implementation unit and system owners (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO3-P3-PR2-A02 | SO3-P3-PR2-A02 | Delayed approval or insufficient institutional participation | Formats, identifiers, vocabularies and API requirements vary. | Manual handling, delay and inconsistent integration. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA technical implementation unit and system owners (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO3-P3-PR3-A03 | SO3-P3-PR3-A03 | Delayed approval or insufficient institutional participation | Controls and service ownership vary across systems. | Data loss, service interruption and reduced trust. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA technical implementation unit and system owners (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO3-P3-PR4-A04 | SO3-P3-PR4-A04 | Delayed approval or insufficient institutional participation | Formats, identifiers, vocabularies and API requirements vary. | Manual handling, delay and inconsistent integration. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA technical implementation unit and system owners (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO3-P3-PR5-A05 | SO3-P3-PR5-A05 | Technology procurement precedes governance and service-design decisions | Architecture, ownership and integration decisions are pending. | Duplicated platforms or technology-led procurement may occur. | Medium | High | High | Use architecture and governance decision gates before procurement and release funding by stage. | EPA/KEPA technical implementation unit and system owners (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO3-P3-PR6-A06 | SO3-P3-PR6-A06 | Delayed approval or insufficient institutional participation | Formats, identifiers, vocabularies and API requirements vary. | Manual handling, delay and inconsistent integration. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA technical implementation unit and system owners (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO4-P4-PR1-A01 | SO4-P4-PR1-A01 | Delayed approval or insufficient institutional participation | Classification, aggregation and approval rules are not uniformly operationalized. | Institutions may over-restrict data or release it without adequate safeguards. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA portal, access and publication function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO4-P4-PR2-A02 | SO4-P4-PR2-A02 | Delayed approval or insufficient institutional participation | Classification, aggregation and approval rules are not uniformly operationalized. | Institutions may over-restrict data or release it without adequate safeguards. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA portal, access and publication function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO4-P4-PR3-A03 | SO4-P4-PR3-A03 | Delayed approval or insufficient institutional participation | Publication readiness, quality and access decisions are not integrated. | Environmental information remains difficult to discover and reuse. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA portal, access and publication function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO4-P4-PR4-A04 | SO4-P4-PR4-A04 | Delayed approval or insufficient institutional participation | Publication readiness, quality and access decisions are not integrated. | Environmental information remains difficult to discover and reuse. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA portal, access and publication function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO4-P4-PR5-A05 | SO4-P4-PR5-A05 | Delayed approval or insufficient institutional participation | Reporting workflows and indicator responsibilities are not consolidated. | Evidence may not be timely or consistently used in policy decisions. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA portal, access and publication function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO4-P4-PR6-A06 | SO4-P4-PR6-A06 | Delayed approval or insufficient institutional participation | Reporting workflows and indicator responsibilities are not consolidated. | Evidence may not be timely or consistently used in policy decisions. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA portal, access and publication function (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO5-P5-PR1-A01 | SO5-P5-PR1-A01 | Delayed approval or insufficient institutional participation | No national competency framework and repeated role-based learning pathway. | Governance, quality and integration controls cannot be sustained. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA capacity, finance and monitoring functions (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO5-P5-PR2-A02 | SO5-P5-PR2-A02 | Delayed approval or insufficient institutional participation | No national competency framework and repeated role-based learning pathway. | Governance, quality and integration controls cannot be sustained. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA capacity, finance and monitoring functions (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO5-P5-PR3-A03 | SO5-P5-PR3-A03 | Delayed approval or insufficient institutional participation | No national competency framework and repeated role-based learning pathway. | Governance, quality and integration controls cannot be sustained. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA capacity, finance and monitoring functions (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO5-P5-PR4-A04 | SO5-P5-PR4-A04 | Delayed approval or insufficient institutional participation | No national competency framework and repeated role-based learning pathway. | Governance, quality and integration controls cannot be sustained. | Medium | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA capacity, finance and monitoring functions (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO5-P5-PR5-A05 | SO5-P5-PR5-A05 | Delayed approval or insufficient institutional participation | Set-up and recurrent costs are not consistently linked to annual workplans. | Systems, standards and staff capabilities may not be maintained. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA capacity, finance and monitoring functions (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |
| R-SO5-P5-PR6-A06 | SO5-P5-PR6-A06 | Delayed approval or insufficient institutional participation | No action-level status, milestone and corrective-action register exists. | Delays and performance gaps may not trigger timely decisions. | High | High | High | Use a decision gate, named owner, escalation deadline and documented management response. | EPA/KEPA capacity, finance and monitoring functions (proposed) | Medium | Missed milestone, unresolved approval, incomplete evidence or funding gap | Monthly for critical actions; otherwise quarterly |

## Annex S. Assumptions Log

Table 38. Assumptions log template

| Assumption ID | Action ID | Assumption | Owner | Validation date | Status | Impact if false | Response |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AS-[Action ID]-01 | [Action ID] | Planning assumption | Approved owner | yyyy-mm-dd | Open | Schedule, scope, cost or target impact | Contingency or change request |

## Annex T. Decision and Issue Log

Table 39. Decision and issue log template

| Record ID | Type | Action ID | Description | Raised | Owner | Decision due | Decision / response | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DI-001 | Decision / Issue | [Action ID] | Description | yyyy-mm-dd | Owner | yyyy-mm-dd | Decision and rationale | Open |

## Annex U. Source-Evidence Traceability Matrix

Table 40. Source-evidence traceability

| Action ID | Action | Finding | Source | Section | Page | Statistic | Objective | Pillar | IP link |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SO1-P1-PR1-A01 | Endorse the NEDMP implementation instruments and governance charter | Governance readiness is lower than technical readiness. | S1 pp. 7, 29; S6 p. 29; IP Chs. 3-4 | Coded source references and Implementation Plan chapters | S1 pp. 7, 29; S6 p. 29; IP Chs. 3-4 | Governance readiness 57.6 per cent compared with interoperability readiness 74.1 per cent. | SO1 | Pillar 1 | WS1; governance-first phased sequence |
| SO1-P1-PR2-A02 | Activate the NEDMP programme management and coordination function | Institutional coordination and reporting responsibilities are fragmented. | S4II pp. 63-68; IP Chs. 4, 7 | Coded source references and Implementation Plan chapters | S4II pp. 63-68; IP Chs. 4, 7 | Diagnostics identify uneven coordination and continued reliance on procedural requests. | SO1 | Pillar 1 | WS1; governance-first phased sequence |
| SO1-P1-PR3-A03 | Establish the institutional environmental data focal-point network | Institutional coordination and reporting responsibilities are fragmented. | S4II pp. 63-68; S6 p. 29; IP Ch. 4 | Coded source references and Implementation Plan chapters | S4II pp. 63-68; S6 p. 29; IP Ch. 4 | Diagnostics identify uneven coordination and continued reliance on procedural requests. | SO1 | Pillar 1 | WS1; governance-first phased sequence |
| SO1-P1-PR4-A04 | Assign data owners, stewards and custodians for priority datasets | Data ownership, stewardship and custodianship are not consistently assigned. | S6 pp. 29-31; IP Chs. 4-5 | Coded source references and Implementation Plan chapters | S6 pp. 29-31; IP Chs. 4-5 | The governance framework calls for formal owner, steward and custodian roles. | SO1 | Pillar 1 | WS1; governance-first phased sequence |
| SO1-P1-PR5-A05 | Complete the environmental data legal and policy gap assessment | Legal, policy, data-sharing and SOP arrangements are incomplete or uneven. | S2 pp. 14-16; S6 p. 32; IP Chs. 2, 4 | Coded source references and Implementation Plan chapters | S2 pp. 14-16; S6 p. 32; IP Chs. 2, 4 | Source assessments report limited documented SOPs and legal constraints on access. | SO1 | Pillar 1 | WS1; governance-first phased sequence |
| SO1-P1-PR6-A06 | Approve the core governance policy, SOP and data-sharing instrument package | Legal, policy, data-sharing and SOP arrangements are incomplete or uneven. | S1 p. 27; S4II p. 72; S6 pp. 29-32 | Coded source references and Implementation Plan chapters | S1 p. 27; S4II p. 72; S6 pp. 29-32 | Source assessments report limited documented SOPs and legal constraints on access. | SO1 | Pillar 1 | WS1; governance-first phased sequence |
| SO2-P2-PR1-A01 | Complete the national environmental dataset inventory and registry | Environmental data gaps, time-series breaks and irregular update cycles remain. | S4III pp. 5, 9; S6 pp. 21, 31; IP Ch. 5 | Coded source references and Implementation Plan chapters | S4III pp. 5, 9; S6 pp. 21, 31; IP Ch. 5 | Overall availability is 70.9 per cent and the documented gap is 29.1 per cent. | SO2 | Pillar 2 | WS2; governance-first phased sequence |
| SO2-P2-PR2-A02 | Approve the priority and authoritative dataset list and indicator catalogue | Environmental data gaps, time-series breaks and irregular update cycles remain. | S4I pp. 31, 34, 39; S4II p. 72; IP Ch. 5 | Coded source references and Implementation Plan chapters | S4I pp. 31, 34, 39; S4II p. 72; IP Ch. 5 | Overall availability is 70.9 per cent and the documented gap is 29.1 per cent. | SO2 | Pillar 2 | WS2; governance-first phased sequence |
| SO2-P2-PR3-A03 | Issue the national environmental metadata profile, dictionaries and vocabularies | Metadata, methodological documentation and QA/QC practices are uneven. | S4III p. 11; S6 pp. 31-32; ISO 19115-1 | Coded source references and Implementation Plan chapters | S4III p. 11; S6 pp. 31-32; ISO 19115-1 | Data-quality readiness is 73.4 per cent, but metadata and QA/QC are not uniformly mandatory. | SO2 | Pillar 2 | WS2; governance-first phased sequence |
| SO2-P2-PR4-A04 | Implement minimum QA/QC, validation and reliability grading | Metadata, methodological documentation and QA/QC practices are uneven. | S4III p. 11; S6 pp. 31-32; IP Ch. 5 | Coded source references and Implementation Plan chapters | S4III p. 11; S6 pp. 31-32; IP Ch. 5 | Data-quality readiness is 73.4 per cent, but metadata and QA/QC are not uniformly mandatory. | SO2 | Pillar 2 | WS2; governance-first phased sequence |
| SO2-P2-PR5-A05 | Establish version control, provenance, traceability and methodology records | Metadata, methodological documentation and QA/QC practices are uneven. | S6 pp. 31-32; S3 pp. 23-24 | Coded source references and Implementation Plan chapters | S6 pp. 31-32; S3 pp. 23-24 | Data-quality readiness is 73.4 per cent, but metadata and QA/QC are not uniformly mandatory. | SO2 | Pillar 2 | WS2; governance-first phased sequence |
| SO2-P2-PR6-A06 | Implement data-quality improvement and priority gap-closure plans | Environmental data gaps, time-series breaks and irregular update cycles remain. | S4I pp. 38-42; S4III pp. 5, 9; S6 p. 21 | Coded source references and Implementation Plan chapters | S4I pp. 38-42; S4III pp. 5, 9; S6 p. 21 | Overall availability is 70.9 per cent and the documented gap is 29.1 per cent. | SO2 | Pillar 2 | WS2; governance-first phased sequence |
| SO3-P3-PR1-A01 | Complete the systems inventory, digital-readiness assessment and target architecture | Existing systems and portal options require an agreed national operating model. | S4I pp. 12-22; S4II pp. 67-71; S6 pp. 35-38 | Coded source references and Implementation Plan chapters | S4I pp. 12-22; S4II pp. 67-71; S6 pp. 35-38 | The sources identify eMISK and a national portal as priorities but do not require wholesale replacement. | SO3 | Pillar 3 | WS3; governance-first phased sequence |
| SO3-P3-PR2-A02 | Approve the national environmental data interoperability framework | Data exchange remains partly request-based and insufficiently machine-readable. | S4III pp. 10-11; S6 p. 13; SDMX 3.1 | Coded source references and Implementation Plan chapters | S4III pp. 10-11; S6 p. 13; SDMX 3.1 | Interoperability readiness is 74.1 per cent, but recurrent standards-based exchange is partial. | SO3 | Pillar 3 | WS3; governance-first phased sequence |
| SO3-P3-PR3-A03 | Establish identity, cybersecurity, backup and business-continuity controls | Cybersecurity, backup, disaster-recovery and continuity readiness are uneven. | S6 pp. 13, 41; ISO/IEC 27001:2022; ISO 22301:2019 | Coded source references and Implementation Plan chapters | S6 pp. 13, 41; ISO/IEC 27001:2022; ISO 22301:2019 | The governance framework identifies resilience and continuity controls as implementation prerequisites. | SO3 | Pillar 3 | WS3; governance-first phased sequence |
| SO3-P3-PR4-A04 | Pilot governed recurrent data flows linked to eMISK | Data exchange remains partly request-based and insufficiently machine-readable. | S4II p. 71; S6 pp. 35-38; IP Ch. 7 | Coded source references and Implementation Plan chapters | S4II p. 71; S6 pp. 35-38; IP Ch. 7 | Interoperability readiness is 74.1 per cent, but recurrent standards-based exchange is partial. | SO3 | Pillar 3 | WS3; governance-first phased sequence |
| SO3-P3-PR5-A05 | Approve and implement the National Environmental Data Portal operating model | Existing systems and portal options require an agreed national operating model. | S4II p. 71; S6 pp. 35-38; IP Ch. 7 | Coded source references and Implementation Plan chapters | S4II p. 71; S6 pp. 35-38; IP Ch. 7 | The sources identify eMISK and a national portal as priorities but do not require wholesale replacement. | SO3 | Pillar 3 | WS3; governance-first phased sequence |
| SO3-P3-PR6-A06 | Scale integration, migration, service management and technology renewal | Data exchange remains partly request-based and insufficiently machine-readable. | S6 pp. 35-41; IP Chs. 7, 14 | Coded source references and Implementation Plan chapters | S6 pp. 35-41; IP Chs. 7, 14 | Interoperability readiness is 74.1 per cent, but recurrent standards-based exchange is partial. | SO3 | Pillar 3 | WS3; governance-first phased sequence |
| SO4-P4-PR1-A01 | Operationalize the five-level environmental data classification model | Sensitivity and legal restrictions constrain access and sharing. | S6 pp. 27-28, 32; IP Ch. 7 | Coded source references and Implementation Plan chapters | S6 pp. 27-28, 32; IP Ch. 7 | Data sensitivity is reported as an access constraint by 80.6 per cent and legal restrictions by 63.3 per cent. | SO4 | Pillar 4 | WS4; governance-first phased sequence |
| SO4-P4-PR2-A02 | Implement access request, approval, release, licensing and appeal workflows | Sensitivity and legal restrictions constrain access and sharing. | S6 pp. 27-32; IP Ch. 7 | Coded source references and Implementation Plan chapters | S6 pp. 27-32; IP Ch. 7 | Data sensitivity is reported as an access constraint by 80.6 per cent and legal restrictions by 63.3 per cent. | SO4 | Pillar 4 | WS4; governance-first phased sequence |
| SO4-P4-PR3-A03 | Operate a publication-readiness and open environmental data calendar | Public availability and open-data practice are limited and inconsistent. | S6 p. 16; S4II p. 71; IP Ch. 7 | Coded source references and Implementation Plan chapters | S6 p. 16; S4II p. 71; IP Ch. 7 | Full public availability is reported at 18.8 per cent. | SO4 | Pillar 4 | WS4; governance-first phased sequence |
| SO4-P4-PR4-A04 | Develop national environmental dashboards, maps and information services | Public availability and open-data practice are limited and inconsistent. | S4I pp. 12-22; S6 pp. 35-38 | Coded source references and Implementation Plan chapters | S4I pp. 12-22; S6 pp. 35-38 | Full public availability is reported at 18.8 per cent. | SO4 | Pillar 4 | WS4; governance-first phased sequence |
| SO4-P4-PR5-A05 | Standardize national, SDG, MEA and State of the Environment reporting workflows | Environmental data use across the policy and reporting cycle is inconsistent. | NEDMP pp. 17, 30; S2 pp. 13-16; S4I pp. 31-39 | Coded source references and Implementation Plan chapters | NEDMP pp. 17, 30; S2 pp. 13-16; S4I pp. 31-39 | The NEDMP requires stronger links between datasets, indicators, assessment and reporting. | SO4 | Pillar 4 | WS4; governance-first phased sequence |
| SO4-P4-PR6-A06 | Operate user feedback, data correction, researcher access and data-use monitoring | Environmental data use across the policy and reporting cycle is inconsistent. | S3 pp. 23-26; S6 pp. 27-32 | Coded source references and Implementation Plan chapters | S3 pp. 23-26; S6 pp. 27-32 | The NEDMP requires stronger links between datasets, indicators, assessment and reporting. | SO4 | Pillar 4 | WS4; governance-first phased sequence |
| SO5-P5-PR1-A01 | Complete institutional capacity, staffing and training-needs assessments | Specialist skills, staffing and coordinated training remain insufficient. | S4II p. 72; S6 p. 30; IP Ch. 12 | Coded source references and Implementation Plan chapters | S4II p. 72; S6 p. 30; IP Ch. 12 | EPA and stakeholder assessments identify capacity and specialist staffing gaps. | SO5 | Pillar 5 | WS5; governance-first phased sequence |
| SO5-P5-PR2-A02 | Approve the NEDMP competency framework and role-based learning pathways | Specialist skills, staffing and coordinated training remain insufficient. | S1 p. 21; S4II p. 72; S6 p. 30 | Coded source references and Implementation Plan chapters | S1 p. 21; S4II p. 72; S6 p. 30 | EPA and stakeholder assessments identify capacity and specialist staffing gaps. | SO5 | Pillar 5 | WS5; governance-first phased sequence |
| SO5-P5-PR3-A03 | Deliver and certify role-based NEDMP training | Specialist skills, staffing and coordinated training remain insufficient. | S4II p. 72; S6 p. 30; IP Ch. 12 | Coded source references and Implementation Plan chapters | S4II p. 72; S6 p. 30; IP Ch. 12 | EPA and stakeholder assessments identify capacity and specialist staffing gaps. | SO5 | Pillar 5 | WS5; governance-first phased sequence |
| SO5-P5-PR4-A04 | Establish train-the-trainer, communities of practice and knowledge management | Specialist skills, staffing and coordinated training remain insufficient. | S1 p. 21; S6 pp. 30, 39-41 | Coded source references and Implementation Plan chapters | S1 p. 21; S6 pp. 30, 39-41 | EPA and stakeholder assessments identify capacity and specialist staffing gaps. | SO5 | Pillar 5 | WS5; governance-first phased sequence |
| SO5-P5-PR5-A05 | Establish multi-year resource, costing and financing arrangements | Funding and recurrent financing are fragmented or uncertain. | S4II p. 73; S6 pp. 14, 39; IP Ch. 8 | Coded source references and Implementation Plan chapters | S4II p. 73; S6 pp. 14, 39; IP Ch. 8 | Source assessments identify financing divergence and sustainability risk. | SO5 | Pillar 5 | WS5; governance-first phased sequence |
| SO5-P5-PR6-A06 | Institutionalize monitoring, adaptive management, succession and responsible AI readiness | Implementation performance, benefits and corrective actions require a common monitoring system. | NEDMP p. 30; S6 pp. 39-41; IP Chs. 10, 14-15 | Coded source references and Implementation Plan chapters | NEDMP p. 30; S6 pp. 39-41; IP Chs. 10, 14-15 | The Implementation Plan establishes KPIs, annual review and adaptive management requirements. | SO5 | Pillar 5 | WS5; governance-first phased sequence |

## Annex V. Glossary

Table 41. Strategic Action Plan glossary

| Term | Definition |
| --- | --- |
| Action | A time-bound intervention that delivers a measurable result under an NEDMP programme. |
| Task | An assignable activity that produces a defined working output or deliverable. |
| Milestone | A dated decision, review, acceptance or completion point. |
| Baseline | The verified starting value or status against which progress is measured. |
| Traffic light | A standardized visual status: grey, green, amber, red or blue. |
| Data steward | The operational role responsible for metadata, quality, versioning and dataset status. |
| Critical path | The sequence of dependencies whose delay affects dependent action completion. |

## Annex W. References

Table 42. References

Reference

DAMA International (2017). DAMA-DMBOK: Data Management Body of Knowledge, 2nd edition. Technics Publications.

European Commission (2007). Directive 2007/2/EC establishing INSPIRE.

ISO (2014, amended 2018 and 2020). ISO 19115-1:2014 Geographic information - Metadata - Part 1: Fundamentals. Current published edition; revision work is under way.

ISO (2018). ISO 31000:2018 Risk management - Guidelines. Current published edition; revision work is under way.

ISO (2019, amended 2024). ISO 22301:2019 Security and resilience - Business continuity management systems - Requirements.

ISO/IEC (2022, amended 2024). ISO/IEC 27001:2022 Information security management systems - Requirements.

KEPA/UNEP (2026). Kuwait National Environmental Data Management Plan (NEDMP).

KEPA/UNEP (2026). NEDMP Implementation Plan.

KEPA/UNEP (2026). Section I - Mandate, Vision, Objectives and Pillars of Environmental Data Governance.

KEPA/UNEP (2026). Section II - Alignment with Key National and International Frameworks.

KEPA/UNEP (2026). Section III - Benchmarking Best Practices in Environmental Data Governance.

KEPA/UNEP (2026). Section IV Part I - Situational Analysis: Current State of National Environmental Data.

KEPA/UNEP (2026). Section IV Part II - Situational Analysis Assessment of EPA/KEPA Departments.

KEPA/UNEP (2026). Section IV Part III - All-Stakeholder Assessment.

KEPA/UNEP (2026). NEDMP Data Classification and Governance Framework.

SDMX Sponsoring Organizations (2025). SDMX Technical Specifications, version 3.1.

UN Statistics Division (2013). Framework for the Development of Environment Statistics.

United Nations et al. (2012). System of Environmental-Economic Accounting 2012 - Central Framework.

UNEP (2026). Global Environmental Data Strategy. Submitted to UNEA-7 as UNEP/EA.7/INF/5; implementation began in 2026.

Wilkinson, M. D. et al. (2016). The FAIR Guiding Principles for scientific data management and stewardship. Scientific Data.